## Part-I
Monitoring Format for Monthly Report Under
National Rural Employment Gurantee Act (N.R.E.G.A.)
Employment Generation Under NREGA During the year 2007-08 Up to the Month of November' 07
Jalpaiguri District
Sl. No. | Name of the Block | No. of Application Registered as on 15-09-07 | No. of Application Registerd | Differece | No. of households issued job cards (till the reporting month) |  |  |  | Job Card Issued up to 15-09-2007 | Differece | No. of Household who have demanded wage employment |  |  | No. of Household who have provided wage employment (out of col. 3) |  |  | Out of total of column 4, no. of individual applicants provided employment during the month | No. of women provided employment out of col. 5 | cummulative number of households which have completed 100 days of employment
[5 empty] | SCs | STs | Others | Total |  |  | Households demanded up to previous month | Addl. Household demand during month | Total | Households provided up to previous month | Addl. Household provided during month | Total
| 1 |  | 1(A) |  | 2 | [5 empty] | 3 |  |  | 4 |  |  | 5 | 6 | 7
1 | Alipurduar-I | 32208 | 32089 | -119 | 18262 | 7204 | 6618 | 32084 | 31693 | 391 | 17792 | 1245 | 19037 | 17720 | 1317 | 19037 | 19343 | 6625 | 4
2 | Alipurduar-II | 38165 | 37553 | -612 | 18793 | 7954 | 10752 | 37499 | 37481 | 18 | 23025 | 0 | 23025 | 21939 | 0 | 21939 | 16454.25 | 5758.9875 | 0
3 | Dhupguri | 72500 | 72500 | 0 | 38050 | 15567 | 18159 | 71776 | 70238 | 1538 | 53446 | 5801 | 59247 | 51375 | 5298 | 56673 | 10310 | 4147 | 0
4 | Falakata | 41253 | 41075 | -178 | 19455 | 8079 | 13187 | 40721 | 40615 | 106 | 19445 | 1395 | 20840 | 19445 | 1395 | 20840 | 3349 | 925 | 2
5 | Kalchini | 47636 | 47416 | -220 | 5510 | 28486 | 12270 | 46266 | 46517 | -251 | 32128 | 322 | 32450 | 30464 | 762 | 31226 | 762 | 171 | 0
6 | Kumargram | 35739 | 35753 | 14 | 14362 | 12303 | 9043 | 35708 | 35184 | 524 | 20949 | 1553 | 22502 | 19296 | 1572 | 20868 | 6333 | 2369 | 0
7 | Madarihat-Birpara | 33751 | 33734 | -17 | 7860 | 13865 | 11888 | 33613 | 33477 | 136 | 21530 | 1081 | 22611 | 20601 | 1840 | 20631 | 8830 | 3088.1 | 0
8 | Mal | 49332 | 49259 | -73 | 15970 | 16631 | 15785 | 48386 | 48301 | 85 | 19824 | 1594 | 19824 | 19341 | 825 | 20166 | 2567 | 1047 | 0
9 | Matiali | 20112 | 20289 | 177 | 5085 | 9333 | 5701 | 20119 | 19517 | 602 | 12536 | 1523 | 12536 | 12154 | 1620 | 13774 | 3871 | 1511 | 0
10 | Maynaguri | 59266 | 58700 | -566 | 44194 | 876 | 13396 | 58466 | 58333 | 133 | 29436 | 3536 | 29832 | 29083 | 3346 | 32429 | 9317 | 2298 | 19
11 | Nagrakata | 21455 | 21649 | 194 | 4644 | 10567 | 6333 | 21544 | 21416 | 128 | 12637 | 194 | 12831 | 12637 | 194 | 12831 | 194 | 119 | 0
12 | Rajganj | 40600 | 40654 | 54 | 24146 | 2323 | 14185 | 40654 | 40472 | 182 | 18346 | 578 | 18924 | 17887 | 576 | 18463 | 2407 | 835 | 2
13 | Sadar | 54722 | 54395 | -327 | 36463 | 4195 | 13520 | 54178 | 54103 | 75 | 37194 | 2244 | 39438 | 34602 | 2165 | 36767 | 6459 | 3088 | 1
| Total | 546739 | 545066 | -1673 | 252794 | 137383 | 150837 | 541014 | 537347 | 3667 | 318288 | 21066 | 333097 | 306544 | 20910 | 325644 | 90196.25 | 31982.0875 | 28
20949
| APD-II Block reduced 612 nos. of registered HH and 1 Job Card from prev. month without showing any reason. | nos. of job card reduced from prev. month.

## Part-II
Monitoring Format for Monthly Report Under
National Rural Employment Gurantee Act (N.R.E.G.A.)
Employment Generation Under NREGA During the year 2007-08 Up to the Month of November' 07
Jalpaiguri District
Sl. No. | Name of the Block | Employment Generated ( In lakh Mandays) Cummulative for the year
|  | SCs |  | STs |  | Other |  | Total |  | No. of Days Worked by Women in Col. 10 | No. of land reform / IAY beneficiary out of col. 9 | Disabled beneficiaries out of col. 9
|  | Households | Persondays | Households | Persondays | Households | Persondays | Households (3+5+7) | Persondays (4+6+8)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
1 | Alipurduar-I | 11149 | 1.4006 | 4141 | 0.43927 | 3747 | 0.50034 | 19037 | 2.3402 | 82463 | 2232 | 35 | 163.8126 | 99.6613 | 64.1513 | 7.2928
2 | Alipurduar-II | 12429.21 | 0.51802 | 2640.77 | 0.30935 | 7913.02 | 0.77593 | 22983 | 1.6033 | 32120.5518 | 2890.8497 | 1284.8221 | 112.2308 | 56.7555 | 55.4753 | 4.2694
3 | Dhupguri | 23284 | 1.7881 | 15729 | 1.9299 | 17660 | 1.1911 | 56673 | 4.9092 | 134402 | 3717 | 105 | 343.6433 | 124.8266 | 218.8167 | 6.7713
4 | Falakata | 8588 | 1.1422 | 5277 | 0.56654 | 6975 | 0.82029 | 20840 | 2.529 | 81932 | 1384 | 7 | 177.0317 | 80.8768 | 96.155 | 6.1571
5 | Kalchini | 6228 | 0.51936 | 20261 | 1.9009 | 10303 | 0.86525 | 36792 | 3.2855 | 101947.5 | 1941 | 51 | 229.9854 | 124.9542 | 105.0311 | 6.9291
6 | Kumargram | 9311 | 0.84696 | 8087 | 0.86006 | 4659 | 0.43972 | 22057 | 2.1467 | 49086.5 | 5007 | 52 | 150.2718 | 48.3377 | 101.9341 | 6.0044
7 | Madarihat-Birpara | 4182 | 0.71929 | 9663 | 1.9425 | 5787 | 0.96803 | 19632 | 3.6298 | 111949.6 | 566 | 83 | 254.0868 | 72.3662 | 181.7206 | 10.7601
8 | Mal | 6303 | 0.57295 | 7006 | 0.68241 | 7505 | 0.70455 | 20814 | 1.9599 | 45173 | 1591 | 45 | 137.1937 | 89.0503 | 48.1434 | 3.9788
9 | Matiali | 4436 | 0.4779 | 6056 | 0.69857 | 4944 | 0.52216 | 15436 | 1.6986 | 75354.5 | 1061 | 128 | 118.9038 | 43.5173 | 75.3864 | 8.3721
10 | Maynaguri | 25429 | 1.7106 | 741 | 0.07327 | 7670 | 0.59317 | 29084 | 2.377 | 53663 | 4120 | 493 | 166.3907 | 73.9524 | 92.4383 | 4.0494
11 | Nagrakata | 2465 | 0.34607 | 6203 | 0.83723 | 4173 | 0.4555 | 12841 | 1.6388 | 39688 | 461 | 0 | 114.716 | 39.1098 | 75.6062 | 7.5699
12 | Rajganj | 9361 | 1.0664 | 1666 | 0.35093 | 7426 | 0.64542 | 18453 | 2.0628 | 67563 | 3159 | 17 | 144.3932 | 99.6765 | 44.7167 | 5.0739
13 | Sadar | 24106 | 1.8069 | 2184 | 0.47456 | 8077 | 0.54027 | 34367 | 2.8217 | 68283 | 1619 | 187 | 197.5211 | 62.8171 | 134.704 | 5.1875
| Total | 147271.21 | 12.9153 | 89654.77 | 11.0655 | 96839.02 | 9.0218 | 329009 | 33.0026 | 943625.6518 | 29748.8497 | 2487.8221 | 2244.1757 |  | 1294.2792 | 6.0548
0
this column should be = to col. no. 4 of Part-I

## Part-III
National Rural Employment Gurantee Act (N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2007-08 Up to the Month of November' 07
Jalpaiguri District | [15 empty] | (Rs. in lakh)
Sl. No. | Name of the Block | No. of Household | Actual O.B. as on 01.04.07 | Released last year but received during the current year |  | Release During the Current Year by the Govt. to Z.P. |  | Release During the Current Year to P.S./ Line Deptt. |  | Misc. Receipt | Total Availability (4+5+6+7+8) | Cummulative Expenditure
|  |  |  | Central | State | Central | State | Central | State |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | On Contingency | Total (9+10+11+12)
| 1 |  | 2 | 3 | 4 | 5 | 6 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 2.488
1 | Alipurduar-I | 2912 | 37.2833 |  |  |  |  | 236.7038 |  | 0.56169 | 274.5488 | 160.1793 | 5.9159 | 28.8344 | 3.4864 | 198.416 | 0.714 | 159.4653 | 127.2321 | 71.1839
2 | Alipurduar-II | 4447 | 101.5512 | 6.8511 |  |  |  | 181.0128 |  | 0.12447 | 289.5397 | 113.2036 | 3.3345 | 81.1675 | 0.9106 | 198.6163 | 0.9044 | 112.2992 | 124.3249 | 74.2914
3 | Dhupguri | 2895 | 102.1284 |  |  |  |  | 341.9935 |  | 0.496 | 444.6179 | 342.4795 | 12.7295 | 134.232 | 2.9051 | 492.3461 | 0.21148 | 342.268 | 220.2133 | 272.1328
4 | Falakata | 4593 | 35.8404 | 5.0821 |  |  |  | 266.1774 | 2.1579 | 0.22028 | 309.4781 | 174.9899 | 5.4568 | 57.4467 | 0.91464 | 238.808 | 6.46 | 168.5299 | 164.2829 | 74.5251
5 | Kalchini | 2539 | 116.9174 |  |  |  |  | 310.2828 | 8.08 | 0.39742 | 435.6776 | 237.4125 | 15.6929 | 41.4394 | 5.5097 | 300.0545 | 2.1855 | 235.227 | 204.825 | 95.2296
6 | Kumargram | 3620 | 75.9799 | 35.766 |  |  |  | 173.7523 |  | 3.2255 | 229.4868 | 135.5042 | 8.9256 | 40.8816 | 7.6341 | 192.9455 | 7.4086 | 128.0956 | 107.5594 | 85.3861
7 | Madarihat-Birpara | 3872 | 75.5432 | 137.6192 | 0 |  |  | 160.2232 | 0 | 1.3203 | 374.7059 | 254.9782 | 8.9153 | 82.6931 | 7.4996 | 354.0862 | 0.10336 | 254.8748 | 207.3482 | 146.738
8 | Mal | 3006 | 143.3522 |  | 1.6356 |  |  |  | 116.6089 | 1.8969 | 263.4936 | 134.4603 | 5.6597 | 25.0333 | 1.7171 | 166.8703 | 11.2696 | 123.1907 | 134.5847 | 32.2856
9 | Matiali |  | 45.2166 |  |  |  |  | 153.0621 | 0 | 2.5839 | 200.8626 | 117.353 | 5.0307 | 56.7234 | 2.9682 | 182.0753 | 0 | 117.353 | 101.6925 | 80.3828
10 | Maynaguri |  | 147.4743 | 25.9972 |  |  |  | 328.5688 |  | 3.2297 | 420.4734 | 169.1836 | 7.1095 | 156.6067 | 4.1285 | 337.0282 | 0.0408 | 169.1428 | 188.1484 | 148.8798
11 | Nagrakata |  | 42.6977 | [5 empty] | 55.5142 | 1.0608 | 208.8783 | 119.8709 | 6.228 | 62.6827 | 3.8562 | 192.6378 | 3.4619 | 116.409 | 115.3297 | 77.3081
12 | Rajganj | 2781 | 145.519 | 7.2111 |  |  |  | 216.8471 |  | 1.1224 | 370.6996 | 149.8474 | 4.8611 | 56.6607 | 2.1855 | 213.5546 | 0.2516 | 149.5958 | 135.0134 | 78.5412
13 | Sadar | 3059 | 157.8944 |  |  |  |  | 283.4566 |  | 1.4252 | 442.7762 | 208.1458 | 14.3299 | 57.2055 | 1.4884 | 281.1696 | 0 | 208.1458 | 195.9161 | 85.2535
| Total | 33724 | 1227.3982 | 218.5267 | 1.6356 | 0 | 0 | 2652.0804 | 182.361 | 17.6646 | 4265.2386 | 2317.6081 | 104.1894 | 881.6069 | 45.204 | 3348.6084 | 33.0113
1 | Line Deptt. |  | 2: 0; 8: 0; 9: 29.684; 13: 29.684
2 | Zilla Parishad |  | 2: 389.6533; 8: 389.6533; 12: 27.8905; 13: 27.8905
| Total | 57194 | 389.6533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 389.6533 | 29.684 | 0 | 0 | 27.8905 | 57.5745
| G.T. |  | 1617.0515 | 218.5267 | 1.6356 | 0 | 0 | 2652.0804 | 182.361 | 17.6646 | 4654.892 | 2347.2921 | 104.1894 | 881.6069 | 73.0945 | 3406.1829
3174.74
924.1209

## Part-IV
National Rural Employment Gurantee Act (NREGA) | [19 empty] | National Rural Employment Gurantee Act (NREGA) | [17 empty] | National Rural Employment Gurantee Act (NREGA)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2007-08 Up to the Month of November' 07 | [19 empty] | Physical Performance Under NREGA During the year 2007-08 Up to the Month of November' 07 | [17 empty] | Physical Performance Under NREGA During the year 2007-08 Up to the Month of November' 07
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the Block | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec. |  | No. | Hec. |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  |  | No.
1 | Alipurduar-I | 16 | 9013.8 | 13.1706 | 1 | 6.3 | 0.1722 | 24 | 36.65 | 16.5124 | 179 | 136 | 40.53 | 0 | 0 | 0 | 2 | 100.5 | 1.6678 | 2 | 200 | 0.6855 | 2 | 0 | 0.38382 | 2 | 10588.6 | 1.8883 | 1 | 0.33 | 0.38722 | 10 | 10.92 | 10.5929 | 24 | 20.38 | 2.83 | 24 | 24.535 | 34.1719 | 5 | 2.8 | 2.68 | 45 | 39.3 | 53.1845 | 14 | 13.25 | 12.69 |  | 0 | 0 | 0 | 0 | 0 | 123 |  | 130.2062 | 228 | 0 | 62.4319 | 192.6381 | 186.8959 | -5.7422
2 | Alipurduar-II | 1 | 6885 | 2.0655 | 3 | 10585.0794 | 3.3343 | 17 | 16.1947 | 5.1823 | 22 | 21.6095 | 7.5633 | 3 | 2.5932 | 1.6078 | 4 | 3.411 | 2.2171 | 6 | 20.9361 | 5.9668 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3183.6364 | 1.0506 | 1 | 0.045333 | 0.01428 | 1 | 2.4468 | 0.78296 | 13 | 14.4699 | 31.5443 | 18 | 18.4855 | 40.5757 | 42 | 28.5953 | 51.4159 | 33 | 19.1345 | 48.9843 | 0 | 0 | 0 | 0 | 0 | 0 | 83 |  | 97.7969 | 82 |  | 104.5083 | 202.3052 | 198.6163 | -3.6889
3 | Dhupguri | 48 | 23364.3385 | 7.5934 | 7 | 9521.3231 | 3.0944 | 23 | 67844.2017 | 16.1469 | 22 | 29560.8824 | 7.0355 | 23 | 36.1048 | 22.3849 | 5 | 1.0081 | 0.62502 | 6 | 18.6848 | 5.0449 | 0 | 0 | 0 | 6 | 18663.0794 | 5.8789 | 4 | 12734.8889 | 4.0115 | 36 | 351.2849 | 112.4112 | 5 | 4.5013 | 1.4404 | 78 | 41.7203 | 95.1223 | 40 | 50.7957 | 115.8143 | 77 | 150.3173 | 72.1523 | 40 | 46.0516 | 22.1047 | 0 | 0 | 0 | 0 | 0 | 0 | 297 |  | 336.7348 | 123 |  | 154.1259 | 490.8607 | 492.3461 | 1.4854
4 | Falakata | 23 | 114351.4815 | 30.8749 | 7 | 22517.2222 | 6.0796 | 18 | 37.1867 | 9.2967 | 19 | 21.5832 | 5.3958 | 2 | 3.2883 | 2.0388 | 4 | 4.756 | 2.9487 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1161.75 | 0.37176 | 0 | 0 | 0 | 5 | 12.5519 | 3.8911 | 3 | 0.24068 | 0.07461 | 28 | 9.6345 | 21.6777 | 15 | 7.1651 | 16.1216 | 75 | 96.2 | 76.6409 | 80 | 81.6 | 62.5249 | 0 | 0 | 0 | 0 | 0 | 0 | 155 |  | 144.7918 | 128 |  | 93.1453 | 237.9371 | 238.808 | 0.87096
5 | Kalchini | 11 | 22061.11 | 9.3837 | 4 | 5115 | 1.9688 | 3 | 19.76 | 3.6292 | 0 | 0 | 0 | 5 | 6.675 | 4.5801 | 3 | 4.3 | 1.6587 | 3 | 2272 | 3.3414 | 0 | 0 | 0 | 2 | 2673 | 2.0355 | 0 | 0 | 0 | 2 | 10.2015 | 7.205 | 0 | 0 | 0 | 42 | 26.888 | 61.6064 | 29 | 8.467 | 19.7958 | 130 | 213.334 | 146.5233 | 32 | 25.08 | 18.2233 | 0 | 0 | 0 | 0 | 0 | 0 | 198 |  | 238.3046 | 68 |  | 41.6467 | 279.9512 | 311.8899 | 31.9387
6 | Kumargram | 8 | 21777 | 7.5325 | 8 | 11510 | 6.4215 | 32 | 23.66 | 16.1984 | 40 | 27.27 | 17.0708 | 9 | 311.36 | 6.6681 | 11 | 269.95 | 5.658 | 0 | 0 | 0 | 1 | 54 | 2.0174 | 4 | 1754.82 | 0.46804 | 4 | 3816 | 2.9354 | 11 | 2.648 | 5.5996 | 13 | 29.92 | 7.8173 | 20 | 168.601 | 13.7665 | 12 | 5.883 | 5.3612 | 75 | 65.883 | 58.8794 | 35 | 24.895 | 19.3883 | 0 | 0 | 0 | 0 | 0 | 0 | 159 |  | 109.1127 | 124 |  | 66.6698 | 175.7824 | 192.9455 | 17.1631
7 | Madarihat-Birpara | 15 | 27585.125 | 11.7585 | 8 | 22200 | 10.0033 | 15 | 45.3 | 8.2408 | 18 | 61.5 | 7.9802 | 6 | 11.9 | 8.312 | 2 | 0.7 | 0.5719 | 17 | 60 | 11.1662 | 5 | 12.5 | 7.145 | 3 | 28326 | 10.3287 | 3 | 500 | 0 | 17 | 71 | 27.1836 | 4 | 1.3 | 1.5708 | 74 | 49.3 | 108.0276 | 37 | 5.65 | 19.1952 | 103 | 138.11 | 110.0548 | 50 | 6.9 | 10.0744 | 0 | 0 | 0 | 0 | 0 | 0 | 250 |  | 295.0722 | 127 |  | 56.5408 | 351.613 | 354.0862 | 2.4732
8 | Mal | 3 | 11080 | 3.0565 | 6 | 7216 | 2.1408 | 24 | 21.34 | 5.9009 | 53 | 50.65 | 19.1461 | 34 | 48.21 | 27.36 | 3 | 6 | 3.87 | 5 | 6.5 | 6.9307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6.5 | 2.8914 | 0 | 0 | 0 | 13 | 6.8 | 15.9256 | 15 | 13.79 | 28.8224 | 36 | 38.685 | 28.5056 | 12 | 14.16 | 13.8228 | 0 | 0 | 0 | 0 | 0 | 0 | 118 |  | 90.5707 | 89 |  | 67.8021 | 158.3728 | 153.7092 | -4.6636
9 | Matiali | 0 | 0 | 0 | 2 | 4036 | 1.6351 | 1 | 15 | 4.1312 | 3 | 37.82 | 11.2662 | 55 | 57.76 | 46.2385 | 19 | 110.05 | 22.1796 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 22952.4286 | 8.0334 | 2 | 10426.7714 | 3.6494 | 3 | 5.88 | 3.4248 | 0 | 0 | 0 | 15 | 16.21 | 18.5519 | 13 | 15.8 | 27.0434 | 19 | 14.05 | 16.0264 | 19 | 12.2 | 16.8641 | 0 | 0 | 0 | 0 | 0 | 0 | 94 |  | 96.4061 | 58 |  | 82.6378 | 179.0439 | 182.0753 | 3.0314
10 | Maynaguri | 0 | 0 | 0 | 2 | 8529 | 4.3532 | 22 | 9.1 | 4.5259 | 153 | 88 | 73.0276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3802 | 0.88097 | 1 | 1.5 | 0.1656 | 3 | 5 | 0.7499 | 11 | 12.84 | 12.4056 | 6 | 7.5 | 4.2017 | 89 | 118.45 | 108.7665 | 72 | 94.17 | 124.9626 | 0 | 0 | 0 |  | 0 | 0 | 123 |  | 125.8636 | 238 |  | 208.176 | 334.0396 | 337.0282 | 2.9887
11 | Nagrakata | 1 | 1069 | 0.77588 | 0 | 0 | 0 | 7 | 57.175 | 10.921 | 1 | 187.5 | 3.2894 | 77 | 114.5 | 61.6468 | 2 | 0.5 | 0.59933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 4.673 | 29.3948 | 10 | 0.45 | 8.6922 | 66 | 108.5 | 76.9467 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 171 |  | 179.6851 | 13 |  | 12.5809 | 192.266 | 192.6378 | 0.37176
12 | Rajganj | 4 | 11341.8 | 3.7975 | 2 | 1887.14 | 0.574 | 5 | 4.5 | 0.51714 | 83 | 326.48 | 54.5177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 9.6416 | 0 | 0 | 0 | 9 | 5.542 | 5.082 | 3 | 2.8 | 3.0495 | 7 | 23 | 21.9466 | 0 | 0 | 0 | 72 | 103.439 | 79.4442 | 34 | 519.9 | 32.7989 | 0 | 0 | 0 | 0 | 0 | 0 | 98 |  | 120.4291 | 122 |  | 90.94 | 211.3691 | 191.0397 | -20.3294
13 | Sadar | 6 | 7261.9 | 4.3321 | 12 | 14732.764 | 6.4199 | 34 | 31.6 | 18.5644 | 41 | 60.39 | 20.4763 | 1 | 0.75 | 0.40758 | 2 | 1.3 | 8.4937 | 12 | 10.03 | 5.6955 | 5 | 3.5 | 2.2056 | 7 | 29161 | 7.497 | 1 | 575 | 1.2232 | 17 | 23.154 | 16.2093 | 18 | 72.73 | 53.9729 | 14 | 22.142 | 16.6613 | 7 | 5.28 | 9.7775 | 62 | 82.6 | 72.7186 | 29 | 47.73 | 35.5414 | 0 | 0 | 0 | 0 | 0 | 0 | 153 |  | 142.0857 | 115 |  | 138.1105 | 280.1963 | 281.1696 | 0.97335
| Total | 136 | 255790.5549 | 94.3411 | 62 | 117855.8287 | 46.1971 | 225 | 68161.6681 | 119.7673 | 634 | 30579.685 | 267.2989 | 215 | 593.1413 | 181.2446 | 57 | 502.4751 | 50.4899 | 51 | 2588.1509 | 38.8309 | 13 | 70 | 11.7518 | 30 | 115283.6779 | 46.1431 | 18 | 35038.6267 | 14.1382 | 115 | 501.2276 | 194.6708 | 74 | 139.3187 | 72.2883 | 359 | 420.8137 | 480.8024 | 207 | 142.0664 | 298.0809 | 891 | 1197.4637 | 951.2592 | 450 | 905.0711 | 417.9798 | 0 | 0 | 0 | 0 | 0 | 0 | 2022 | 0 | 2107.0595 | 1515 | 0 | 1179.3159
[56 empty] | 1584 |  |  | 1224
[56 empty] | -438 |  |  | -291