## Part-I
National Rural Employment Gurantee Act (N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of November' 2008
MPR- Part-I
1 | 2 |  | 3 | [5 empty] | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  |  | 10 | 11 | 12
|  |  | a | b | c | d |  |  |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Register | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Job Card as on 15-06-08 | Difference | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) |  |  |  |  | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals
|  |  | SC | ST | Others | Total | [8 empty] | ST | Others | Total | Women | bar: 9
1 | Alipurduar-I | 35012 | 19501 | 7800 | 7711 | 35012 | 33502 | 1510 | 10056 | 2994662 | 10056 | 1063 | 204624 | 0.99087 | 0.41043 | 0.35693 | 1.7582 | 1.1515 | 0 | 1106 | 17
2 | Alipurduar-II | 40735 | 19440 | 9452 | 11843 | 40735 | 40465 | 270 | 16323 | 243770 | 16298 | 3639 | 130613 | 0.39184 | 0.58776 | 0.32653 | 1.3061 | 0.41796 | 2 | 1952 | 299
3 | Dhupguri | 75331 | 39789 | 16324 | 19150 | 75263 | 75263 | 0 | 30179 | 89002 | 30179 | 6931 | 1304431 | 1.5918 | 0.93626 | 0.96483 | 3.4929 | 1.0395 | 0 | 669 | 35
4 | Falakata | 43018 | 20476 | 8537 | 13933 | 42946 | 42195 | 751 | 13173 | 28614 | 13164 | 324 | 170718 | 0.50362 | 0.23654 | 0.34398 | 1.0841 | 0.33529 | 1 | 820 | 7
5 | Kalchini | 49815 | 6914 | 28697 | 14123 | 49734 | 48777 | 957 | 19921 | 66304.06 | 23051 | 3649 | 928256.84 | 0.6887 | 1.988 | 0.91152 | 3.5882 | 1.0752 | 0 | 3763 | 493
6 | Kumargram | 37583 | 14801 | 14072 | 8710 | 37583 | 14072 | 8710 | 27219 | 138753 | 26848 | 9585 | 1155373 | 2.1004 | 0.98578 | 0.87477 | 3.961 | 1.1474 | 0 | 9083 | 1451
7 | Madarihat-Birpara | 34386 | 6958 | 14536 | 12892 | 34382 | 34186 | 196 | 15171 | 62118 | 14464 | 3756 | 662229 | 0.63537 | 1.308 | 0.97838 | 2.9217 | 1.1266 | 6 | 328 | 70
8 | Mal | 52804 | 16896 | 18419 | 17489 | 52804 | 51300 | 1504 | 23426 | 42500 | 23132 | 3908 | 177210 | 0.89652 | 1.2259 | 1.0619 | 3.1843 | 1.0448 | 0 | 981 | 79
9 | Matiali | 21803 | 5348 | 10745 | 5685 | 21778 | 21292 | 486 | 11507 | 9826 | 10588 | 1564 | 203444 | 0.37516 | 0.68401 | 0.58697 | 1.6461 | 0.77453 | 0 | 432 | 68
10 | Maynaguri | 61026 | 46051 | 998 | 13912 | 60961 | 60376 | 585 | 25013 | 42415 | 25013 | 5473 | 7.1624 | 1.5143 | 0.04772 | 0.41326 | 1.9753 | 0.49199 | 0 | 2613 | 85
11 | Nagrakata | 23217 | 3652 | 13561 | 6004 | 23217 | 22683 | 534 | 16504 | 0 | 16504 | 2305 | 0 | 0.38514 | 1.3704 | 0.67474 | 2.4303 | 0.74134 | 0 | 843 | 136
12 | Rajganj | 44771 | 26793 | 2387 | 15591 | 44771 | 40114 | 4657 | 9092 | 20309 | 8812 | 2131 | 304743 | 0.40195 | 0.05993 | 0.1252 | 0.58708 | 0.23569 | 0 | 504 | 2
13 | Sadar | 55326 | 37705 | 4105 | 13516 | 55326 | 54816 | 510 | 13774 | 0 | 13767 | 4012 | 0 | 0.79583 | 0.14463 | 0.18831 | 1.1288 | 0.30467 | 0 | 782 | 40
| Total: | 574827 | 264324 | 149633 | 160559 | 574512 | 539041 | 20670 | 231358 | 3738273.06 | 231876 | 48340 | 5241649.0024 | 11.2716 | 9.9853 | 7.8073 | 29.0642 | 9.8865 | 9 | 23876 | 2782

## Part-II
Part-II
National Rural Employment Gurantee Act (N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2008-09 Up to the Month of November' 08
Jalpaiguri District | [15 empty] | (Rs. in lakh)
Sl. No. | Name of the Block | No. of Household | Actual O.B. as on 01.04.08 | Released last year but received during the current year |  | Release During the Current Year by the Govt. to Z.P. |  | Misc. Receipt | Total Availability (4+5+6+7+8) | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure
|  |  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (9+10+11+12)
[14 empty] | Recurring | Non-Recurring
| 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Alipurduar-I | 2912 | 100.2988 | [5 empty] | 304.8279 | 149.0976 | 131.4587 | 5.6729 | 69.6007 | 1.0411 | 2.5835 | 210.3569 |  | 62.49%
2 | Alipurduar-II | 4447 | 96.0436 | [5 empty] | 269.5707 | 284.9992 | 107.5418 | 6.8559 | 77.2459 | 7.4812 | 2.8101 | 201.9349 |  | 53.26%
3 | Dhupguri | 2895 | 98.1287 | [5 empty] | 684.8231 | 1239.2098 | 278.3974 | 10.5319 | 278.5144 | 0.65967 | 9.4386 | 577.5419 |  | 48.2%
4 | Falakata | 4593 | 58.3644 | [5 empty] | 235.0462 | 230.4693 | 80.7477 | 3.5534 | 54.7178 | 2.9287 | 0.67078 | 142.6183 |  | 56.62%
5 | Kalchini | 2539 | 129.3238 | [5 empty] | 533.3365 | 881.844 | 286.8137 | 20.21 | 108.639 | 3.6452 | 2.948 | 422.256 |  | 67.92%
6 | Kumargram | 3620 | 77.2946 | [5 empty] | 587.8694 | 414.1122 | 321.6077 | 17.3769 | 202.4061 | 2.2974 | 13.2975 | 556.9856 |  | 57.74%
7 | Madarihat-Birpara | 3872 | 42.5347 | [5 empty] | 577.4136 | 630.7032 | 229.2371 | 17.8542 | 249.5561 | 2.5718 | 10.105 | 509.3242 |  | 45.01%
8 | Mal | 3006 | 124.7644 | [5 empty] | 423.7705 | 299 | 254.4199 | 10.1807 | 94.9615 | 3.2756 | 6.6385 | 369.4762 |  | 68.86%
9 | Matiali |  | 70.1932 | [5 empty] | 266.9534 | 315.281 | 140.2276 | 7.2927 | 77.2632 | 3.2405 | 3.8847 | 231.9088 |  | 60.47%
10 | Maynaguri |  | 99.5516 | [5 empty] | 390.5728 | 649.0922 | 148.1482 | 4.0905 | 82.9217 | 4.9573 | 3.6119 | 243.7297 |  | 60.78%
11 | Nagrakata |  | 31.5438 | [5 empty] | 332.4392 | 0 | 182.3092 | 10.5687 | 97.9026 | 2.6335 | 6.9757 | 300.3897 |  | 60.69%
12 | Rajganj | 2781 | 37.5782 | [5 empty] | 161.8304 | 351.3882 | 46.4759 | 1.4804 | 30.7372 | 24.4384 | 0.17502 | 103.307 |  | 44.99%
13 | Sadar | 3059 | 118.9983 | [5 empty] | 243.9569 | 0 | 86.1516 | 4.1023 | 41.0888 | 0.98102 | 1.971 | 134.2947 |  | 64.15%
| Total | 33724 | 1084.6182 | 0 | 0 | 0 | 0 | 0 | 5012.4105 |  | 2293.5367 | 119.7704 | 1465.555 | 60.1514 | 65.1104 | 4004.1239 | 0
1 | Line Deptt. |  | 2: 68.313; 8: 68.313; 10: 74.99; Non-Recurring 15: 74.99
2 | District Cell |  | 2: 319.8484; 8: 319.8484; Recurring 13: 7.7109; Non-Recurring 14: 17.6737; Non-Recurring 15: 25.3846 |  | 25.3846
| Total | 57194 | 388.1614 | 0 | 0 | 0 | 0 | 0 | 388.1614 |  | 74.99 | 0 | 0 | 7.7109 | 17.6737 | 100.3746
| G.T. |  | 1472.7796 | 0 | 0 | 0 | 0 | 0 | 5400.5719 |  | 2368.5267 | 119.7704 | 1465.555 | 67.8623 | 82.784 | 4104.4985 |  |  | 4104.4985
Note on O28: N.R.E.G.S.4: For the month of Nov, 08
Note on P28: N.R.E.G.S.4: For the month of Nov, 08
Note on L27: N.R.E.G.S.4: Nov' 08

## Part-III
National Rural Employment Gurantee Act (NREGA) | [19 empty] | National Rural Employment Gurantee Act (NREGA) | [17 empty] | National Rural Employment Gurantee Act (NREGA)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2008-09 Up to the Month of November' 08 | [19 empty] | Physical Performance Under NREGA During the year 2008-09 Up to the Month of November' 08 | [17 empty] | Physical Performance Under NREGA During the year 2008-09 Up to the Month of November' 08
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the Block | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec. |  | No. | Hec. |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  |  | No.
1 | Alipurduar-I | 48 | 51382.49 | 24.7613 | 9 | 16663.4 | 4.4141 | 20 | 14.04 | 2.4941 | 29 | 23.32 | 2.4373 | 1 | 0.55 | 0.25625 | 0 | 0 | 0 | 6 | 3.25 | 4.7484 | 2 | 1.5 | 0.4 | 18 | 8100 | 8.4962 | 1 | 150 | 0.38466 | 5 | 5.05 | 3.2184 | 1 | 0 | 0.93825 | 16 | 10.419 | 22.2987 | 9 | 6.493 | 43.0831 | 60 | 64.285 | 73.0278 | 22 | 20.115 | 21.7558 | 0 | 0 | 0 | 0 | 0 | 0 | 174 |  | 139.3012 | 73 | 0 | 62.4319 | 201.733
2 | Alipurduar-II | 8 | 22094 | 7.8641 | 12 | 11490 | 361930 | 4 | 9.53 | 3.0505 | 37 | 32 | 12.3341 | 4 | 1.2712 | 0.78817 | 5 | 10.8726 | 7.0672 | 1 | 3.296 | 0.93938 | 0 | 0 | 0 | 3 | 2858.697 | 0.94337 | 3 | 2859 | 1.8073 | 0 | 0 | 0 | 2 | 1.2 | 0.36875 | 9 | 2.5 | 5.4547 | 33 | 24.1 | 51.9357 | 42 | 13 | 34.6356 | 51 | 34 | 59.4942 | 0 | 0 | 0 | 0 | 0 | 0 | 71 |  | 53.6758 | 143 |  | 362063.0073 | 362116.683
3 | Dhupguri | 42 | 107765.7231 | 35.0239 | 4 | 10078.0615 | 3.2754 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 22.891 | 14.1924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 35.2405 | 11.277 | 1 | 0 | 0 | 14 | 22.1936 | 50.6015 | 0 | 0 | 0 | 240 | 838.46 | 402.4608 | 73 | 123.9821 | 59.5114 | 0 | 0 | 0 | 0 | 0 | 0 | 316 |  | 513.5556 | 78 |  | 62.7868 | 576.3424
4 | Falakata | 18 | 31816.5185 | 8.5905 | 9 | 18706.7778 | 5.0508 | 3 | 5.9251 | 1.4813 | 2 | 0.555 | 0.13875 | 8 | 3.9925 | 2.4754 | 4 | 0.25766 | 1.062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3378.5 | 1.0811 | 6 | 16.4573 | 5.1018 | 3 | 4.9875 | 1.5461 | 8 | 3.6539 | 8.2214 | 4 | 3.9183 | 8.8162 | 63 | 53.67 | 42.6568 | 67 | 73.21 | 52.7571 | 0 | 0 | 0 | 0 | 0 | 0 | 106 |  | 68.527 | 91 |  | 70.4522 | 138.9792
5 | Kalchini | 14 | 26472.12 | 10.0902 | 7 | 2765.81 | 1.3319 | 0 | 0 | 0 | 9 | 5.1 | 1.29 | 52 | 133.57 | 63.4993 | 4 | 3.5 | 2.7667 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 7.61 | 0 | 0 | 0 | 14 | 74.18 | 40.7418 | 1 | 0 | 0.002 | 84 | 44.423 | 192.9279 | 30 | 14.3 | 21.8685 | 109 | 129.3 | 140.5668 | 25 | 15.285 | 11.4936 | 0 | 0 | 0 | 0 | 0 | 0 | 274 |  | 455.436 | 76 |  | 38.7528 | 494.1888
6 | Kumargram | 29 | 67351.5 | 24.2044 | 28 | 33344.05 | 26.0769 | 16 | 6.706 | 5.9345 | 25 | 13.051 | 18.6017 | 11 | 10.89 | 12.9471 | 15 | 8.004 | 19.1542 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 95 | 0.98512 | 2 | 0 | 0.75613 | 44 | 80.731 | 41.2312 | 12 | 9.015 | 12.6525 | 10 | 13.9 | 34.3783 | 16 | 6 | 95.9752 | 77 | 11452.955 | 76.6353 | 100 | 82.375 | 132.2321 | 0 | 0 | 0 | 0 | 0 | 0 | 188 |  | 196.3159 | 198 |  | 305.4487 | 501.7645
7 | Madarihat-Birpara | 7 | 9855.13 | 5.0789 | 6 | 27251 | 10.7827 | 4 | 2 | 5.9813 | 27 | 1.9 | 4.4254 | 3 | 2.8 | 3.5379 | 1 | 0 | 0 | 2 | 8 | 1.9305 | 2 | 0 | 0.37305 | 7 | 16951 | 10.5649 | 12 | 54598 | 10.7789 | 5 | 14.94 | 4.8412 | 4 | 2.5 | 1.2075 | 57 | 65.07 | 136.045 | 38 | 20.18 | 74.4893 | 88 | 124.2 | 98.8734 | 82 | 63.1 | 99.8556 | 0 | 0 | 0 | 0 | 0 | 0 | 173 |  | 266.8532 | 172 |  | 201.9124 | 468.7656
8 | Mal | 19 | 10249.916 | 13.0652 | 40 | 55517.393 | 34.9008 | 8 | 7.59 | 2.0842 | 34 | 28.33 | 10.2662 | 160 | 102.193 | 69.3115 | 50 | 63.16 | 22.5928 | 1 | 160 | 5.0713 | 0 | 0 | 0 | 8 | 4625 | 3.7679 | 8 | 2300 | 8.5122 | 4 | 3.9 | 1.7181 | 7 | 2.795 | 2.7804 | 9 | 9.275 | 17.1322 | 33 | 1044.4 | 25.0003 | 68 | 82.048 | 73.3824 | 44 | 44.939 | 52.0851 | 0 | 0 | 0 | 0 | 0 | 0 | 277 |  | 185.5328 | 216 |  | 156.1378 | 341.6706
9 | Matiali | 23 | 25064.5556 | 11.279 | 6 | 7578.1111 | 3.4101 | 1 | 2.6592 | 0.64485 | 7 | 41.1198 | 9.7012 | 51 | 76.2268 | 49.2044 | 23 | 23.7614 | 14.0664 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2967.3143 | 1.0386 | 16 | 16172.6857 | 5.6604 | 13 | 33.0704 | 8.0305 | 6 | 18.5074 | 4.5019 | 10 | 14.2734 | 8.6252 | 18 | 69.6697 | 66.7193 | 27 | 28.5936 | 17.8375 | 39 | 32.8782 | 24.0151 | 0 | 0 | 0 | 0 | 0 | 0 | 127 |  | 96.6601 | 115 |  | 128.0745 | 224.7346
10 | Maynaguri | 8 | 2541 | 4.1231 | 42 | 62777.5 | 16.7706 | 40 | 5.8 | 9.2863 | 142 | 119.675 | 59.9134 | 1 | 0.2 | 0 | 1 | 0.6 | 0.43687 | 1 | 0 | 0.70226 | 9 | 14 | 4.6516 | 4 | 15000 | 0.58311 | 5 | 5630 | 1.7682 | 0 | 0 | 0 | 8 | 3.675 | 2.0474 | 7 | 5 | 4.6943 | 12 | 16.8 | 4.4131 | 57 | 48.58 | 35.8539 | 96 | 105.075 | 69.2881 | 0 | 0 | 0 | 0 | 0 | 0 | 118 |  | 55.243 | 315 |  | 159.2894 | 214.5324
11 | Nagrakata | 11 | 33446.24 | 12.9071 | 1 | 0 | 0 | 45 | 202.17 | 40.6567 | 1 | 1.7 | 0.23475 | 60 | 140.24 | 65.7373 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 221.16 | 7.7032 | 0 | 0 | 0 | 6 | 13500 | 6.2472 | 1 | 0 | 0 | 23 | 20.425 | 48.734 | 11 | 1.25 | 12.1985 | 67 | 74.2 | 104.4203 | 10 | 1 | 1.5507 | 0 | 0 | 0 | 0 | 0 | 0 | 226 |  | 286.4059 | 40 |  | 13.9839 | 300.3897
12 | Rajganj | 1 | 1133.41 | 0.39175 | 2 | 2297 | 0.07412 | 11 | 52.42 | 2.1778 | 46 | 106.535 | 20.6749 | 0 | 0 | 0 | 7 | 16 | 3.4211 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6.25 | 7.7544 | 0 | 0 | 0 | 2 | 1.8 | 2.8865 | 2 | 1.084 | 0.66988 | 0 | 0 | 0 | 4 | 1.4 | 0.54297 | 35 | 38.35 | 32.5692 | 23 | 21.45 | 12.1079 | 0 | 0 | 0 | 0 | 0 | 0 | 59 |  | 45.7797 | 84 |  | 37.4909 | 83.2706
13 | Sadar | 24 | 16353 | 9.5577 | 6 | 5046 | 2.1772 | 16 | 1591.32 | 5.8336 | 36 | 45.39 | 18.4993 | 1 | 1 | 0.189 | 1 | 2 | 0.394 | 2 | 6.82 | 0.6345 | 0 | 0 | 0 | 3 | 9 | 1.224 | 15 | 1152 | 8.8999 | 5 | 8.63 | 6.994 | 17 | 39.29 | 37.8779 | 5 | 4.75 | 3.8845 | 6 | 10 | 2.8608 | 31 | 1921.69 | 27.0005 | 20 | 11.397 | 15.649 | 0 | 0 | 0 | 0 | 0 | 0 | 87 |  | 55.3178 | 101 |  | 86.358 | 141.6759
| Total | 252 | 405525.6032 | 166.9372 | 172 | 253515.1034 | 362038.2646 | 168 | 1900.1603 | 79.6252 | 395 | 418.6758 | 158.5171 | 369 | 495.8246 | 282.1387 | 127 | 128.1556 | 70.9613 | 13 | 181.366 | 14.0263 | 13 | 15.5 | 5.4246 | 71 | 52921.4213 | 50.6708 | 64 | 86240.1857 | 39.649 | 107 | 13773.9993 | 132.2877 | 65 | 83.0539 | 64.5927 | 252 | 215.883 | 532.9977 | 214 | 1218.511 | 407.9028 | 964 | 14869.3316 | 1159.9203 | 652 | 628.8063 | 611.7958 | 0 | 0 | 0 | 0 | 0 | 0 | 2196 | 0 | 2418.6038 | 1702 | 0 | 363386.1265 | 365804.7303
[56 empty] | 1584 |  |  | 1224
[56 empty] | -612 |  |  | -478

## Part-IV
Part-IV
National Rural Employment Gurantee Act (N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2008-09 Up to the Month of November' 08
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 458 | 105 | 0 | 40 | 0 | 60 | 0 | 11 | 3 | 5
2 | Alipurduar-II | 213 | 5 | 210 | 8 | 218 | 0 | 1 | 4 | 0 | 0
3 | Dhupguri | 152 | 10 | 41 | 0 | 41 | 0 | 32 | 0 | 0 | 0
4 | Falakata | 147 | 6349 | 41 | 0 | 41 | 4 | 0 | 12 | 0 | 0
5 | Kalchini | 14262 | 225 | 0 | 11 | 0 | 147 | 4 | 18 | 0 | 5
6 | Kumargram | 1562 | 1236 | 867 | 27 | 23 | 0.82 | 35 | 3 | 0 | 0
7 | Madarihat-Birpara | 484 | 3 | 365 | 30 | 391 | 4 | 3 | 93 | 0 | 0
8 | Mal | 2289 | 79 | 488 | 5 | 485 | 8 | 0 | 0 | 0 | 0
9 | Matiali | 14 | 101 | 2 | 3 | 0 | 0 | 61 | 59 | 0 | 0
10 | Maynaguri | 35 | 15 | 0 | 0 | 35 | 15 | 165 | 0 | 0 | 0
11 | Nagrakata | 48 | 17 | 7 | 7 |  |  | 5 | 5 | 0 | 0
12 | Rajganj | 820 | 58 | 50 | 0 | 50 | 0 | 68 | 85 | 0 | 0
13 | Sadar | 146 | 18 | 46 | 4 | 24 | 0 | 2 | 1 | 0 | 0
| Total | 20630 | 8221 | 2117 | 135 | 1308 | 238.82 | 376 | 291 | 3 | 10

## Part-V-A
MPR Part - V-A
National Rural Employment Guarantee Act (NREGA)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the month of November' 2008)
Jalpaiguri District
Sl. No | Name of the BLOCK / GP | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | Alipurduar-I | 11 | 8 | 1 | 1 | 7 | 7 | 1 | 1 | 1 | 1
2 | Alipurduar-II | 11 | 9 | 1 | 1 | 5 | 5 | 1 | 1 | 1 | 1
3 | Dhupguri | 16 | 14 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1
4 | Falakata | 12 | 9 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
5 | Kalchini | 11 | 9 | 1 | 1 | 6 | 5 | 1 | 1 | 1 | 1
6 | Kumargram | 11 | 9 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
7 | Madarihat-Birpara | 10 | 6 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1
8 | Mal | 12 | 6 | 2 | 2 | 7 | 7 | 3 | 3 | 1 | 1
9 | Matiali | 5 | 5 | 1 | 1 | 5 | 5 | 1 | 1 | 1 | 1
10 | Maynaguri | 16 | 15 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
11 | Nagrakata | 5 | 3 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1
12 | Rajganj | 12 | 6 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
13 | Sadar | 14 | 11 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1
| Total: | 146 | 110 | 11 | 11 | 44 | 42 | 15 | 15 | 13 | 13 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1

## Part-V-B
MPR Part - V-B
National Rural Employment Guarantee Act (NREGA)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the month of November' 2008)
Jalpaiguri District
Sl. No | Name of the BLOCK / GP | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1 | Alipurduar-I | 8 | 8 | 1 | 0 | 7 | 0 | 1 | 0 | 1 | 0 | [10 empty] | 0 | 0 | 0 | 0
2 | Alipurduar-II | 9 | 0 | 1 | 1 | 5 | 5 | 0 | 1 | 0 | 1 | [10 empty] | 55 | 33 | 0 | 0
3 | Dhupguri | 14 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 291 | 291 | 17 | 17
4 | Falakata | 9 | 0 | 1 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | [10 empty] | 213 | 204 | 0 | 0
5 | Kalchini | 9 | 0 | 1 | 0 | 5 | 2 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0
6 | Kumargram | 9 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 0 | [10 empty] | 0 | 0 | 0 | 0
7 | Madarihat-Birpara | 6 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
8 | Mal | 6 | 0 | 2 | 2 | 7 | 7 | 3 | 3 | 1 | 1 | [10 empty] | 202 | 202 | 573 | 0
9 | Matiali | 5 | 0 | 1 | 1 | 5 | 5 | 1 | 1 | 1 | 1 | [10 empty] | 85 | 85 | 0 | 0
10 | Maynaguri | 15 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 4
11 | Nagrakata | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 1 | 1 | [10 empty] | 89 | 0 | 512 | 0
12 | Rajganj | 6 | 0 | 1 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | [10 empty] | 222 | 222 | 3460 | 36160
13 | Sadar | 11 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Total: | 110 | 8 | 13 | 10 | 41 | 28 | 12 | 13 | 10 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157 | 1037 | 4562 | 36177 | 0