## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of February' 2011
MPR- Part-I
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Register | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals | Avg. No. of Employment Provided per Household | % Women
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C | [25 empty] | Minority |  | Women | bar: 9
1 | 2 |  | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12 | [16 empty] | SC | ST | Others | Total
1 | Alipurduar-I | 39654 | 20965 | 8631 | 10108 | 39704 | 21154 |  | 21131 | 3093 |  | 2.7739 | 1.0303 | 0.89456 | 4.6988 | 2.0639 | 0.18655 | 58 | 1494 | 26 | 22.2363 | 43.92% | 43.92% | 20.85% | 0.29545 | 0.02985 | 103.3158 | 100.5629 | 4.0338 | 4.0338 | 0 | 120.3461 | 3.2671 | 0.59036 | 0.21926 | 0.19038 | 2.3814 | 0.88446 | 0.89456 | 4.1604 | 0.98478 | 0.20853 | 0.18655 | 0.38156 | 1.5875 | -0.47647 | 0.22898 | 0.20483 | 0.018289 | 7 | 1269 | 26 | -51 | -225 | 0
2 | Alipurduar-II | 44575 | 19699 | 9478 | 12205 | 41382 | 21470 |  | 21110 | 1010 |  | 1.6122 | 0.55696 | 2.1989 | 4.3681 | 1.3343 | 0.45854 | 41 | 236 | 29 | 20.6919 | 30.55% | 30.55% | 20.85% | 0.36152 | 0.07645 | 101.0262 | 101.5899 | 2.9528 | 4.3438 | 1.3911 | 101.5899 | 4.3438 | 0.3691 | 0.12751 | 0.5034 | 1.6033 | 0.55387 | 2.1989 | 4.356 | 0.87223 | 0.20853 | 0.45854 | 0.31109 | 1.3551 | 0.020849 | 0.089865 | 0.1976 | -0.26094 | 16 | 256 | 29 | -25 | 20 | 0
3 | Dhupguri | 80508 | 39105 | 16764 | 21163 | 77032 | 49196 |  | 48946 | 4749 |  | 7.0837 | 2.4011 | 3.4166 | 12.9015 | 5.541 | 0.71248 | 66 | 602 | 41 | 26.3585 | 42.95% | 42.95% | 20.85% | 1.3346 | 0.18348 | 100.6957 | 100.0593 | 11.595 | 12.9835 | 1.3885 | 100.0593 | 12.9835 | 0.54906 | 0.18611 | 0.26483 | 7.1287 | 2.4164 | 3.4166 | 12.9618 | 2.9887 | 0.20853 | 0.71248 | 0.45 | 5.8328 | 0.29183 | 0.21327 | 0.72867 | 0.016193 | 0 | 912 | 41 | -66 | 310 | 0
4 | Falakata | 49083 | 22167 | 9586 | 16396 | 48149 | 21979 |  | 21368 | 2247 |  | 2.09 | 0.84256 | 1.38 | 4.3125 | 1.8629 | 0.28777 | 228 | 1746 | 41 | 20.1821 | 43.2% | 43.2% | 20.85% | 0.65516 | 0.08436 | 106.2884 | 102.3292 | 3.8486 | 4.4794 | 0.63079 | 102.3292 | 4.4794 | 0.48463 | 0.19538 | 0.31999 | 2.1708 | 0.87516 | 1.38 | 4.426 | 1.2246 | 0.20853 | 0.28777 | 0.43691 | 1.9338 | 0.070854 | 0.12111 | 0.16713 | -0.12064 | 8 | 1500 | 41 | -220 | -246 | 0
5 | Kalchini | 56348 | 8355 | 31072 | 15593 | 55020 | 26405 |  | 26244 | 1430 |  | 0.91224 | 2.39 | 1.9847 | 5.2869 | 2.1826 | 0.41387 | 13 | 2457 | 17 | 20.1451 | 41.28% | 41.28% | 20.85% | 0.25415 | 0.04575 | 120.1509 | 100.7899 | 4.3531 | 6.3025 | 1.9493 | 100.7899 | 6.3025 | 0.17255 | 0.45206 | 0.3754 | 1.0875 | 2.8491 | 1.9847 | 5.9212 | 1.4922 | 0.20853 | 0.41387 | 0.4192 | 2.4822 | 0.29955 | 0.044626 | 0.088569 | -0.3253 | 0 | 2157 | 17 | -13 | -300 | 0
6 | Kumargram | 39869 | 15435 | 13492 | 9346 | 38273 | 29606 |  | 29601 | 917 |  | 2 | 0.92763 | 3.5293 | 6.4569 | 3.5338 | 0.73598 | 33 | 5126 | 278 | 21.8133 | 54.73% | 54.73% | 20.85% | 1.3127 | 0.12505 | 107.4324 | 99.252 | 7.8529 | 7.8529 | 0 | 88.3353 | 6.626 | 0.30974 | 0.14366 | 0.54659 | 2.4324 | 1.1282 | 3.5293 | 7.0899 | 2.4868 | 0.20853 | 0.73598 | 0.45 | 3.1904 | -0.34335 | 0.26335 | 0.92945 | 0.19347 | 0 | 5126 | 278 | -33 | 0 | 0
7 | Madarihat-Birpara | 38645 | 7774 | 16308 | 14225 | 38307 | 25842 |  | 24754 | 694 |  | 1.6814 | 2.6563 | 2.469 | 6.8067 | 3.2499 | 0.51487 | 64 | 74 | 127 | 27.4973 | 47.75% | 47.75% | 20.85% | 0.33008 | 0.04223 | 100.683 | 100.4944 | 6.0812 | 6.0812 | 0 | 112.694 | 4.8802 | 0.24702 | 0.39025 | 0.36273 | 1.5022 | 2.3732 | 2.469 | 6.3444 | 1.9789 | 0.20853 | 0.51487 | 0.53442 | 3.3905 | 0.14063 | 0.19583 | 0.4835 | -0.031368 | 22 | 201 | 127 | -42 | 127 | 0
8 | Mal | 57213 | 18393 | 20598 | 18221 | 57212 | 24004 |  | 23991 | 1339 |  | 0.81535 | 1.8666 | 2.3211 | 5.0031 | 2.566 | 0.48403 | 38 | 527 | 71 | 20.8541 | 51.29% | 51.29% | 20.85% | 0.38885 | 0.04705 | 105.8912 | 98.1499 | 4.0657 | 5.3977 | 1.332 | 98.1499 | 5.3977 | 0.16297 | 0.3731 | 0.46394 | 0.87966 | 2.0139 | 2.3211 | 5.2146 | 1.7092 | 0.20853 | 0.48403 | 0.4204 | 2.1922 | -0.3738 | 0.18407 | 0.42725 | -0.056785 | 0 | 527 | 71 | -38 | 0 | 0
9 | Matiali | 24986 | 5985 | 12135 | 6226 | 24346 | 15190 |  | 14728 | 53 |  | 0.77084 | 1.4539 | 0.69247 | 2.9172 | 1.4398 | 0.1444 | 40 | 216 | 94 | 19.8074 | 49.36% | 49.36% | 20.85% | 0.34569 | 0.02349 | 103.2608 | 101.0225 | 2.5694 | 2.9819 | 0.41244 | 101.0225 | 2.9819 | 0.26424 | 0.49839 | 0.23737 | 0.78792 | 1.4861 | 0.69247 | 2.9665 | 0.99313 | 0.20853 | 0.1444 | 0.52207 | 1.5487 | 0.10892 | 0.19181 | 0.13282 | -0.011583 | 0 | 204 | 94 | -40 | -12 | 0
10 | Maynaguri | 67180 | 49852 | 1048 | 14866 | 65766 | 39776 |  | 39574 | 4224 |  | 4.3479 | 0.09941 | 2.661 | 7.1083 | 4.7795 | 0.55491 | 20 | 1153 | 73 | 17.9621 | 67.24% | 67.24% | 20.85% | 1.5706 | 0.0653 | 100.0902 | 99.2579 | 6.6707 | 7.1679 | 0.49723 | 99.2579 | 7.1679 | 0.61166 | 0.013985 | 0.37435 | 4.3844 | 0.10024 | 2.661 | 7.1456 | 1.7581 | 0.20853 | 0.55491 | 0.65805 | 4.7022 | -0.077269 | 0.1202 | 0.31986 | -0.23505 | 5 | 1066 | 73 | -15 | -87 | 0
11 | Nagrakata | 25551 | 3981 | 14866 | 6669 | 25516 | 17593 |  | 17588 | 245 |  | 0.30522 | 1.1834 | 0.53757 | 2.0262 | 2.1923 | 0.1121 | 13 | 52 | 16 | 11.5202 | 108.2% |  |  | 0 | 0 | 103.7008 | 99.1169 | 1.8554 | 1.8554 | 0 | 113.2429 | 1.5926 | 0.15064 | 0.58405 | 0.26531 | 0.2795 | 1.0837 | 0.53757 | 1.9007 | 0.51953 | 0.20853 | 0.1121 | 0.34204 | 0.65013 | -1.5422 | 0.196 | 0.10536 | -0.0067373 | 0 | 68 | 16 | -13 | 16 | 0
12 | Rajganj | 50740 | 29823 | 2726 | 17511 | 50060 | 19461 |  | 19415 | 3124 |  | 1.2353 | 0.28583 | 1.4175 | 2.9386 | 1.1501 | 0.29559 | 18 | 1085 | 16 | 15.1355 | 39.14% | 39.14% | 20.85% | 0.15098 | 0.09394 | 114.2687 | 100.4488 | 2.6645 | 3.3429 | 0.67831 | 100.4488 | 3.3429 | 0.42037 | 0.097269 | 0.48236 | 1.4052 | 0.32515 | 1.4175 | 3.1478 | 0.87933 | 0.20853 | 0.29559 | 0.41007 | 1.2908 | 0.14072 | 0.47593 | 0.67461 | 0.37902 | 3 | 1012 | 16 | -15 | -73 | 0
13 | Sadar | 59423 | 36995 | 4458 | 17558 | 59011 | 28865 |  | 28855 | 7084 |  | 2.1976 | 0.19323 | 1.443 | 3.8339 | 1.3127 | 0.30091 | 36 | 830 | 95 | 13.2867 | 34.24% | 34.24% | 20.85% | 0.07384 | 0.03738 | 115.8765 | 113.5153 | 3.083 | 3.083 | 0 | 144.0978 | 1.9433 | 0.57322 | 0.050401 | 0.37638 | 1.7672 | 0.15539 | 1.443 | 3.3656 | 0.53216 | 0.20853 | 0.30091 | 0.32967 | 1.1096 | -0.20318 | 0.3039 | 0.43852 | 0.13761 | 1 | 653 | 95 | -35 | -177 | 0
| Total: | 633775 | 278529 | 161162 | 180087 | 619778 | 340541 | 0 | 337305 | 30209 | 0 | 27.8257 | 15.8872 | 24.9457 | 68.6586 | 33.2089 | 5.202 | 668 | 15598 | 924 | 20.3551 | 48.37% | [5 empty] | 105.3199 |  | 69.9059
|  |  | 213245 | 101708 | 317233 | 632186 | 4: 300656; 5: 2.813; 6: 24.4076 |  |  | 15.1816 | [5 empty] | 62200.1976 | 0
[6 empty] | 12408 | 4: 3.0066; 5: 22.8363
|  | 213906 | 102185 | 317343
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2010-11 Up to the Month of February' 2011
Jalpaiguri District | [14 empty] | (Rs. in lakh)
Sl. No. | Name of the Block | Actual O.B. as on 01.04.10 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability (4+5+6+7+8) | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (9+10+11+12) | Balance |  | Expenditure up to prev. months | expenditure during the month | Balance | Balance | Balance
[13 empty] | Recurring | Non-Recurring
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Alipurduar-I | 55.1042 |  |  | 736.4794 |  |  | 791.5836 |  | 485.4555 | 16.8909 | 104.5082 | 50.3528 | 8.3564 | 665.5638 | 126.0198 | 103.3158 | 274.4036 | 391.1602 | 61.85 |  | 252.6622 | 56.4542 | 103.3158 | 0.061592 | 573.8681 | 574.4589 | 599.3779 | 24.919 | 438.0416 | 161.3363 | 0.72939 | 0.025378 | 0.15702 | 0.075654 | 0.012555 | 437.1801 | 15.2112 | 94.1155 | 45.3456 | 7.5254 | 599.3779 | 665.5638 | 0
2 | Alipurduar-II | 27.1426 |  |  | 705.506 |  |  | 732.6486 |  | 441.2897 | 9.1448 | 133.337 | 18.2295 | 0.28996 | 602.2908 | 130.3578 | 101.0262 | 304.4107 | 297.8801 | 36.8578 |  | 3.5529 | -4.4117 | 101.0262 | 0.055737 | 589.7099 | 470.1956 | 589.7099 | 119.5143 | 392.2321 | 197.4779 | 0.73269 | 0.015183 | 0.22138 | 0.030267 | 0.00048143 | 432.0719 | 8.9537 | 130.5518 | 17.8487 | 0.2839 | 589.71 | 551.2643 | -51.0266
3 | Dhupguri | 55.2121 |  |  | 2343.6763 |  |  | 2398.8884 |  | 1299.12 | 98.2216 | 726.2158 | 62.7551 | 27.3581 | 2213.6706 | 185.2178 | 100.6957 | 959.1269 | 1254.5437 | 166.1673 |  | 1364.224 | 553.57 | 100.6957 | 0.20486 | 1879.1267 | 1879.1267 | 1879.1267 | 0 | 1278.7301 | 600.3966 | 0.58686 | 0.04437 | 0.32806 | 0.028349 | 0.012359 | 1102.7888 | 83.3777 | 616.4655 | 53.2711 | 23.2235 | 1879.1267 | 2107.9662 | -105.7044
4 | Falakata | 68.1981 |  |  | 826.2846 |  |  | 894.4827 |  | 458.3699 | 22.5231 | 155.4394 | 48.2509 | 7.3797 | 691.9629 | 202.5199 | 106.2884 | 292.4339 | 399.529 | 44.8451 |  | 371.8555 | 93.4222 | 106.2884 | 0.064035 | 596.6302 | 553.8766 | 608.5869 | 54.7103 | 423.0094 | 185.5775 | 0.66242 | 0.03255 | 0.22464 | 0.06973 | 0.010665 | 403.14 | 19.8092 | 136.7102 | 42.437 | 6.4905 | 608.5869 | 626.3605 | -65.6023
5 | Kalchini | 43.4726 |  |  | 1046.1538 |  |  | 1089.6264 |  | 635.2248 | 24.6392 | 233.5902 | 24.8103 | 8.8059 | 927.0703 | 162.5561 | 120.1509 | 214.0691 | 713.0012 | 90.2812 | 4.3138 | 335.5909 | 74.4711 | 120.1509 | 0.085792 | 752.6468 | 752.6468 | 752.6468 | 0 | 466.2353 | 286.4115 | 0.6852 | 0.026577 | 0.25197 | 0.026762 | 0.0094987 | 515.7105 | 20.0034 | 189.6414 | 20.1424 | 7.1491 | 752.6468 | 796.327 | -130.7433
6 | Kumargram | 10.6689 |  |  | 1232.9802 |  |  | 1243.6491 |  | 693.6855 | 46.027 | 351.9201 | 43.1808 | 33.2223 | 1168.0357 | 75.6134 | 107.4324 | 530.3212 | 637.7145 | 81.51 |  | 535.6372 | 175.6395 | 107.4324 | 0.10809 | 1007.1138 | 1046.5287 | 1058.2784 | 11.7497 | 748.4184 | 309.86 | 0.59389 | 0.039405 | 0.30129 | 0.036969 | 0.028443 | 628.5017 | 41.702 | 318.8511 | 39.1232 | 30.1005 | 1058.2784 | 1137.3277 | -30.708
7 | Madarihat-Birpara | 21.0557 |  |  | 1039.08 |  |  | 1060.1357 |  | 685.3179 | 22.6358 | 213.2441 | 8.2921 | 22.125 | 951.6148 | 108.5208 | 100.683 | 325.6474 | 625.9675 | 84.9085 |  | 408.5993 | 81.3194 | 100.683 | 0.088064 | 840.8678 | 840.8678 | 840.8678 | 0 | 550.854 | 290.0139 | 0.72016 | 0.023787 | 0.22409 | 0.0087137 | 0.02325 | 605.562 | 20.0014 | 188.4272 | 7.3271 | 19.5501 | 840.8678 | 934.5582 | -17.0566
8 | Mal | 52.4402 |  |  | 943.8146 |  |  | 996.2548 |  | 529.7855 | 28.8155 | 218.8047 | 25.301 | 8.8881 | 811.5948 | 184.66 | 105.8912 | 367.8294 | 443.7654 | 95.95 |  | 410.8089 | 123.4423 | 105.8912 | 0.075106 | 741.3659 | 567.0824 | 741.3659 | 174.2835 | 567.0824 | 174.2835 | 0.65277 | 0.035505 | 0.2696 | 0.031174 | 0.010951 | 483.9421 | 26.322 | 199.8711 | 23.1116 | 8.119 | 741.3659 | 803.7225 | -7.8723
9 | Matiali | 19.6377 |  |  | 423.6362 |  |  | 443.2739 |  | 301.2366 | 15.5691 | 53.4093 | 12.0219 | 7.8137 | 390.0506 | 53.2233 | 103.2608 | 147.3002 | 242.7504 | 83.8542 |  | 166.6748 | 41.4683 | 103.2608 | 0.036096 | 328.6891 | 328.6891 | 328.6891 | 0 | 234.0252 | 94.6639 | 0.7723 | 0.039916 | 0.13693 | 0.030821 | 0.020033 | 253.847 | 13.1198 | 45.0071 | 10.1306 | 6.5845 | 328.6891 | 372.6225 | -17.4281
10 | Maynaguri | 90.7682 |  |  | 1153.8565 |  |  | 1244.6246 |  | 711.4751 | 27.4671 | 203.3511 | 29.2321 | 13.4287 | 984.9541 | 259.6706 | 100.0902 | 266.2758 | 718.6783 | 80.1736 |  | 430.2199 | 56.252 | 100.0902 | 0.091149 | 849.2556 | 850.1292 | 874.5503 | 24.4211 | 620.145 | 254.4053 | 0.72234 | 0.027887 | 0.20646 | 0.029679 | 0.013634 | 631.7257 | 24.3883 | 180.5574 | 25.9555 | 11.9235 | 874.5503 | 920.1095 | -64.8446
11 | Nagrakata | 10.2604 |  |  | 359.4357 |  |  | 369.6962 |  | 210.1155 | 11.2568 | 61.0706 | 17.5809 | 3.1045 | 303.1282 | 66.5679 | 103.7008 | 73.3785 | 229.7498 | 29.6664 |  | 43.2724 | 25.3537 | 103.7008 | 0.028052 | 271.4775 | 271.4775 | 271.4775 | 0 | 170.4715 | 101.006 | 0.69316 | 0.037136 | 0.20147 | 0.057998 | 0.010242 | 188.1765 | 10.0815 | 54.694 | 15.7452 | 2.7803 | 271.4775 | 290.0696 | -13.0586
12 | Rajganj | 15.6417 |  |  | 579.1846 |  |  | 594.8263 |  | 335.7855 | 12.7144 | 71.3249 | 13.7809 | 5.2775 | 438.8832 | 155.9431 | 114.2687 | 158.2235 | 280.6597 | 52.4855 |  | 214.7079 | 30.3348 | 114.2687 | 0.040615 | 359.2629 | 359.2629 | 359.2629 | 0 | 250.2098 | 109.0531 | 0.76509 | 0.02897 | 0.16251 | 0.0314 | 0.012025 | 274.8687 | 10.4078 | 58.3855 | 11.2808 | 4.3201 | 359.2629 | 431.0233 | -7.8599
13 | Sadar | 36.488 |  |  | 793.8017 |  |  | 830.2898 |  | 444.2565 | 21.5284 | 123.129 | 46.9019 | 21.3542 | 657.17 | 173.1197 | 115.8765 | 198.2151 | 458.9549 | 61.025 |  | 233.9871 | 78.6092 | 115.8765 | 0.060815 | 482.3963 | 482.3963 | 482.3963 | 0 | 303.7427 | 178.6536 | 0.67601 | 0.032759 | 0.18736 | 0.07137 | 0.032494 | 326.107 | 15.8029 | 90.3829 | 34.4284 | 15.6751 | 482.3963 | 583.1518 | -74.0182
| Total | 506.0906 | 0 | 0 | 12183.8896 |  | 0 | 12689.9802 | 0 | 7231.118 | 357.4336 | 2649.3442 | 400.69 | 167.4042 | 10805.99 | 1883.9902 | 1382.6807 | 4111.6353 | 6694.3547 | 969.5746 |  | 4771.7929 | 1385.9249 |  |  | 9272.4106 | 8976.7386 | 9386.3365 | 409.5979 | 11215.5879 | [11 empty] | 9386.3365
1 | Line Deptt. | 222.78 |  |  | 102.5618 |  |  | 325.3418 |  | 270.62 |  |  |  |  | 270.62 | 54.7218 |  | 83.25 | [7 empty] | -44.8228
2 | District Cell | 983.81 |  | 555.56 | 9000 | 1033.33 | 0 | 11572.7 |  |  |  |  | 39.001 | 29.5661 | 68.5671 |  |  | 29.3346 | [7 empty] | 641.4529 |  | 41.962 | 0.5688 | 23.868 | 23.868 | 18.094
| Total | 1206.59 | 0 | 555.56 | 9000 | 1033.33 | 0 | 11898.0418 |  | 270.62 | 0 | 0 | 39.001 | 29.5661 | 339.1871 |  |  | 407.7541
| G.T. | 1712.6806 | 0 | 555.56 | 9000 | 1033.33 | 0 | 12301.5706 | 0 | 7501.738 | 357.4336 | 2649.3442 | 439.691 | 196.9702 | 11145.1771 | 1156.3935 | 5238.4338 | 4519.3894 |  | 5906.7433 |  |  |  |  | 76.3368 | 9611.5977
[9 empty] | -2115.7653 | -2386.3853 |  |  | 367.8229 | 11513 | 9317.2334 |  | -43.9548 | 76.1962 | [6 empty] | 7486.3369 | 44.8228
[10 empty] | 4864941 |  |  |  | 0.96957 | 9033.6771 | [9 empty] | 7825.524 | 9257.4035 |  | 11945.1771
[10 empty] | 48.6494 |  |  | District Programme Coordinator |  | 8758.7918 | [10 empty] | 8976.7386 |  | 9257.4035
[10 empty] | 68.5671 |  |  | MGNREGS, Jalpaiguri | [12 empty] | -1829.2514
[9 empty] | 0.5688 | 0.4312 |  |  | & | [12 empty] | 11605.99 | 11945.1771
[9 empty] | 27.6718 | 20.9776 |  |  | District Magistrate | [12 empty] | 8758.7918
[13 empty] | Jalpaiguri | [11 empty] | exp. 4 d month | 3186.3853
0.5688
53.008
30.151
[13 empty] | 30.151 | 22.857
Note on K27: N.R.E.G.S.4: Feb' 11
Note on N28: N.R.E.G.S.4: Feb' 11
Note on O28: N.R.E.G.S.4: Feb' 11

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2010-11 Up to the Month of February' 2011 | [19 empty] | Physical Performance Under NREGA During the year 2010-11 Up to the Month of February' 2011 | [17 empty] | Physical Performance Under NREGA During the year 2010-11 Up to the Month of February' 2011
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 596 | 963209.7996 | 432.5964 | 914 | 1476192.4867 | 653.1388 | 353 | 1557.7435 | 260.3826 | 350 | 1479.7672 | 253.1239 | 437 | 574.2827 | 363.5022 | 344 | 358.1093 | 272.0561 | 341 | 817.5662 | 181.8673 | 193 | 403.6587 | 97.6974 | 123 | 86671.6889 | 98.6783 | 149 | 115570.3503 | 117.1239 | 1319 | 4034.6415 | 1417.2179 | 958 | 3077.6964 | 789.1307 | 484 | 395.5071 | 823.7928 | 465 | 320.0459 | 1041.1425 | 1257 | 2128.7307 | 1947.2945 | 1021 | 568.5109 | 1759.7704 | 0 | 0 | 0 | 0 | 0 | 0 | 4910 | 5525.3321 | 4394 | 4983.1837 | 10508.5158 | 10508.5158 | -3.881e-06
District Magistrate
Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2010-11 Up to the Month of February' 2011
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 4469 | 326 | 274 | 1 | 237 | 38 | 0 | 0 | 0 | 1 | 4795 | 275 | 0.10409 | 275 | 275 | 275 | 237 | 274
2 | Alipurduar-II | 4073 | 384 | 141 | 4 | 107 | 38 | 0 | 0 | 0 | 0 | 4457 | 145 | 0.054883 | 145 | 145 | 145 | 107 | 141
3 | Dhupguri | 12507 | 658 | 855 | 10 | 823 | 42 | 0 | 0 | 3 | 0 | 13165 | 865 | 0.3274 | 865 | 865 | 865 | 823 | 855
4 | Falakata | 2853 | 1548 | 249 | 3 | 218 | 34 | 0 | 0 | 1 | 1 | 4401 | 252 | 0.095382 | 252 | 252 | 252 | 218 | 249
5 | Kalchini | 5206 | 189 | 413 | 3 | 384 | 32 | 0 | 0 | 0 | 1 | 5395 | 416 | 0.15746 | 416 | 416 | 416 | 384 | 413
6 | Kumargram | 6536 | 53 | 101 | 1 | 55 | 47 | 0 | 0 | 1 | 0 | 6589 | 102 | 0.038607 | 102 | 102 | 102 | 55 | 101
7 | Madarihat-Birpara | 6761 | 185 | 400 | 10 | 380 | 30 | 0 | 0 | 0 | 0 | 6946 | 410 | 0.15519 | 410 | 410 | 410 | 380 | 400
8 | Mal | 4741 | 364 | 477 | 1 | 444 | 34 | 0 | 0 | 0 | 0 | 5105 | 478 | 0.18092 | 478 | 478 | 478 | 444 | 477
9 | Matiali | 2067 | 910 | 258 | 1 | 181 | 78 | 0 | 0 | 1 | 1 | 2977 | 259 | 0.098032 | 259 | 259 | 259 | 181 | 258
10 | Maynaguri | 5191 | 2062 | 973 | 1 | 932 | 42 | 0 | 0 | 0 | 0 | 7253 | 974 | 0.36866 | 974 | 974 | 974 | 932 | 973
11 | Nagrakata | 1364 | 704 | 178 | 1 | 148 | 31 | 0 | 0 | 1 | 1 | 2068 | 179 | 0.067752 | 179 | 179 | 179 | 148 | 178
12 | Rajganj | 2122 | 877 | 213 | 2 | 161 | 54 | 0 | 0 | 0 | 0 | 2999 | 215 | 0.081378 | 215 | 215 | 215 | 161 | 213
13 | Sadar | 3460 | 452 | 337 | 3 | 302 | 38 | 0 | 0 | 1 | 0 | 3912 | 340 | 0.12869 | 340 | 340 | 340 | 302 | 337
| Total | 61350 | 8712 | 4869 | 41 | 4372 | 538 | 0 | 0 | 8 | 5 |  | 2642 |  |  | 4910
2642
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of February' 2011)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | - | - | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of February' 2011)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | - | - | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri