## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of November' 2010
MPR- Part-I
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Register | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals | Avg. No. of Employment Provided per Household | % Women
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C | bar: 9
1 | 2 |  | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Alipurduar-I | 39654 | 20665 | 8896 | 10093 | 39654 | 16178 |  | 16178 | 5917 |  | 2.0198 | 0.68122 | 0.56609 | 3.2671 | 1.2466 | 0.12962 | 7 | 1269 | 26 | 20.1948 | 38.16% | 38.16% | 22.9% | 0.25665 | 0.03277 | 114.8807 | 101.057 | 2.1688 | 3.2671 | 1.0983 | 97.783 | 3.2671 | 0.61822 | 0.20851 | 0.17327 | 2.0198 | 0.68122 | 0.56609 | 0.98478 | 0.22898 | 0.12962 | 0.38156 | 1.2466 | 0 | 0.22898 | 0.12962 | 0 | 7 | 1269 | 26 | 0 | 0 | 0
2 | Alipurduar-II | 41382 | 19700 | 9478 | 12204 | 41382 | 17949 |  | 17949 | 7989 |  | 1.131 | 0.37896 | 1.5524 | 3.0623 | 0.95266 | 0.1395 | 16 | 256 | 29 | 17.0611 | 31.11% | 31.11% | 8.986% | 0.36819 | 0.03295 | 146.1372 | 122.2134 | 2.2479 | 3.0623 | 0.8144 | 122.2134 | 3.0623 | 0.36932 | 0.12375 | 0.50693 | 1.131 | 0.37896 | 1.5524 | 0.87223 | 0.089865 | 0.1395 | 0.31109 | 0.95266 | 0 | 0.089865 | 0.1395 | 0 | 16 | 256 | 29 | 0 | 0 | 0
3 | Dhupguri | 76270 | 38793 | 16434 | 21043 | 76270 | 31892 |  | 31492 | 12773 |  | 5.2908 | 1.8597 | 2.3926 | 9.5431 | 4.2944 | 0.51027 | 0 | 912 | 41 | 30.3033 | 45% | 45% | 21.33% | 1.3983 | 0.18765 | 99.9536 | 99.9396 | 8.3906 | 9.5431 | 1.1525 | 99.9396 | 9.5431 | 0.55442 | 0.19487 | 0.25071 | 5.2908 | 1.8597 | 2.3926 | 2.9887 | 0.21327 | 0.51027 | 0.45 | 4.2944 | 0 | 0.21327 | 0.51027 | 0 | 0 | 912 | 41 | 0 | 0 | 0
4 | Falakata | 48075 | 22127 | 9574 | 16374 | 48075 | 30756 |  | 30124 | 16629 |  | 1.8775 | 0.7454 | 1.2299 | 3.8527 | 1.6833 | 0.14895 | 8 | 1500 | 41 | 12.7895 | 43.69% | 43.69% | 12.11% | 0.66264 | 0.049 | 103.2914 | 102.5062 | 3.1592 | 3.8527 | 0.69351 | 102.5062 | 3.8527 | 0.48731 | 0.19347 | 0.31922 | 1.8775 | 0.7454 | 1.2299 | 1.2246 | 0.12111 | 0.14895 | 0.43691 | 1.6833 | 0 | 0.12111 | 0.14895 | 0 | 8 | 1500 | 41 | 0 | 0 | 0
5 | Kalchini | 54907 | 8354 | 31028 | 15525 | 54907 | 17434 |  | 17434 | 6674 |  | 0.58645 | 1.5368 | 1.2665 | 3.3897 | 1.5133 | 0.056517 | 0 | 2157 | 17 | 19.4428 | 44.65% | 44.65% | 4.463% | 0.27484 | 0.00979 | 123.0278 | 111.013 | 2.3291 | 3.3897 | 1.0606 | 111.013 | 3.3897 | 0.17301 | 0.45337 | 0.37362 | 0.58645 | 1.5368 | 1.2665 | 1.4922 | 0.044626 | 0.056517 | 0.4192 | 1.5133 | 0 | 0.044626 | 0.056517 | 0 | 0 | 2157 | 17 | 0 | 0 | 0
6 | Kumargram | 38333 | 15468 | 13514 | 9351 | 38333 | 31280 |  | 30243 | 3798 |  | 1.9878 | 2.9817 | 1.6565 | 6.626 | 2.9817 | 0.43624 | 0 | 5126 | 278 | 21.9092 | 45% | 45% | 26.34% | 1.0794 | 0.15792 | 81 | 95.146 | 5.5023 | 6.626 | 1.1237 | 82.8043 | 6.626 | 0.3 | 0.45 | 0.25 | 1.9878 | 2.9817 | 1.6565 | 2.4868 | 0.26335 | 0.43624 | 0.1234 | 2.9817 | 0 | 0.26335 | 0.43624 | 0 | 0 | 5126 | 278 | 0 | 0 | 0
7 | Madarihat-Birpara | 38064 | 7771 | 16287 | 14006 | 38064 | 21282 |  | 21282 | 9442 |  | 1.0386 | 1.9684 | 1.8732 | 4.8802 | 2.608 | 0.36682 | 22 | 201 | 127 | 22.9309 | 53.44% | 53.44% | 19.58% | 0.36946 | 0.03966 | 80.1581 | 100.4944 | 3.8308 | 4.8802 | 1.0494 | 84.4516 | 4.8802 | 0.21282 | 0.40335 | 0.38383 | 1.0386 | 1.9684 | 1.8732 | 1.9789 | 0.19583 | 0.36682 | 0.53442 | 2.608 | 0 | 0.19583 | 0.36682 | 0 | 22 | 201 | 127 | 0 | 0 | 0
8 | Mal | 57212 | 18393 | 20598 | 18221 | 57212 | 15257 |  | 15257 | 8791 |  | 1.6582 | 1.4641 | 1.6942 | 4.8166 | 2.0249 | 0.31185 | 0 | 527 | 71 | 31.5697 | 42.04% | 42.04% | 18.41% | 0.31873 | 0.04153 | 116.1972 | 98.1499 | 3.4679 | 4.8166 | 1.3487 | 98.1499 | 4.8166 | 0.34428 | 0.30397 | 0.35175 | 1.6582 | 1.4641 | 1.6942 | 1.7092 | 0.18407 | 0.31185 | 0.4204 | 2.0249 | 0 | 0.18407 | 0.31185 | 0 | 0 | 527 | 71 | 0 | 0 | 0
9 | Matiali | 24986 | 5892 | 13019 | 6075 | 24986 | 12228 |  | 12228 | 4531 |  | 0.57854 | 1.0801 | 0.47409 | 2.1328 | 1.1134 | 0.090933 | 0 | 204 | 94 | 17.4417 | 52.21% | 52.21% | 19.18% | 0.36567 | 0.02161 | 99.6517 | 101.122 | 1.6615 | 2.1328 | 0.47128 | 101.122 | 2.1328 | 0.27126 | 0.50645 | 0.22229 | 0.57854 | 1.0801 | 0.47409 | 0.99313 | 0.19181 | 0.090933 | 0.52207 | 1.1134 | 0 | 0.19181 | 0.090933 | 0 | 0 | 204 | 94 | 0 | 0 | 0
10 | Maynaguri | 66197 | 49933 | 1131 | 15133 | 66197 | 24169 |  | 24169 | 10689 |  | 4.74 | 0.11396 | 1.2891 | 6.143 | 4.0424 | 0.15495 | 5 | 1066 | 73 | 25.417 | 65.81% | 65.81% | 12.02% | 1.5372 | 0.03764 | 124.1776 | 94.9998 | 3.4615 | 6.143 | 2.6815 | 94.9998 | 6.143 | 0.7716 | 0.018551 | 0.20985 | 4.74 | 0.11396 | 1.2891 | 1.7581 | 0.1202 | 0.15495 | 0.65805 | 4.0424 | 0 | 0.1202 | 0.15495 | 0 | 5 | 1066 | 73 | 0 | 0 | 0
11 | Nagrakata | 25551 | 3983 | 14888 | 6680 | 25551 | 10941 |  | 9341 | 1735 |  | 0.25219 | 0.90638 | 0.43401 | 1.5926 | 0.54473 | 0.085066 | 0 | 68 | 16 | 17.0494 | 34.2% |  |  | 0 | 0 | 98.417 | 99.0572 | 0.73439 | 1.5926 | 0.85819 | 80.1134 | 1.5926 | 0.15835 | 0.56913 | 0.27252 | 0.25219 | 0.90638 | 0.43401 | 0.51953 | 0.196 | 0.085066 | 0.34204 | 0.54473 | 0 | 0.196 | 0.085066 | 0 | 0 | 68 | 16 | 0 | 0 | 0
12 | Rajganj | 50131 | 29820 | 2737 | 17574 | 50131 | 12221 |  | 12221 | 3398 |  | 1.2233 | 0.29172 | 0.71267 | 2.2277 | 0.91353 | 0.33918 | 3 | 1012 | 16 | 18.2286 | 41.01% | 41.01% | 47.59% | 0.15819 | 0.09394 | 101.7596 | 101.4575 | 1.5863 | 2.2277 | 0.6414 | 101.4575 | 2.2277 | 0.54914 | 0.13095 | 0.31991 | 1.2233 | 0.29172 | 0.71267 | 0.87933 | 0.47593 | 0.33918 | 0.41007 | 0.91353 | 0 | 0.47593 | 0.33918 | 0 | 3 | 1012 | 16 | 0 | 0 | 0
13 | Sadar | 58761 | 36789 | 4051 | 17921 | 58761 | 17860 |  | 17860 | 18011 |  | 1.1965 | 0.06661 | 0.68015 | 1.9433 | 0.64064 | 0.2067 | 1 | 653 | 95 | 10.8806 | 32.97% | 32.97% | 30.39% | 0.0711 | 0.03738 | 142.243 | 114.9622 | 1.3057 | 1.9433 | 0.63753 | 114.7449 | 1.9433 | 0.61572 | 0.034277 | 0.35 | 1.1965 | 0.06661 | 0.68015 | 0.53216 | 0.3039 | 0.2067 | 0.32967 | 0.64064 | 0 | 0.3039 | 0.2067 | 0 | 1 | 653 | 95 | 0 | 0 | 0
| Total: | 619523 | 277688 | 161635 | 180200 | 619523 | 259447 | 0 | 255778 | 110377 | 0 | 23.5807 | 14.0751 | 15.8212 | 53.477 | 24.5597 | 2.9766 | 62 | 14951 | 924 | 20.9076 | 45.93% | [5 empty] | 97.7629 |  | 53.477
[21 empty] | #DIV/0! | #DIV/0!
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2010-11 Up to the Month of November' 2010
Jalpaiguri District | [14 empty] | (Rs. in lakh)
Sl. No. | Name of the Block | Actual O.B. as on 01.04.10 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability (4+5+6+7+8) | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (9+10+11+12) | Balance |  | Expenditure up to prev. months | expenditure during the month | Balance | Balance | Balance
[13 empty] | Recurring | Non-Recurring
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Alipurduar-I | 55.1042 |  |  | 519.4447 |  |  | 574.5489 |  | 319.4674 | 14.0112 | 101.4968 | 43.3908 | 6.8355 | 485.2017 | 89.3472 | 97.7826 | 274.4036 | 210.7981 | 61.85 |  | 72.3 | 53.4428 | 0.06433 | 0 | 483.6914 | 485.2017 | -7.5175e-06 | 438.0416 | 47.1601 | 0.65842 | 0.028877 | 0.20918 | 0.089428 | 0.014088 | 319.4674 | 14.0112 | 101.4968 | 43.3908 | 6.8355 | 485.2017
2 | Alipurduar-II | 27.1426 |  |  | 540.7355 |  |  | 567.8781 |  | 374.253 | 7.0388 | 111.1131 | 13.9473 | 0.16556 | 506.5177 | 61.3604 | 122.213 | 304.4107 | 202.107 | 36.8578 |  | -92.2202 | -26.6356 | 0.067156 | 0 | 427.0204 | 506.5177 | 4.7368e-06 | 392.2321 | 114.2857 | 0.73887 | 0.013896 | 0.21937 | 0.027536 | 0.00032686 | 374.253 | 7.0388 | 111.1131 | 13.9473 | 0.16556 | 506.5177
3 | Dhupguri | 55.2121 |  |  | 1635.9963 |  |  | 1691.2084 |  | 953.734 | 77.4666 | 379.0863 | 16.482 | 27.861 | 1454.6299 | 236.5785 | 99.9396 | 959.1269 | 495.503 | 166.1673 |  | 605.1833 | 206.4404 | 0.19286 | 0 | 1403.1981 | 1454.6299 | -7.5562e-06 | 1278.7301 | 175.8998 | 0.65565 | 0.053255 | 0.26061 | 0.011331 | 0.019153 | 953.734 | 77.4666 | 379.0863 | 16.482 | 27.861 | 1454.6299
4 | Falakata | 68.1981 |  |  | 589.8187 |  |  | 658.0168 |  | 394.9271 | 19.8173 | 124.8813 | 4.3101 | 6.9261 | 550.862 | 107.1548 | 102.506 | 292.4339 | 258.4281 | 44.8451 |  | 230.7546 | 62.8641 | 0.073036 | 0 | 436.7769 | 550.862 | 9.9783e-07 | 423.0094 | 127.8526 | 0.71693 | 0.035975 | 0.2267 | 0.0078243 | 0.012573 | 394.9271 | 19.8173 | 124.8813 | 4.3101 | 6.9261 | 550.862
5 | Kalchini | 43.4726 |  |  | 603.2694 |  |  | 646.742 |  | 376.2962 | 20.4132 | 112.849 | 21.5204 | 8.6128 | 539.6917 | 107.0503 | 111.013 | 214.0691 | 325.6226 | 90.2812 | 4.3138 | -51.7878 | -46.27 | 0.071555 | 0 | 513.5482 | 539.6917 | 3.1369e-06 | 466.2353 | 73.4564 | 0.69724 | 0.037824 | 0.2091 | 0.039875 | 0.015959 | 376.2962 | 20.4132 | 112.849 | 21.5204 | 8.6128 | 539.6917
6 | Kumargram | 10.6689 |  |  | 892.4402 |  |  | 903.1091 |  | 548.6624 | 37.5687 | 246.2797 | 10.0472 | 14.1277 | 856.6857 | 46.4234 | 82.8043 | 530.3212 | 326.3645 | 81.51 |  | 224.2871 | 69.9991 | 0.11358 | 0 | 841.4091 | 856.6857 | -9.5391e-06 | 748.4184 | 108.2672 | 0.64045 | 0.043854 | 0.28748 | 0.011728 | 0.016491 | 548.6624 | 37.5687 | 246.2797 | 10.0472 | 14.1277 | 856.6857
7 | Madarihat-Birpara | 21.0557 |  |  | 733.8605 |  |  | 754.9162 |  | 412.1364 | 17.6881 | 209.0808 | 9.9182 | 23.9319 | 672.7554 | 82.1608 | 84.4516 | 325.6474 | 347.1081 | 84.9085 |  | 129.7399 | 77.1561 | 0.089197 | 672.7554 | 672.7554 | 672.7554 | 0 | 550.854 | 121.9015 | 0.61261 | 0.026292 | 0.31078 | 0.014743 | 0.035573 | 412.1364 | 17.6881 | 209.0808 | 9.9182 | 23.9319 | 672.7554
8 | Mal | 52.4402 |  |  | 694.1036 |  |  | 746.5438 |  | 472.748 | 27.9815 | 130.6969 | 3.043 | 6.9577 | 641.4271 | 105.1167 | 98.1499 | 367.8294 | 273.5977 | 95.95 |  | 240.6412 | 35.3345 | 0.085043 | 0 | 567.0824 | 641.4271 | -1.3319e-06 | 567.0824 | 74.3448 | 0.73703 | 0.043624 | 0.20376 | 0.0047441 | 0.010847 | 472.748 | 27.9815 | 130.6969 | 3.043 | 6.9577 | 641.4271
9 | Matiali | 19.6377 |  |  | 293.3602 |  |  | 312.9979 |  | 215.6694 | 9.1406 | 34.1185 | 1.9043 | 3.9262 | 264.759 | 48.2389 | 101.1217 | 147.3002 | 117.4588 | 83.8542 |  | 41.3832 | 22.1776 | 0.035103 | 0 | 251.8917 | 264.759 | 1.3798e-06 | 234.0252 | 30.7338 | 0.81459 | 0.034524 | 0.12887 | 0.0071925 | 0.014829 | 215.6694 | 9.1406 | 34.1185 | 1.9043 | 3.9262 | 264.759
10 | Maynaguri | 90.7682 |  |  | 790.4582 |  |  | 881.2264 |  | 583.587 | 19.9907 | 94.6434 | 2.7726 | 6.9625 | 707.9562 | 173.2702 | 94.9997 | 266.2758 | 441.6804 | 80.1736 |  | 153.222 | -52.4557 | 0.093864 | 0 | 687.1914 | 707.9562 | -8.3341e-07 | 620.145 | 87.8112 | 0.82433 | 0.028237 | 0.13369 | 0.0039164 | 0.0098347 | 583.587 | 19.9907 | 94.6434 | 2.7726 | 6.9625 | 707.9562
11 | Nagrakata | 10.2604 |  |  | 245.3931 |  |  | 255.6535 |  | 127.587 | 9.6134 | 61.9841 | 14.3529 | 1.9669 | 215.5043 | 40.1492 | 80.1134 | 73.3785 | 142.1258 | 29.6664 |  | -44.3516 | 26.2672 | 0.028572 | 215.5043 | 215.5043 | 215.5043 | 1e-05 | 170.4715 | 45.0328 | 0.59204 | 0.044609 | 0.28762 | 0.066601 | 0.009127 | 127.587 | 9.6134 | 61.9841 | 14.3529 | 1.9669 | 215.5043
12 | Rajganj | 15.6417 |  |  | 370.5736 |  |  | 386.2153 |  | 226.019 | 9.5509 | 36.8652 | 2.4672 | 13.3219 | 288.2243 | 97.991 | 101.4576 | 158.2235 | 130.0008 | 52.4855 |  | 64.0491 | -4.1249 | 0.038214 | 0 | 267.8833 | 288.2243 | 1.7632e-06 | 250.2098 | 38.0145 | 0.78418 | 0.033137 | 0.1279 | 0.0085601 | 0.046221 | 226.019 | 9.5509 | 36.8652 | 2.4672 | 13.3219 | 288.2243
13 | Sadar | 36.488 |  |  | 420.2213 |  |  | 456.7094 |  | 222.9803 | 14.4176 | 72.6651 | 4.8521 | 43.2524 | 358.1675 | 98.5418 | 114.7449 | 198.2151 | 159.9524 | 61.025 |  | -65.0154 | 28.1453 | 0.047487 | 0 | 355.7875 | 358.1675 | -1.004e-07 | 303.7427 | 54.4249 | 0.62256 | 0.040254 | 0.20288 | 0.013547 | 0.12076 | 222.9803 | 14.4176 | 72.6651 | 4.8521 | 43.2524 | 358.1675
| Total | 506.0906 | 0 | 0 | 8329.6752 |  | 0 | 8835.7658 | 0 | 5228.0672 | 284.6988 | 1715.7602 | 149.0081 | 164.8482 | 7542.3825 | 1293.3834 | 1291.2974 | 4111.6353 | 3430.7472 | 969.5746 |  | 1508.1854 | 452.3409 |  | 888.2597 | 7123.7401 | 7542.3825 | -4.864e-06 | 7542.3825 | [11 empty] | 7542.3825
1 | Line Deptt. | 222.78 |  |  | 102.5618 |  |  | 325.3418 |  | 170.394 |  |  |  |  | 170.394 | 154.9478 |  | 83.25
2 | District Cell | 983.81 |  | 555.56 | 7000 | 1033.33 | 0 | 9572.7 |  |  |  |  | 24.7522 | 18.7643 | 43.5165 |  |  | 29.3346 | [8 empty] | 41.962 | 0.5688 | 23.868 | 23.868 | 18.094
| Total | 1206.59 | 0 | 555.56 | 7000 | 1033.33 | 0 | 9898.0418 |  | 170.394 | 0 | 0 | 24.7522 | 18.7643 | 213.9105 |  |  | 257.427
| G.T. | 1712.6806 | 0 | 555.56 | 7000 | 1033.33 | 0 | 10301.5706 | 0 | 5398.4612 | 284.6988 | 1715.7602 | 173.7603 | 183.6125 | 7756.293 | 2545.2776 | 5238.4338 | 4369.0623 |  | 2517.8592 |  |  |  | 53.1253
[17 empty] | -56.7659 | 54.247 | [5 empty] | 7486.3369
[24 empty] | 7700.2474 |  |  | 8556.293
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri
Note on K27: N.R.E.G.S.4: Nov' 10
Note on N28: N.R.E.G.S.4: For the month of Nov, 10
Note on O28: N.R.E.G.S.4: For the month of Nov, 10

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2010-11 Up to the Month of November' 2010 | [19 empty] | Physical Performance Under NREGA During the year 2010-11 Up to the Month of November' 2010 | [17 empty] | Physical Performance Under NREGA During the year 2010-11 Up to the Month of November' 2010
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 432 | 710257.4133 | 331.4453 | 560 | 885649.114 | 341.8284 | 110 | 499.8935 | 80.2202 | 405 | 1748.5569 | 264.1126 | 259 | 310.4598 | 214.0461 | 349 | 391.0331 | 193.5893 | 214 | 475.2078 | 116.5304 | 166 | 365.8035 | 61.5603 | 123 | 86671.6889 | 98.6783 | 124 | 95496.4026 | 71.8267 | 833 | 2552.4696 | 914.3641 | 696 | 2371.443 | 514.215 | 373 | 298.5524 | 585.2306 | 499 | 305.7856 | 686.1067 | 917 | 1502.4344 | 1190.0341 | 1290 | 643.7034 | 1735.1321 | 0 | 0 | 0 | 0 | 0 | 0 | 3261 | 3530.5491 | 4089 | 3868.3711 | 7398.9201 | 7398.9201 | 0
District Magistrate
Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2010-11 Up to the Month of November' 2010
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 2611 | 21 | 75 | 1 | 75 | 6 | 0 | 0 | 0 | 1 | 2632 | 81 | 0.030659 | 81 | 76
2 | Alipurduar-II | 2354 | 18 | 79 | 4 | 87 | 8 | 0 | 0 | 0 | 0 | 2372 | 95 | 0.035958 | 95 | 83
3 | Dhupguri | 8592 | 55 | 638 | 10 | 647 | 12 | 0 | 0 | 3 | 0 | 8647 | 659 | 0.24943 | 659 | 648
4 | Falakata | 1814 | 1391 | 178 | 3 | 158 | 6 | 0 | 0 | 1 | 1 | 3205 | 164 | 0.062074 | 164 | 181
5 | Kalchini | 3352 | 19 | 425 | 3 | 398 | 3 | 0 | 0 | 0 | 1 | 3371 | 401 | 0.15178 | 401 | 428
6 | Kumargram | 7838 | 53 | 41 | 1 | 46 | 15 | 0 | 0 | 1 | 0 | 7891 | 61 | 0.023089 | 61 | 42
7 | Madarihat-Birpara | 4008 | 16 | 171 | 10 | 181 | 11 | 0 | 0 | 0 | 0 | 4024 | 192 | 0.072672 | 192 | 181
8 | Mal | 4138 | 11 | 198 | 1 | 198 | 6 | 0 | 0 | 0 | 0 | 4149 | 204 | 0.077214 | 204 | 199
9 | Matiali | 1300 | 645 | 188 | 1 | 168 | 39 | 0 | 0 | 1 | 1 | 1945 | 207 | 0.07835 | 207 | 189
10 | Maynaguri | 4553 | 46 | 315 | 1 | 335 | 11 | 0 | 0 | 0 | 0 | 4599 | 346 | 0.13096 | 346 | 316
11 | Nagrakata | 1216 | 105 | 105 | 1 | 124 | 6 | 0 | 0 | 1 | 1 | 1321 | 130 | 0.049205 | 130 | 106
12 | Rajganj | 1868 | 41 | 165 | 2 | 164 | 11 | 0 | 0 | 0 | 0 | 1909 | 175 | 0.066238 | 175 | 167
13 | Sadar | 1631 | 65 | 64 | 3 | 61 | 6 | 0 | 0 | 1 | 0 | 1696 | 67 | 0.02536 | 67 | 67
| Total | 45275 | 2486 | 2642 | 41 | 2642 | 140 | 0 | 0 | 8 | 5 |  | 2642 |  |  | 2683
|  |  |  | 2642 |  | 2642 | [6 empty] | 2642
|  |  |  | 0 |  | 0
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of November' 2010)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | - | - | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of November' 2010)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | - | - | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri