## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
part I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of FEBRUARY 2012 (for the financial year 2011-12)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 |  | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Alipurduar-I | 40448 | 21046 | 8586 | 10816 | 40448 | 14034 | 7609 | 14034 | 5000 | 298225 | 2.1149 | 0.74766 | 0.55064 | 3.4132 | 1.53 | 0.03814 | 5 | 1048 | 39 | 44.8265 | 24.3207
2 | Alipurduar-II | 45215 | 17364 | 5073 | 22778 | 45215 | 13725 | 8831 | 13725 | 1204 | 346096 | 0.76048 | 0.29558 | 1.0081 | 2.0642 | 0.71 | 1.4 | 28 | 217 | 22 | 34.3961 | 15.0396
3 | Dhupguri | 80508 | 39105 | 16764 | 22691 | 78560 | 36866 | 25228 | 36866 | 30899 | 988720 | 6.1104 | 2.0465 | 2.5191 | 10.676 | 3.97 | 0.09 | 10 | 2102 | 46 | 37.1864 | 28.9588
4 | Falakata | 51791 | 23402 | 9952 | 18437 | 51791 | 27999 | 16751 | 27999 | 14704 | 656509 | 3.2218 | 1.6095 | 2.654 | 7.4854 | 3.61 | 0.88 | 153 | 2623 | 10 | 48.2274 | 26.7344
5 | Kalchini | 56616 | 8537 | 31469 | 16481 | 56487 | 36265 | 14997 | 36265 | 14281 | 587707 | 1.0388 | 4.0161 | 2.4561 | 7.511 | 3.13 | 0.51 | 10 | 1080 | 5 | 41.672 | 20.7116
6 | Kumargram | 40056 | 16487 | 13480 | 9827 | 39794 | 30148 | 24710 | 29979 | 17586 | 968483 | 3.613 | 2.0682 | 1.9014 | 7.5825 | 2.67 | 2.194 | 128 | 484 | 61 | 35.2126 | 25.2927
7 | Madarihat | 39294 | 7539 | 16324 | 15431 | 39294 | 12817 | 16406 | 12817 | 1515 | 643007 | 1.3213 | 2.112 | 2.2188 | 5.6521 | 3.14 | 0.79 | 12 | 0 | 0 | 55.5546 | 44.0985
8 | Mal | 58540 | 18394 | 20606 | 19540 | 58540 | 17499 | 12570 | 17499 | 2642 | 492646 | 0.70227 | 0.93271 | 1.1181 | 2.753 | 1.03 | 0.048415 | 4 | 181 | 40 | 37.4132 | 15.7326
9 | Matiali | 24986 | 5981 | 12141 | 6675 | 24797 | 13594 | 5950 | 13594 | 7205 | 233192 | 0.89658 | 1.6553 | 0.72452 | 3.2764 | 1.81 | 0.04 | 34 | 524 | 41 | 55.2429 | 24.1021
10 | Maynaguri | 67439 | 49907 | 1053 | 15938 | 66898 | 25346 | 23975 | 25217 | 14713 | 939789 | 2.9902 | 0.03699 | 0.90025 | 3.9275 | 1.72 | 0.09 | 2 | 162 | 16 | 43.7942 | 15.5747
11 | Nagrakata | 26331 | 3949 | 15086 | 7296 | 26331 | 15135 | 6518 | 15135 | 4522 | 255439 | 0.37974 | 1.0963 | 0.55889 | 2.035 | 0.76 | 0.16 | 0 | 53 | 0 | 37.3472 | 13.4454
12 | Rajganj | 51625 | 29922 | 2727 | 18976 | 51625 | 14893 | 7837 | 14893 | 9833 | 307153 | 1.3318 | 0.35876 | 1.7392 | 3.4298 | 1.04 | 0.42 | 2 | 828 | 124 | 30.3228 | 23.0293
13 | Sadar | 60195 | 37038 | 4460 | 18697 | 60195 | 27214 | 7827 | 26375 | 20711 | 308719 | 2.3924 | 0.13013 | 1.0837 | 3.6062 | 1.33 | 0.39 | 6 | 508 | 78 | 36.8812 | 13.6727
| Total: | 643044 | 278671 | 157721 | 203583 | 639975 | 285535 | 179209 | 284398 | 144815 | 7025685 | 26.8737 | 17.1058 | 19.4327 | 63.4122 | 26.45 | 7.0505 | 394 | 9810 | 482 | 41.7112 | 22.297
District Programme Coordinator
| Falakata Block has Rectified application registered & Cum. No of HH issued job cards | [16 empty] | MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2011-12 Up to the Month of FEBRUARY' 2012
Sl. No. | Name of the Block | Actual O.B. as on 01.04.10 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability (4+5+6+7+8) | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh)
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (9+10+11+12) | Balance |  | Expenditure up to prev. months | expenditure during the month | Balance | Balance | Balance
[13 empty] | Recurring | Non-Recurring
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Alipurduar-I | 23.5 |  |  | 687.8508 |  |  | 711.3508 | 596.45 | 447.7136 | 20.6683 | 115.0304 | 78.8534 | 3.0498 | 665.3153 | 46.0355 | #REF! | 274.4036 | 390.9117 | 61.85 |  | 252.4137
2 | Alipurduar-II | 32.12 |  |  | 664.0061 |  |  | 696.1261 | 692.19 | 476.6393 | 23.0679 | 70.448 | 29.8269 | 8.2011 | 608.1832 | 87.9429 | #REF! | 304.4107 | 303.7725 | 36.8578 |  | 9.4452
3 | Dhupguri | 43.37 |  |  | 3056.3753 |  |  | 3099.7453 | 1970.48 | 1474.4588 | 84.3116 | 1037.8587 | 33.7016 | 17.6824 | 2648.0131 | 451.7322 | 138.1102 | 959.1269 | 1688.8862 | 166.1673 |  | 1798.5665
4 | Falakata | 64.68 |  |  | 1897.6176 |  |  | 1962.2976 | 1313.02 | 1242.3175 | 71.9182 | 446.8846 | 17.2144 | 24.6397 | 1802.9744 | 159.3232 | #REF! | 292.4339 | 1510.5405 | 44.8451 |  | 1482.867
5 | Kalchini | 17.85 |  |  | 1837.8426 |  |  | 1855.6926 | 1173.41 | 1034.8242 | 81.284 | 398.7349 | 46.99 | 13.2954 | 1575.1285 | 280.5642 | #REF! | 214.0691 | 1361.0593 | 90.2812 | 4.3138 | 983.649
6 | Kumargram | 10.19 |  |  | 2087.4942 |  |  | 2097.6842 | 1936.96 | 1123.1687 | 74.6838 | 619.46 | 22.933 | 23.2533 | 1863.4987 | 234.1856 | #REF! | 530.3212 | 1333.1774 | 81.51 |  | 1231.1001
7 | Madarihat | 11.67 |  |  | 1248.8219 |  |  | 1260.4919 | 1286.01 | 734.7744 | 45.5549 | 277.2983 | 12.391 | 25.24 | 1095.2586 | 165.2333 | 130.0003 | 325.6474 | 769.6113 | 84.9085 |  | 552.2431
8 | Mal | 26.38 |  |  | 950.1559 |  |  | 976.5359 | 985.29 | 509.5364 | 44.2449 | 204.378 | 9.585 | 14.6986 | 782.4429 | 194.0931 | 185.0814 | 367.8294 | 414.6134 | 95.95 |  | 381.657
9 | Matiali | 15.07 |  |  | 680.6423 |  |  | 695.7123 | 466.38 | 433.0469 | 27.712 | 92.812 | 5.057 | 5.5491 | 564.1771 | 131.5352 | #REF! | 147.3002 | 416.8769 | 83.8542 |  | 340.8013
10 | Maynaguri | 58.6 |  |  | 1156.9177 |  |  | 1215.5177 | 1879.57 | 632.6851 | 31.4515 | 160.8515 | 20.5447 | 11.3185 | 856.8512 | 358.6665 | 161.0927 | 266.2758 | 590.5755 | 80.1736 |  | 302.117
11 | Nagrakata | 24.69 |  |  | 432.1958 |  |  | 456.8858 | 510.87 | 280.7101 | 16.0334 | 28.9887 | 14.6381 | 7.5716 | 347.9419 | 108.9438 | #REF! | 73.3785 | 274.5635 | 29.6664 |  | 88.0861
12 | Rajganj | 40.06 |  |  | 568.9833 |  |  | 609.0433 | 614.32 | 345.3311 | 16.9543 | 76.3445 | 10.3183 | 7.2097 | 456.1578 | 152.8855 | #REF! | 158.2235 | 297.9343 | 52.4855 |  | 231.9825
13 | Sadar | 41.81 |  |  | 1220.1844 |  |  | 1261.9944 | 613.44 | 734.8865 | 36.4593 | 158.4466 | 28.8723 | 9.6813 | 968.3459 | 293.6484 | 203.7859 | 198.2151 | 770.1308 | 61.025 |  | 545.163
| Total | 409.99 | 0 | 0 | 16489.088 |  | 0 | 16899.078 | 14047.39 | 9470.0925 | 574.344 | 3687.5361 | 330.9255 | 171.3904 | 14234.2885 | 2664.7894 | #REF! | 4111.6353 | 10122.6532 | 969.5746 |  | 8200.0914
1 | Line Deptt. | 171.41 |  |  | 241.93 |  |  | 413.34 |  | 175.93 |  |  |  |  | 175.93 | 237.41 |  | 83.25
2 | District Cell | 155.93 |  |  | 16700 | 1855.55 | 10.3673 | 18721.8473 |  |  |  |  | 52.7239 | 22.3848 | 75.1088 |  |  | 29.3346
| Total | 327.34 | 0 | 0 | 16700 | 1855.55 | 10.3673 | 19135.1873 |  | 175.93 | 0 | 0 | 52.7239 | 22.3848 | 251.0388 |  |  | 326.1475
| G.T. | 737.33 | 0 | 0 | 16700 | 1855.55 | 10.3673 | 19303.2473 |  | 9646.0225 | 574.344 | 3687.5361 | 383.6494 | 193.7753 | 14485.3273 | 4817.92 | 5238.4338 | 4437.7828 |  | 9246.8935
** SOME OF THE BLOCKS HAVE REFLECTED THE MANDAYS IN THE LAST FINANCIAL YEAR ,NOW THE DUE PAYMENT IS BEING CLEARING AND SHOWN IN THE REPORTS ADNORMAL HIKE IN AVG. WAGE PAYMENT .
DPC
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri
Note on K25: FEB' 12
Note on N26: FEB' 12
Note on O26: FEB' 12

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2011-12 Up to the Month of FEBRUARY' 2012 | [19 empty] | Physical Performance Under NREGA During the year 2011-12 Up to the Month of FEBRUARY' 2012 | [17 empty] | Physical Performance Under NREGA During the year 2011-12 Up to the Month of FEBRUARY' 2012
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 891 | 936374.1694 | 1048.4249 | 869 | 362823.7342 | 521.6894 | 749 | 303274.1526 | 357.6922 | 212 | 868.4504 | 93.6928 | 549 | 735.8831 | 738.1576 | 342 | 338.474 | 384.3161 | 135 | 92.6582 | 108.4972 | 49 | 0.35476 | 3.0934 | 408 | 129724.1652 | 135.2066 | 221 | 83035.2476 | 105.0112 | 1703 | 19788.194 | 1240.9108 | 1245 | 5544.9436 | 670.7186 | 689 | 1806.3848 | 2148.4762 | 519 | 1224.2462 | 1383.4084 | 1520 | 2072.9132 | 2891.4251 | 1346 | 910.5334 | 1974.6676 | 9 | 1.4351 | 7.4604 | 36 | 1816.74 | 95.054 | 6653 | 8676.251 | 4839 | 5231.6516 | 13907.9026 | 13907.9026 | 5e-06
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2011-12 Up to the Month of FEBRUARY 2012
[6 empty] | 14 | 237 | 1 | 5 | 0 | 0
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 3111 | 317 | 14 | 8 | 264 | 34 | 0 | 10 | 0 | 0
2 | Alipurduar-II | 334 | 149 | 9 | 13 | 429 | 44 | 1 | 4 | 8 | 5
3 | Dhupguri | 3714.9376 | 14859.7506 | 17 | 15 | 0 | 0 | 0 | 0 | 0 | 0
4 | Falakata | 2152 | 3680 | 11 | 13 | 14 | 237 | 1 | 5 | 0 | 0
5 | Kalchini | 1736 | 342 | 3 | 19 | 0 | 13.1 | 7 | 76 | 0 | 5
6 | Kumargram | 3806 | 457 | 4 | 18 | 14 | 7 | 10 | 1 | 0 | 0
7 | Madarihat-Birpara | 3806.5238 | 1960.9365 | 7 | 13 | 191 | 249 | 0 | 10 | 2 | 7
8 | Mal | 0 | 81 | 12 | 12 | 0 | 25 | 0 | 12 | 1 | 0
9 | Matiali | 0 | 87 | 5 | 5 | 0 | 12 | 2 | 3 | 0 | 0
10 | Maynaguri | 0 | 1245 | 20 | 12 | 0 | 15 | 0 | 16 | 7 | 6
11 | Nagrakata | 4754 | 626 | 0 | 10 | 199 | 140 | 0 | 5 | 0 | 2
12 | Rajganj | 8041 | 556 | 3 | 21 | 116 | 36 | 0 | 0 | 1 | 0
13 | Sadar | 0 | 333 | 14 | 14 | 0 | 30 | 0 | 0 | 0 | 5
| Total | 31455.4614 | 24693.6871 | 119 | 173 | 1227 | 842.1 | 21 | 142 | 19 | 30
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of FEBRUARY' 2012)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 12 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of FEBRUARY' 2012)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
FEBRUARY 2011
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10
1 | Alipurduar-I | 3802 | 0 | 66.24 | 35944 | 320 | 381.4736
2 | Alipurduar-II | 7895 | 36 | 63.6619 | 26404 | 45 | 412.9774
3 | Dhupguri | 920 | 752 | 183.25 | 8751 | 3637 | 1291.2088
4 | Falakata | 15696 | 612 | 372.6685 | 44370 | 59 | 869.649
5 | Kalchini | 18953 | 345 | 400.4268 | 34750 | 3086 | 634.3974
6 | Kumargram | 4445 | 1606 | 214.76 | 30300 | 5707 | 908.4087
7 | Madarihat | 4022 | 53 | 49.51 | 34827 | 4300 | 685.2644
8 | Mal | 2380 | 11 | 24.3963 | 32582 | 1389 | 485.1401
9 | Matiali | 0 | 0 | 0 | 51609 | 368 | 433.0469
10 | Maynaguri | 3583 | 0 | 29.5015 | 44790 | 0 | 603.1836
11 | Nagrakata | 3213 | 0 | 44.2912 | 28403 | 0 | 236.4189
12 | Rajganj | 2906 | 0 | 13.2704 | 45609 | 4733 | 332.0607
13 | Sadar | 2740 | 0 | 74.8212 | 38656 | 0 | 660.0653
Total |  | 70555 | 3415 | 1536.7977 | 456995 | 23644 | 7933.2949
Rajganj Block has rectified report.