## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of JULY' 2011 (for the financial year 2011-12)
MPR- Part-I
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Register | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C | bar: 9
1 | 2 |  | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Alipurduar-I | 40448 | 21046 | 8586 | 10816 | 40448 | 861 |  | 861 | 372 |  | 0.8563 | 0.28947 | 0.16919 | 1.315 | 0.47769 | 0.03464 | 0 | 289 | 102
2 | Alipurduar-II | 44575 | 19699 | 9478 | 13086 | 42263 | 2264 |  | 2264 | 0 |  | 0.11141 | 0.05516 | 0.11163 | 0.2782 | 0.10895 | 0.07591 | 0 | 50 | 0
3 | Dhupguri | 80508 | 39105 | 16764 | 22691 | 78560 | 11143 |  | 11143 | 7025 |  | 2.0692 | 0.59068 | 0.97081 | 3.6307 | 1.2803 | 0.084856 | 0 | 498 | 11
4 | Falakata | 50312 | 22510 | 9773 | 18029 | 50312 | 2331 |  | 2331 | 1596 |  | 0.02426 | 0.03873 | 0.02451 | 0.0875 | 0.03525 | 0.0057117 | 0 | 680 | 3
5 | Kalchini | 56348 | 8386 | 31129 | 16746 | 56261 | 12066 |  | 12066 | 6546 |  | 0.40488 | 1.2142 | 0.62156 | 2.2406 | 0.75034 | 0.075806 | 0 | 0 | 0
6 | Kumargram | 39869 | 15435 | 13492 | 10021 | 38948 | 8725 |  | 8185 | 105 |  | 1.3523 | 0.73163 | 0.66911 | 2.7531 | 1.2405 | 0.095829 | 0 | 272 | 26
7 | Madarihat-Birpara | 39294 | 7539 | 16324 | 15431 | 39294 | 2001 |  | 670 | 0 |  | 0.01392 | 0.09283 | 0.00929 | 0.11604 | 0.07891 | 0.00977 | 0 | 0 | 0
8 | Mal | 58540 | 18394 | 20606 | 19540 | 58540 | 5292 |  | 5292 | 1639 |  | 0.42251 | 0.22779 | 0.37553 | 1.0258 | 0.42733 | 0.048415 | 0 | 181 | 40
9 | Matiali | 24986 | 5981 | 12141 | 6675 | 24797 | 6320 |  | 6320 | 2585 |  | 0.23523 | 0.52793 | 0.18753 | 0.95069 | 0.47371 | 0.022857 | 0 | 280 | 41
10 | Maynaguri | 67180 | 49882 | 1048 | 15956 | 66886 | 323 |  | 323 | 0 |  | 0.66663 | 0.01908 | 0.15227 | 0.83798 | 0.29244 | 0.025987 | 0 | 21 | 1
11 | Nagrakata | 26331 | 3949 | 15086 | 7296 | 26331 | 857 |  | 157 | 0 |  | 0.07277 | 0.23764 | 0.14157 | 0.45198 | 0.26822 | 0.04389 | 0 | 4 | 0
12 | Rajganj | 51625 | 29922 | 2727 | 18976 | 51625 | 3939 |  | 3939 | 101 |  | 0.5188 | 0.12707 | 0.67834 | 1.3242 | 0.51706 | 0.14146 | 0 | 72 | 2
13 | Sadar | 60195 | 37038 | 4460 | 18697 | 60195 | 1126 |  | 925 | 0 |  | 0.009953 | 0.00369 | 0.00153 | 0.015173 | 0.00395 | 0.00736 | 0 | 0 | 0
| Total: | 640211 | 278886 | 161614 | 193960 | 634460 | 57248 | 0 | 54476 | 19969 | 0 | 6.7582 | 4.1559 | 4.1129 | 15.027 | 5.9546 | 0.67249 | 0 | 2347 | 226
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri
As on 30/06/2011
Employment provided to HHS: 37177 nos.
Persondays [in lac]: Total: 9.59,
SCs : 4.56 [47.55%], STs : 2.44 [25.44%],
Women : 3.36 [35.04%], Others : 2.60 [27.11%]
Total works taken up : 3929 nos.
Works completed : 1121 nos.
Works in progress : 2808 nos.

## Part-II
Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2010-11 Up to the Month of JULY' 2011
Jalpaiguri District | [14 empty] | (Rs. in lakh)
Sl. No. | Name of the Block | Actual O.B. as on 01.04.10 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability (4+5+6+7+8) | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (9+10+11+12) | Balance |  | Expenditure up to prev. months | expenditure during the month | Balance | Balance | Balance
[13 empty] | Recurring | Non-Recurring
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Alipurduar-I | -0.49758 |  |  | 278.7094 |  |  | 278.2119 |  | 182.002 | 4.6819 | 11.7156 | 15.7265 | 1.0406 | 215.1666 | 63.0453 | 138.4088 | 274.4036 | -59.2371 | 61.85 |  | -197.7351 | -36.3384
2 | Alipurduar-II | 27.8954 |  |  | 185.9197 |  |  | 213.8152 |  | 137.7451 | 3.6406 | 2.0958 | 4.2956 | 0.1051 | 147.8823 | 65.9329 | 495.1297 | 304.4107 | -156.5284 | 36.8578 |  | -450.8557 | -135.6529
3 | Dhupguri | 24.998 |  |  | 1107.6739 |  |  | 1132.6719 |  | 622.8771 | 38.2521 | 151.7638 | 32.7138 | 6.5922 | 852.1989 | 280.473 | 171.5579 | 959.1269 | -106.928 | 166.1673 |  | 2.7523 | -20.8821
4 | Falakata | 68.106 |  |  | 511.8116 |  |  | 579.9176 |  | 272.7537 | 9.2843 | 14.6609 | 4.4809 | 4.3826 | 305.5623 | 274.3553 | 3117.185 | 292.4339 | 13.1283 | 44.8451 |  | -14.5451 | -47.3563
5 | Kalchini | 23.1928 |  |  | 522.6128 |  |  | 545.8056 |  | 228.8157 | 18.9151 | 102.5181 | 21.9148 | 4.09 | 376.2536 | 169.552 | 102.1216 | 214.0691 | 162.1845 | 90.2812 | 4.3138 | -215.2259 | -56.601
6 | Kumargram | -8.5519 |  |  | 633.9069 |  |  | 625.355 |  | 398.9181 | 21.8106 | 90.9523 | 6.5586 | 5.5854 | 523.825 | 101.5299 | 144.8983 | 530.3212 | -6.4962 | 81.51 |  | -108.5735 | -85.3283
7 | Madarihat-Birpara | 8.2932 |  |  | 466.4478 |  |  | 474.741 |  | 321.2786 | 10.9985 | 27.5402 | 5.328 | 5.335 | 370.4803 | 104.2606 | 2768.6887 | 325.6474 | 44.833 | 84.9085 |  | -172.5352 | -104.3845
8 | Mal | 48.9421 |  |  | 306.3154 |  |  | 355.2576 |  | 226.8843 | 7.4274 | 26.1964 | 2.0832 | 2.9836 | 265.5749 | 89.6827 | 221.1714 | 367.8294 | -102.2546 | 95.95 |  | -135.2111 | -69.166
9 | Matiali | 20.8149 |  |  | 222.6443 |  |  | 243.4592 |  | 124.3679 | 7.9642 | 26.1705 | 1.5108 | 1.6951 | 161.7085 | 81.7507 | #REF! | 147.3002 | 14.4083 | 83.8542 |  | -61.6673 | #REF!
10 | Maynaguri | 182.6292 |  |  | 210.2286 |  |  | 392.8579 |  | 131.8686 | 4.8565 | 23.9388 | 7.053 | 2.901 | 170.618 | 222.2399 | 157.3648 | 266.2758 | -95.6578 | 80.1736 |  | -384.1163 | -123.1603
11 | Nagrakata | 19.2437 |  |  | 87.7594 |  |  | 107.0031 |  | 57.9874 | 2.3989 | 7.9618 | 4.3676 | 4.2622 | 76.9779 | 30.0253 | 128.2964 | 73.3785 | 3.5994 | 29.6664 |  | -182.878 | -27.7551
12 | Rajganj | 50.4265 |  |  | 213.6813 |  |  | 264.1078 |  | 117.6692 | 2.7202 | 18.4505 | 4.4108 | 1.393 | 144.6437 | 119.4641 | 88.8596 | 158.2235 | -13.5798 | 52.4855 |  | -79.5315 | -22.5396
13 | Sadar | -32.9013 |  |  | 310.6323 |  |  | 277.731 |  | 262.2312 | 5.9937 | 42.2164 | 19.1974 | 4.1818 | 333.8205 | -56.0895 | 17282.7516 | 198.2151 | 135.6053 | 61.025 |  | -89.3624 | -2.3033
| Total | 432.5912 | 0 | 0 | 5058.3434 |  | 0 | 5490.9346 | 0 | 3085.3989 | 138.944 | 546.1811 | 129.641 | 44.5474 | 3944.7124 | 1546.2222 | #REF! | 4111.6353 | -166.9229 | 969.5746 |  | -2089.4847 | -717.2382
1 | Line Deptt. | 181.1268 |  |  | 67.4132 |  |  | 248.54 |  | 50.03 |  |  |  |  | 50.03 | 198.51 |  | 83.25
2 | District Cell | 134.363 |  |  | 10200 | 244.44 | 10.3673 | 10589.1703 |  |  |  |  | 16.2211 | 10.814 | 27.0351 |  |  | 29.3346
| Total | 315.4898 | 0 | 0 | 10200 | 244.44 | 10.3673 | 10837.7103 |  | 50.03 | 0 | 0 | 16.2211 | 10.814 | 77.0651 |  |  | 104.1003
| G.T. | 748.081 | 0 | 0 | 10200 | 244.44 | 10.3673 | 11202.8883 | 0 | 3135.4289 | 138.944 | 546.1811 | 145.8621 | 55.3615 | 4021.7775 | 7181.1108 | 5238.4338 | 4215.7355 |  | -1216.6563
[17 empty] | -69.3639 | 32.7577
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri
Note on K27: June' 11
Note on N28: JULY' 11
Note on O28: JULY' 11

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2010-11 Up to the Month of JULY' 2011 | [19 empty] | Physical Performance Under NREGA During the year 2010-11 Up to the Month of JULY' 2011 | [17 empty] | Physical Performance Under NREGA During the year 2010-11 Up to the Month of JULY' 2011
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 363 | 419459.5068 | 445.1493 | 338 | 463609.9291 | 210.1231 | 113 | 84692.0128 | 46.0197 | 257 | 79.35 | 70.7537 | 89 | 112.3034 | 130.4982 | 247 | 56.9241 | 126.4261 | 85 | 106.4421 | 41.6615 | 30 | 7.7 | 16.9968 | 61 | 89418.2 | 58.3255 | 447 | 134494.881 | 56.9884 | 459 | 581.3318 | 403.2012 | 522 | 210.6496 | 204.8261 | 220 | 279.8649 | 366.9468 | 447 | 1336.577 | 363.7101 | 439 | 588.8125 | 659.4053 | 707 | 1218.2302 | 619.522 | 0 | 0 | 0 | 0 | 0 | 0 | 1829 | 2151.2076 | 2995 | 1669.3464 | 3820.5539 | 3820.5539 | 0
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of June' 2011)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | - | - | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of June' 2011)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | - | - | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri