## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
part I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of Dec 2012 (for the financial year 2012-13)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 | 3 | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Alipurduar-I | 40448 | 21046 | 8586 | 10816 | 40448 | 11327 | 8738 | 11327 | 2626 | 264830 | 1.4905 | 0.84271 | 0.49716 | 2.864 | 1.402 | 0.066895 | 0 | 687 | 11 | 48.9512 | 25.285 | 48.9512
2 | Alipurduar-II | 45348 | 17364 | 5206 | 22778 | 45348 | 18492 | 10139 | 18492 | 1912 | 307339 | 1.8875 | 0.81859 | 1.316 | 4.0221 | 1.3557 | 1.8666 | 61 | 576 | 113 | 33.7052 | 21.7505 | 33.7052
3 | Dhupguri | 78560 | 39105 | 16764 | 22691 | 78560 | 41313 | 22651 | 35201 | 32361 | 914397 | 3.9256 | 1.9019 | 1.9893 | 7.8168 | 2.6227 | 0.10854 | 0 | 78 | 10 | 33.5528 | 22.2061 | 33.5528
4 | Falakata | 54234 | 24544 | 10257 | 19433 | 54234 | 17403 | 19230 | 19297 | 2594 | 572990 | 1.0966 | 0.79594 | 0.88128 | 2.7738 | 1.4508 | 0.39502 | 15 | 707 | 24 | 52.3046 | 14.3742 | 52.3046
5 | Kalchini | 61233 | 8929 | 31840 | 19633 | 60402 | 27385 | 17215 | 27385 | 1352 | 521894 | 0.95315 | 3.2756 | 1.9134 | 6.1421 | 2.8081 | 0.17191 | 115 | 1289 | 27 | 45.7193 | 22.4287 | 45.7193
6 | Kumargram | 41075 | 16920 | 13844 | 10028 | 41075 | 25643 | 28368 | 24242 | 6925 | 860026 | 2.0124 | 0.99041 | 6.9552 | 9.958 | 2.3226 | 0.25 | 7 | 335 | 44 | 23.324 | 41.0773 | 23.324
7 | Madarihat | 39710 | 6947 | 16704 | 16059 | 39710 | 14904 | 18836 | 14904 | 1786 | 570997 | 0.4633 | 0.73703 | 0.78077 | 1.9811 | 1.0979 | 0.31423 | 2 | 0 | 0 | #REF! | #REF! | #REF!
8 | Mal | 58666 | 18380 | 21485 | 18801 | 58666 | 16702 | 14431 | 16702 | 3439 | 437476 | 0.95033 | 0.95668 | 1.1708 | 3.0778 | 1.2387 | 0 | 1 | 274 | 26 | 62.0962 | 21.2104 | 62.0962
9 | Matiali | 23995 | 5863 | 12031 | 6066 | 23960 | 15128 | 6832 | 15128 | 956 | 207079 | 0.95186 | 1.4415 | 0.63233 | 3.0257 | 1.4893 | 0.00954 | 7 | 193 | 88 | 49.2217 | 20.0007 | 49.2217
10 | Maynaguri | 68606 | 48594 | 1004 | 19605 | 67750 | 13505 | 18134 | 24343 | 9032 | 846904 | 1.7204 | 0.05408 | 1.2773 | 3.0518 | 0.25551 | 0.031336 | 0 | 378 | 5 | 8.3723 | 12.5366 | 8.3723
11 | Nagrakata | 26423 | 4066 | 15342 | 6959 | 26367 | 13903 | 7482 | 13903 | 6142 | 642731 | 0.53301 | 1.4887 | 0.71722 | 2.739 | 1.0841 | 0.29899 | 1 | 282 | 0 | 39.5806 | 19.7006 | 39.5806
12 | Rajganj | 50966 | 30252 | 2773 | 17885 | 50910 | 13590 | 9002 | 13590 | 5341 | 272761 | 0.89768 | 0.02505 | 0.79666 | 1.7194 | 0.78797 | 0.53746 | 0 | 535 | 11 | 45.8285 | 12.6519 | 45.8285
13 | Sadar | 58406 | 34826 | 3976 | 19604 | 58406 | 22814 | 8986 | 22814 | 7911 | 272373 | 1.999 | 0.16319 | 1.0194 | 3.1816 | 0.89759 | 0.33161 | 4 | 391 | 9 | 28.2118 | 13.9459 | 28.2118
| Total: | 647670 | 276836 | 159812 | 210358 | 645836 | 252109 | 190044 | 257328 | 82377 | 6691797 | 18.8814 | 13.4914 | 19.9467 | 52.3531 | 18.813 | 4.3821 | 213 | 5725 | 368 | 35.9348 | 20.3449 | 35.9348
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2012-13 Up to the Month of Dec ' 2012
Sl. No. | Name of the Block | Actual O.B. as on 01.04.12 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh)
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (10+11+12+13+14)
[13 empty] | Recurring | Non-Recurring |  | 4.32 |  |  |  |  | avg. gp
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | [7 empty] | WAGE% | PER LABOUR
1 | Alipurduar-I | 20.02 |  |  | 749.3622 |  | 2.7648 | 772.147 | 529.6375 | 417.648 | 34.9607 | 236.3854 | 27.9838 | 7.5934 | 724.5713 | 6.5948 | 28.4896 | 446.1375 | 395.2494 | 11 | 65.8701 | 65.8701 | 57.6407 | 145.8253 | Alipurduar-I | 506.4504 | 688.994
2 | Alipurduar-II | 52.31 |  |  | 1301.0579 |  | 4.2923 | 1357.6602 | 614.6875 | 671.7339 | 56.4229 | 491.8938 | 25.061 | 11.7228 | 1256.8344 | 11.4393 | 0 | 671.7339 | 556.075 | 11 | 114.2577 | 114.2577 | 53.4465 | 167.0103 | Alipurduar-II | 704.6012
3 | Dhupguri | 101.11 |  |  | 1795.8568 |  | 3.8608 | 1900.8276 | 1757.983 | 1171.7414 | 69.8626 | 417.0859 | 21.2507 | 18.0621 | 1698.0028 | 15.4547 | 101.9204 | 1273.6619 | 946.3318 | 16 | 106.1252 | 154.3639 | 69.007 | 149.9012 | Dhupguri | 831.2044
4 | Falakata | 40.2 |  |  | 2171.0395 |  | 6.598 | 2217.8374 | 1165.9625 | 1421.2784 | 114.6532 | 497.6904 | 18.3403 | 15.1105 | 2067.0729 | 18.8138 | 215.2165 | 1636.4949 | 1457.4699 | 12 | 172.2561 | 187.9157 | 68.758 | 512.3958 | Falakata | 1512.1343
5 | Kalchini | 58.34 |  |  | 1705.9993 |  | 3.7726 | 1768.1119 | 1043.7875 | 1064.2666 | 116.9038 | 379.8904 | 26.2621 | 18.485 | 1605.808 | 14.6155 | 225.8779 | 1290.1446 | 1030.0591 | 11 | 145.9825 | 145.9825 | 66.2761 | 173.2743 | Kalchini | 866.6745
6 | Kumargram | 30.75 |  |  | 1450.6783 |  | 4.3088 | 1485.7372 | 1720.05 | 788.2077 | 82.9528 | 547.5121 | 23.5552 | 40.1651 | 1482.3928 | 13.4922 | 253.8405 | 1042.0482 | 853.5048 | 11 | 134.763 | 134.763 | 53.1713 | 79.1535 | Kumargram | 952.4868
7 | Madarihat | 8.22 |  |  | 778.5832 |  | 3.099 | 789.9022 | 1141.9875 | 554.6151 | 49.3725 | 91.5489 | 9.302 | 17.4114 | 722.25 | 6.5737 | 96.0778 | 650.6929 | 527.0331 | 10 | 72.225 | 65.6591 | #REF! | #REF! | Madarihat-Birpara | 466.6014
8 | Mal | 48.13 |  |  | 904.6099 |  | 2.3221 | 955.062 | 877.4375 | 477.3659 | 47.1448 | 260.285 | 20.3762 | 12.0814 | 817.2533 | 7.4384 | 100.3603 | 577.7262 | 394.9049 | 12 | 68.1044 | 74.2958 | 58.411 | 155.0987 | Malbazar | 402.7251
9 | Matiali | 17.93 |  |  | 575.4169 |  | 1.6897 | 595.0367 | 414.15 | 419.0532 | 34.2037 | 65.0604 | 10.6851 | 8.1038 | 537.1063 | 4.8886 | 32.1358 | 451.1891 | 329.2062 | 5 | 107.4213 | 48.8278 | #REF! | #REF! | Matiali | 230.7365
10 | Maynaguri | 81.67 |  |  | 965.4001 |  | 3.6106 | 1050.6806 | 1810.4333 | 453.4016 | 41.2641 | 276.4656 | 8.817 | 7.4602 | 787.4084 | 7.1667 | 53.3087 | 506.7103 | 421.4004 | 16 | 49.213 | 71.5826 | 57.5815 | 148.5691 | Maynaguri | 677.9344
11 | Nagrakata | 18.16 |  |  | 523.0415 |  | 1.4547 | 542.6562 | 453.675 | 374.5608 | 31.0087 | 104.0612 | 1.8885 | 3.2717 | 514.791 | 4.6855 | 22.9051 | 397.4659 | 284.0694 | 5 | 102.9582 | 46.7992 | #REF! | #REF! | Nagrakata | 243.0925
12 | Rajganj | 15.1 |  |  | 462.25 |  | 3.2464 | 480.5964 | 547.6875 | 236.6604 | 24.8741 | 106.7931 | 30.4242 | 4.2497 | 403.0015 | 3.668 | 26.2875 | 262.9478 | 217.4445 | 12 | 33.5835 | 36.6365 | 58.7244 | 137.6421 | Rajganj | 282.2
13 | Sadar | 73.46 |  |  | 1066.236 |  | 3.502 | 1143.198 | 539.875 | 660.3491 | 61.3688 | 282.3401 | 20.7386 | 10.9748 | 1035.7714 | 9.4272 | 44.1709 | 704.5201 | 551.7063 | 14 | 73.9837 | 94.161 | 63.7543 | 207.5519 | Sadar | 641.197
| Total | 565.4 | 0 | 0 | 14449.5316 |  | 44.5219 | 15059.4536 | 12617.3538 | 8710.8823 | 764.9927 | 3757.0122 | 244.6847 | 174.692 | 13652.264 |  |  |  |  | 146 | 93.5087 | 1241.1149 | 63.8054
1 | Line Deptt. | 120.21 |  |  | 258.7275 |  |  | 378.9375 |  | 151.55 | 0 | 0 | 0 | 0 | 151.55 |  |  |  |  | 13384.4373 |  | 93.5087
2 | District Cell | 670.31 |  |  | 13084 | 1000 | 47.19 | 14801.5 |  | 0 | 0 | 0 | 47.4 | 5.18 | 52.58
| Total | 790.52 | 0 | 0 | 13084 | 1000 | 47.19 | 15180.4375 |  | 151.55 | 0 | 0 | 47.4 | 5.18 | 204.13
| G.T. | 1355.92 | 0 | 0 | 13084 | 1000 | 91.7119 | 15531.6319 | 12617.3538 | 8862.4323 | 764.9927 | 3757.0122 | 292.0847 | 179.872 | 13856.394
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2012-13 Up to the Month of Dec 2012 | [19 empty] | Physical Performance Under NREGA During the year 2012-13 Up to the Month of Dec 2012 | [17 empty] | Physical Performance Under NREGA During the year 2012-13 Up to the Month of Dec 2012
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 1213 | 740265.1933 | 1329.0938 | 440 | 181659.1583 | 272.5594 | 151 | 93.2178 | 67.3361 | 320 | 1260.6442 | 110.3424 | 481 | 1422.5886 | 730.6053 | 379 | 195.2434 | 573.4032 | 312 | 185.7447 | 179.8269 | 198 | 140.6069 | 162.5255 | 191 | 197277.2676 | 236.8074 | 189 | 67276.3235 | 94.2052 | 1603 | 8517.6589 | 1451.3903 | 709 | 709.7025 | 335.5419 | 577 | 1890.6002 | 1569.7495 | 756 | 719.8551 | 1430.3639 | 1519 | 1149.7312 | 2844.0656 | 1162 | 558.7483 | 1675.4576 | 3 | 0 | 13.394 | 70 | 4.25 | 307.7652 | 6050 | 8422.269 | 4223 | 4962.1643
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2012-13 Up to the Month of Dec 2012
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 2422 | 0 | 3 | 19 | 381 | 2 | 0 | 10 | 0 | 0
2 | Alipurduar-II | 806 | 0 | 4 | 0 | 786 | 0 | 1 | 0 | 8 | 0
3 | Dhupguri | 2952.2334 | 11808.9335 | 839 | 9 | 0 | 0.1 | 0 | 1 | 12 | 12
4 | Falakata | 135 | 1732 | 1 | 11 | 0 | 435 | 3 | 2 | 0 | 2
5 | Kalchini | 406 | 126 | 17 | 5 | 0 | 12 | 18 | 57 | 0 | 0
6 | Kumargram | 2129 | 3015 | 0 | 10 | 48 | 11.16 | 10 | 1 | 0 | 0
7 | Madarihat-Birpara | 2878 | 2021 | 13 | 7 | 403 | 95 | 0 | 10 | 0 | 0
8 | Mal | 0 | 207 | 0 | 0 | 468 | 47 | 0 | 0 | 0 | 0
9 | Matiali | 0 | 312 | 0 | 5 | 0 | 35 | 0 | 5 | 1 | 1
10 | Maynaguri | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
11 | Nagrakata | 4117 | 272 | 5 | 5 | 205 | 96 | 5 | 0 | 0 | 4
12 | Rajganj | 14982 | 1247 | 0 | 12 | 140 | 72 |  |  | 0 | 0 | report collected from sudip da muster roll verification and inspection
13 | Sadar | 0 | 3504 | 8 | 6 | 12 | 16 | 0 | 0 | 2 | 7
| Total | 30830.2334 | 24248.9335 | 895 | 95 | 2450 | 829.26 | 46 | 96 | 34 | 38
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of Dec 2012)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 11 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of Dec 2012)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
Dec 2012
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
1 | Alipurduar-I | 5902 | 0 | 41.0605 | 39269 | 320 | 376.5875 | 417.648 | 417.648 | 0
2 | Alipurduar-II | 7895 | 36 | 82.1799 | 26404 | 45 | 589.5541 | 671.7339 | 671.7339 | 0
3 | Dhupguri | 1050 | 910 | 589.23 | 8801 | 3959 | 582.51 | 1171.74 | 1171.7414 | -0.00143
4 | Falakata | 22510 | 92 | 560.0296 | 33684 | 579 | 861.2488 | 1421.2784 | 1421.2784 | 0
5 | Kalchini | 19315 | 345 | 358.9155 | 36815 | 3086 | 705.3511 | 1064.2666 | 1064.2666 | 0
6 | Kumargram | 4791 | 1607 | 148.9609 | 30546 | 5853 | 639.2423 | 788.2032 | 788.2077 | -0.00452
7 | Madarihat | 4563 | 53 | 45.8191 | 36633 | 4300 | 508.7961 | 554.6151 | 554.6151 | 0
8 | Mal | 2380 | 11 | 0 | 32582 | 1389 | 477.3659 | 477.3659 | 477.3659 | 0
9 | Matiali | 0 | 0 | 0 | 52395 | 501 | 419.0532 | 419.0532 | 419.0532 | 0
10 | Maynaguri | 7679 | 0 | 78.2541 | 48857 | 0 | 375.1475 | 453.4016 | 453.4016 | 0
11 | Nagrakata | 3061 | 0 | 48.5341 | 28403 | 0 | 326.0267 | 374.5608 | 374.5608 | 0
12 | Rajganj | 2906 | 0 | 13.5679 | 45782 | 4733 | 223.0881 | 236.656 | 236.6604 | -0.00442
13 | Sadar | 2796 | 0 | 54.8026 | 37143 | 0 | 605.5504 | 660.353 | 660.3491 | 0.00384
| Line dep. |  |  | 45.258 |  |  | 106.292 | 151.55 | 151.55 | 0
Total |  | 84848 | 3054 | 2066.6122 | 457314 | 24765 | 6795.8236 | 8862.4358 | 8862.4323 | 0.00347