## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
part I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of Jan 2013 (for the financial year 2012-13)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 | 3 | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Alipurduar-I | 40448 | 21046 | 8586 | 10816 | 40448 | 14459 | 9125 | 14459 | 2789 | 321261 | 1.6804 | 0.91814 | 0.52896 | 3.1615 | 1.47 | 0.068235 | 0 | 782 | 11 | 46.496 | 21.8652 | 46.496
2 | Alipurduar-II | 45348 | 17364 | 5206 | 22778 | 45348 | 22524 | 10587 | 22524 | 2072 | 372865 | 2.0915 | 1.0074 | 1.7042 | 4.803 | 1.6793 | 2.2639 | 87 | 576 | 113 | 34.9634 | 21.3239 | 34.9634
3 | Dhupguri | 78560 | 39105 | 16764 | 22691 | 78560 | 43951 | 23707 | 40740 | 38308 | 1064767 | 4.1976 | 1.9168 | 2.138 | 8.2524 | 2.7955 | 0.10854 | 0 | 52 | 10 | 33.8753 | 20.2563 | 33.8753
4 | Falakata | 52369 | 24258 | 10148 | 17963 | 52369 | 21586 | 20084 | 21586 | 4921 | 707291 | 1.2772 | 0.86083 | 1.0472 | 3.1853 | 1.5307 | 0.37487 | 25 | 1124 | 24 | 48.055 | 14.7564 | 48.055
5 | Kalchini | 61233 | 8934 | 31849 | 19633 | 60416 | 29231 | 17992 | 29231 | 8514 | 633168 | 1.0051 | 3.5315 | 2.1257 | 6.6623 | 3.0675 | 0.20786 | 156 | 1499 | 27 | 46.0434 | 22.7918 | 46.0434
6 | Kumargram | 41126 | 16921 | 13846 | 10029 | 41078 | 28109 | 29629 | 26809 | 10634 | 1043393 | 3.6299 | 1.7252 | 6.9551 | 12.3102 | 2.1353 | 0.25 | 15 | 335 | 44 | 17.3455 | 45.9181 | 17.3455
7 | Madarihat | 39545 | 4659 | 11568 | 23318 | 39545 | 19686 | 19673 | 19686 | 4782 | 692741 | 0.5845 | 0.97143 | 0.96288 | 2.5188 | 1.4119 | 0.39143 | 16 | 39 | 11 | #REF! | #REF! | #REF!
8 | Mal | 58666 | 18380 | 21485 | 18801 | 58666 | 19046 | 15071 | 16702 | 3439 | 530753 | 1.1766 | 1.1365 | 1.2931 | 3.6062 | 1.4345 | 0 | 3 | 436 | 26 | 62.0962 | 21.2104 | 62.0962
9 | Matiali | 24084 | 5875 | 12088 | 6086 | 24049 | 15910 | 7136 | 15910 | 10055 | 251231 | 1.0368 | 1.5523 | 0.72009 | 3.3092 | 1.6293 | 0.00954 | 7 | 239 | 56 | 49.2347 | 20.7993 | 49.2347
10 | Maynaguri | 68959 | 47486 | 859 | 19870 | 68215 | 17790 | 18906 | 17790 | 11289 | 1012745 | 1.99 | 0.04388 | 0.61817 | 2.6521 | 1.1037 | 0.082535 | 0 | 1099 | 89 | 41.6156 | 14.9077 | 41.6156
11 | Nagrakata | 26423 | 4066 | 15342 | 6959 | 26367 | 16175 | 7817 | 16175 | 4140 | 275197 | 0.5517 | 1.4964 | 0.72696 | 2.775 | 1.098 | 0.33354 | 1 | 282 | 0 | 39.5662 | 17.1562 | 39.5662
12 | Rajganj | 50966 | 30247 | 2773 | 17885 | 50905 | 14565 | 9397 | 14565 | 6459 | 329293 | 1.0819 | 0.02584 | 0.9416 | 2.0494 | 0.89194 | 0.67092 | 7 | 566 | 16 | 43.5226 | 14.0705 | 43.5226
13 | Sadar | 59179 | 35305 | 4024 | 19850 | 59179 | 28694 | 9385 | 28694 | 8193 | 330448 | 2.7681 | 0.18726 | 1.2902 | 4.2455 | 1.4839 | 0.40857 | 19 | 402 | 11 | 34.9521 | 14.7958 | 34.9521
| Total: | 646906 | 273646 | 154538 | 216679 | 645145 | 291726 | 198509 | 284871 | 115595 | 7565153 | 23.0713 | 15.3734 | 21.0521 | 59.5308 | 21.7315 | 5.1699 | 336 | 7431 | 438 | 36.5047 | 20.8975 | 36.5047
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2012-13 Up to the Month of Jan ' 2013
Sl. No. | Name of the Block | Actual O.B. as on 01.04.12 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh)
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (10+11+12+13+14)
[13 empty] | Recurring | Non-Recurring |  | 4.32 |  |  |  |  | avg. gp
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | [7 empty] | WAGE% | PER LABOUR
1 | Alipurduar-I | 20.02 |  |  | 888.5022 |  | 3.7077 | 912.2299 | 642.6 | 501.39 | 38.0944 | 243.9503 | 32.8136 | 8.0975 | 824.3458 | 7.5029 | 32.4126 | 533.8026 | 395.2494 | 11 | 74.9405 | 74.9405 | 60.8228 | 158.5929 | Alipurduar-I | 506.4504 | 783.4347
2 | Alipurduar-II | 52.31 |  |  | 1492.1828 |  | 4.9206 | 1549.4134 | 736.975 | 846.66 | 62.2663 | 550.4555 | 26.8813 | 12.3136 | 1498.5766 | 13.6395 | 0 | 846.66 | 556.075 | 11 | 136.2342 | 136.2342 | 56.4976 | 176.2773 | Alipurduar-II | 704.6012
3 | Dhupguri | 101.11 |  |  | 2194.8268 |  | 4.9322 | 2300.8691 | 1918.7497 | 1360.88 | 72.2616 | 522.5365 | 26.7102 | 17.961 | 2000.3493 | 18.2065 | 136.602 | 1497.482 | 946.3318 | 16 | 125.0218 | 181.8499 | 68.0321 | 164.9068 | Dhupguri | 831.2044
4 | Falakata | 40.2 |  |  | 2377.0595 |  | 7.0156 | 2424.275 | 1414.5625 | 1593.27 | 120.2089 | 544.3383 | 20.4038 | 16.549 | 2294.77 | 20.8862 | 284.8786 | 1878.1486 | 1457.4699 | 12 | 191.2308 | 208.6155 | 69.4305 | 500.1931 | Falakata | 1512.1343
5 | Kalchini | 58.34 |  |  | 1970.3543 |  | 5.0983 | 2033.7926 | 1266.3625 | 1279.75 | 125.072 | 477.0251 | 28.593 | 21.5904 | 1932.0304 | 17.5847 | 320.1559 | 1599.9059 | 1030.0591 | 11 | 175.6391 | 175.6391 | 66.2386 | 192.0889 | Kalchini | 866.6745
6 | Kumargram | 30.75 |  |  | 1667.3832 |  | 4.9215 | 1703.0547 | 2086.8 | 890.86 | 83.6353 | 566.0841 | 24.9342 | 48.1702 | 1613.6838 | 14.6872 | 306.7604 | 1197.6204 | 853.5048 | 11 | 146.6985 | 146.6985 | 55.2066 | 72.3677 | Kumargram | 952.4868
7 | Madarihat | 8.22 |  |  | 919.0131 |  | 4.3784 | 931.6115 | 1385.4875 | 655.056 | 53.5403 | 101.917 | 10.252 | 20.4514 | 841.2167 | 7.6565 | 134.6367 | 789.6927 | 527.0331 | 10 | 84.1217 | 76.4742 | #REF! | #REF! | Madarihat-Birpara | 466.6014
8 | Mal | 48.13 |  |  | 1076.6099 |  | 3.0574 | 1127.7973 | 1061.525 | 633.24 | 55.135 | 274.0765 | 20.3359 | 12.7523 | 995.5396 | 9.0611 | 133.0818 | 766.3218 | 394.9049 | 12 | 82.9616 | 90.5036 | 63.6077 | 175.599 | Malbazar | 402.7251
9 | Matiali | 17.93 |  |  | 643.8547 |  | 2.0485 | 663.8333 | 502.4625 | 486.31 | 32.2839 | 72.0392 | 11.4455 | 9.0084 | 611.087 | 5.5619 | 42.5846 | 528.8946 | 329.2062 | 5 | 122.2174 | 55.5534 | #REF! | #REF! | Matiali | 230.7365
10 | Maynaguri | 81.67 |  |  | 1165.0401 |  | 4.3729 | 1251.0829 | 2189.3142 | 589.45 | 43.8513 | 305.8757 | 10.4827 | 7.6133 | 957.273 | 8.7128 | 78.9471 | 668.3971 | 421.4004 | 16 | 59.8296 | 87.0248 | 61.576 | 222.2595 | Maynaguri | 677.9344
11 | Nagrakata | 18.16 |  |  | 551.1715 |  | 1.6242 | 570.9557 | 550.3875 | 402.455 | 31.5294 | 111.6448 | 2.4701 | 3.8069 | 551.906 | 5.0233 | 27.9389 | 430.3939 | 284.0694 | 5 | 110.3812 | 50.1733 | #REF! | #REF! | Nagrakata | 243.0925
12 | Rajganj | 15.1 |  |  | 519.5743 |  | 3.4132 | 538.0875 | 661.825 | 253.51 | 27.3729 | 114.2774 | 23.5288 | 4.4491 | 423.1382 | 3.8513 | 33.5552 | 287.0652 | 217.4445 | 12 | 35.2615 | 38.4671 | 59.9119 | 123.7014 | Rajganj | 282.2
13 | Sadar | 73.46 |  |  | 1260.6012 |  | 4.3105 | 1338.3717 | 653.225 | 845.27 | 68.7586 | 305.0207 | 24.273 | 12.1525 | 1255.4748 | 11.4269 | 57.4004 | 902.6704 | 551.7063 | 14 | 89.6768 | 114.1341 | 67.3267 | 199.0969 | Sadar | 641.197
| Total | 565.4 | 0 | 0 | 16726.1737 |  | 53.8008 | 17345.3745 | 15070.2764 | 10338.101 | 814.0098 | 4189.2409 | 263.1241 | 194.9154 | 15799.3913 | 108.215 |  |  |  | 146 | 108.215 | 1436.3083 | 65.4335
1 | Line Deptt. | 120.21 |  |  | 298.7275 |  |  | 418.9375 |  | 158.55 | 0 | 15.26 | 0 | 0 | 173.81 |  |  |  |  | 15515.1617 |  | 108.215
2 | District Cell | 670.31 |  |  | 15632 | 1000 | 47.19 | 17349.5 |  | 0 | 0 | 0 | 51.6015 | 5.7335 | 57.335
| Total | 790.52 | 0 | 0 | 15632 | 1000 | 47.19 | 17768.4375 |  | 158.55 | 0 | 15.26 | 51.6015 | 5.7335 | 231.145
| G.T. | 1355.92 | 0 | 0 | 15632 | 1000 | 100.9908 | 18088.9108 | 15070.2764 | 10496.651 | 814.0098 | 4204.5009 | 314.7256 | 200.6489 | 16030.5363
22.26
[12 empty] | District Programme Coordinator |  |  |  | 15.26
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2012-13 Up to the Month of Jan 2013 | [19 empty] | Physical Performance Under NREGA During the year 2012-13 Up to the Month of Jan 2013 | [17 empty] | Physical Performance Under NREGA During the year 2012-13 Up to the Month of Jan 2013
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 1251 | 746460.7408 | 1445.8383 | 502 | 246951.742 | 304.4869 | 172 | 98.218 | 78.3409 | 316 | 112.474 | 122.3894 | 516 | 1447.7027 | 785.7476 | 378 | 250.6059 | 662.3884 | 318 | 195.7448 | 208.358 | 240 | 131.9445 | 187.1802 | 198 | 196875.7676 | 249.4161 | 207 | 140024.6104 | 128.8221 | 1826 | 4943.6242 | 1580.8444 | 1025 | 1385.3914 | 614.0734 | 641 | 1916.7157 | 1824.2303 | 833 | 145.8741 | 1582.2679 | 1646 | 1231.0927 | 3058.0923 | 1335 | 682.6689 | 2315.1371 | 5 | 0 | 27.7732 | 68 | 6.25 | 339.7715 | 6573 | 9258.64 | 4904 | 6256.52
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator |  | 11477
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2012-13 Up to the Month of Jan 2013
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 2422 | 0 | 3 | 19 | 435 | 2 | 0 | 10 | 0 | 0
2 | Alipurduar-II | 959 | 0 | 4 | 0 | 927 | 0 | 1 | 0 | 8 | 0
3 | Dhupguri | 3226.4731 | 12905.8923 | 832 | 9 | 0 | 0.1 | 0 | 1 | 12 | 12
4 | Falakata | 135 | 1793 | 1 | 11 | 0 | 440 | 3 | 2 | 0 | 2
5 | Kalchini | 470 | 127 | 15 | 7 | 0 | 12 | 17 | 73 | 0 | 0
6 | Kumargram | 2773 | 3168 | 1 | 5 | 48 | 11.16 | 10 | 1 | 0 | 0
7 | Madarihat-Birpara | 2644 | 2255 | 13 | 7 | 509 | 117 | 0 | 10 | 0 | 0
8 | Mal | 0 | 207 | 0 | 0 | 516 | 49 | 0 | 0 | 0 | 0
9 | Matiali | 0 | 407 | 0 | 5 | 0 | 41 | 0 | 5 | 1 | 1
10 | Maynaguri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
11 | Nagrakata | 4572 | 319 | 5 | 5 | 210 | 113 | 5 | 0 | 0 | 4
12 | Rajganj | 13940 | 1247 | 2 | 10 | 1266 | 65 |  |  | 0 | 0 | report collected from sudip da muster roll verification and inspection
13 | Sadar | 0 | 3504 | 8 | 6 | 12 | 16 | 0 | 0 | 2 | 7
| Total | 31141.4731 | 25932.8923 | 884 | 84 | 3923 | 866.26 | 36 | 102 | 25 | 26
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of Jan 2013)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 11 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of Jan 2013)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
Jan 2013
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
1 | Alipurduar-I | 5902 | 0 | 61.1505 | 39269 | 320 | 440.2407 | 501.3912 | 501.39 | 0.00118
2 | Alipurduar-II | 7895 | 36 | 144.4699 | 26404 | 45 | 702.1933 | 846.6632 | 846.66 | 0.00322
3 | Dhupguri | 1061 | 960 | 669.5 | 8990 | 4021 | 691.38 | 1360.88 | 1360.88 | 0
4 | Falakata | 22510 | 92 | 632.1252 | 34116 | 579 | 961.1464 | 1593.2716 | 1593.27 | 0.0016
5 | Kalchini | 19315 | 345 | 454.5571 | 36849 | 3086 | 825.188 | 1279.7451 | 1279.75 | -0.00488
6 | Kumargram | 4791 | 1607 | 223.9798 | 30546 | 5592 | 666.883 | 890.8629 | 890.86 | 0.00286
7 | Madarihat | 4621 | 53 | 89.1593 | 37397 | 4315 | 565.8994 | 655.0587 | 655.056 | 0.00268
8 | Mal | 2380 | 11 | 0 | 32582 | 1389 | 633.2362 | 633.2362 | 633.24 | -0.0038
9 | Matiali | 0 | 0 | 0 | 52395 | 501 | 486.3084 | 486.3084 | 486.31 | -0.0016
10 | Maynaguri | 7679 | 0 | 140.5653 | 48857 | 0 | 448.887 | 589.4523 | 589.45 | 0.00232
11 | Nagrakata | 3061 | 0 | 50.3218 | 28403 | 0 | 352.1288 | 402.4507 | 402.455 | -0.00433
12 | Rajganj | 2906 | 0 | 13.5679 | 45782 | 4733 | 239.9438 | 253.5117 | 253.51 | 0.00169
13 | Sadar | 2796 | 0 | 80.196 | 37143 | 0 | 765.077 | 845.273 | 845.27 | 0.003
| Line dep. |  |  | 52.258 |  |  | 106.292 | 158.55 | 158.55 | 0
Total |  | 84917 | 3104 | 2611.8508 | 458733 | 24581 | 7884.8041 | 10496.6549 | 10496.651 | 0.00394