## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
part I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of MAY 2012 (for the financial year 2012-13)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 |  | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Alipurduar-I | 40448 | 21046 | 8586 | 10816 | 40448 | 2049 | 3631 | 2049 | 969 | 62945 | 0.41917 | 0.14743 | 0.14698 | 0.71359 | 0.3765 | 0 | 0 | 187 | 7 | 52.7614 | 34.8263
2 | Alipurduar-II | 45215 | 17364 | 5073 | 22778 | 45215 | 3214 | 4210 | 3214 | 1552 | 73252 | 0.28755 | 0.1403 | 0.26818 | 0.69603 | 0.44 | 0.17 | 0 | 0 | 0 | 63.2157 | 21.6562
3 | Dhupguri | 80508 | 39105 | 16764 | 22691 | 78560 | 4016 | 9391 | 3316 | 1489 | 207565 | 0.54714 | 0.22629 | 0.42342 | 1.1968 | 0.61346 | 0.07074 | 0 | 77 | 5 | 51.2562 | 36.0932
4 | Falakata | 52370 | 23696 | 10067 | 18607 | 52370 | 1866 | 7987 | 1866 | 1866 | 138566 | 0.34508 | 0.03404 | 0.13432 | 0.51344 | 0.23056 | 0.03181 | 0 | 50 | 0 | 44.905 | 27.5155
5 | Kalchini | 60769 | 8800 | 31649 | 19552 | 60001 | 5209 | 7151 | 4509 | 2574 | 124045 | 0.16423 | 0.35136 | 0.3776 | 0.89319 | 0.41352 | 0.0247 | 0 | 405 | 0 | 46.297 | 19.809
6 | Kumargram | 40494 | 16636 | 13655 | 10183 | 40474 | 17350 | 11785 | 15429 | 15165 | 204411 | 0.72796 | 0.35093 | 0.41859 | 1.4975 | 0.61518 | 0.259 | 0 | 245 | 35 | 41.0808 | 9.7056
7 | Madarihat | 39294 | 7539 | 16324 | 15431 | 39294 | 0 | 7825 | 0 | 0 | 135720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
8 | Mal | 58540 | 18394 | 20606 | 19540 | 58540 | 1737 | 5994 | 1715 | 343 | 103962 | 0.13335 | 0.08808 | 0.16555 | 0.38698 | 0.04996 | 0 | 0 | 0 | 0 | 12.9102 | 22.5644
9 | Matiali | 24986 | 5981 | 12141 | 6675 | 24797 | 3691 | 2839 | 3691 | 3691 | 49221 | 0.16905 | 0.32856 | 0.15152 | 0.64913 | 0.29945 | 0.00113 | 0 | 0 | 0 | 46.131 | 17.5868
10 | Maynaguri | 70679 | 50899 | 1053 | 18261 | 70213 | 2562 | 7332 | 2562 | 2562 | 196294 | 0.43212 | 0.00111 | 0.12484 | 0.55807 | 0.21561 | 0.011388 | 0 | 0 | 0 | 38.6349 | 21.7826
11 | Nagrakata | 26331 | 3949 | 15086 | 7296 | 26331 | 0 | 3109 | 0 | 0 | 53915 | 0.13486 | 0.15361 | 0.17553 | 0.464 | 0.12488 | 0.07039 | 0 | 110 | 0 | 26.9138 | #DIV/0!
12 | Rajganj | 51625 | 29922 | 2727 | 18976 | 51625 | 4891 | 3737 | 4891 | 4891 | 64828 | 0.30324 | 0.00969 | 0.23114 | 0.54407 | 0.24198 | 0.11855 | 0 | 40 | 0 | 44.4759 | 11.1239
13 | Sadar | 58642 | 34782 | 4355 | 19505 | 58642 | 0 | 3733 | 0 | 0 | 64737 | 0.04961 | 0.00761 | 0.03843 | 0.09565 | 0.03834 | 0.03706 | 0 | 169 | 0 | 40.0836 | #DIV/0!
| Total: | 649901 | 278113 | 158086 | 210311 | 646510 | 46585 | 78724 | 43242 | 35102 | 1479461 | 3.7134 | 1.839 | 2.6561 | 8.2085 | 3.6594 | 0.79477 | 0 | 1283 | 47 | 44.5812 | 18.9827
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri
As on 31/05/2012
Employment provided to HHS: 43242 nos.
Persondays[in lac]: Total: 8.21, SCs: 3.71 [ 45.24 %], STs: 1.84 [22.40% ], Women : 3.66 [44.58%], Others: 2.66 [32.36 %]
Works taken up: 5031 nos.,Works completed: 1650 nos., Works in progress: 3381 nos.
Total exp:3302.27 lac,GP wise avg exp:22.18 lac

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2012-13 Up to the Month of MAY ' 2012
[16 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Sl. No. | Name of the Block | Actual O.B. as on 01.04.12 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability (4+5+6+7+8) | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh)
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (9+10+11+12) | Balance |  | Expenditure up to prev. months | expenditure during the month | Balance | Balance | Balance
[13 empty] | Recurring | Non-Recurring
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Alipurduar-I | -24.5211 |  |  | 333.8584 |  |  | 309.3372 | 125.935 | 127.1822 | 6.3771 | 49.5399 | 5.3267 | 0.89662 | 189.3226 | 120.0146 | #REF! | 274.4036 | -85.081 | 61.85 |  | -223.5791
2 | Alipurduar-II | 44.2983 |  |  | 426.4733 |  |  | 470.7717 | 146.0875 | 248.8215 | 15.8079 | 78.6252 | 7.0198 | 3.4483 | 353.7227 | 117.049 | #REF! | 304.4107 | 49.312 | 36.8577 |  | -245.0153
3 | Dhupguri | 106.7473 |  |  | 442.1948 |  |  | 548.9422 | 417.3966 | 236.792 | 8.9403 | 45.0674 | 1.158 | 2.1975 | 294.1552 | 254.787 | #REF! | 959.1269 | -664.9717 | 166.1673 |  | -555.2914
4 | Falakata | 42.231 |  |  | 833.8322 |  |  | 876.0632 | 277.125 | 437.9858 | 28.0961 | 74.8587 | 7.0387 | 2.2384 | 550.2178 | 325.8454 | #REF! | 292.4339 | 257.7839 | 44.8451 |  | 230.1104
5 | Kalchini | 53.1356 |  |  | 478.2747 |  |  | 531.4103 | 248.075 | 251.8425 | 21.0766 | 69.3504 | 5.6259 | 2.3369 | 350.2322 | 181.1782 | #REF! | 214.0691 | 136.1631 | 90.2812 | 4.3138 | -241.2473
6 | Kumargram | 39.365 |  |  | 382.9904 |  |  | 422.3553 | 406.325 | 223.3313 | 16.6151 | 123.7719 | 4.8764 | 3.5477 | 372.1424 | 50.213 | #REF! | 530.3212 | -158.1789 | 81.51 |  | -260.2562
7 | Madarihat | 8.2693 |  |  | 347.5918 |  |  | 355.8611 | 271.3375 | 128.9015 | 15.0654 | 18.1458 | 2.086 | 4.5678 | 168.7665 | 187.0947 | #DIV/0! | 325.6474 | -156.8809 | 84.9085 |  | -374.2491
8 | Mal | 92.7703 |  |  | 264.0603 |  |  | 356.8306 | 207.9625 | 110.6106 | 7.142 | 17.5373 | 4.4544 | 1.4364 | 141.1807 | 215.6499 | 285.8303 | 367.8294 | -226.6487 | 95.95 |  | -259.6052
9 | Matiali | 18.3071 |  |  | 143.3141 |  |  | 161.6212 | 98.4375 | 86.4154 | 5.5464 | 7.5462 | 2.1816 | 1.338 | 103.0275 | 58.5936 | #REF! | 147.3002 | -44.2726 | 83.8542 |  | -120.3483
10 | Maynaguri | 152.7345 |  |  | 415.6172 |  |  | 568.3517 | 402.0921 | 121.1996 | 7.2168 | 48.9911 | 0.77387 | 1.2117 | 179.3931 | 388.9585 | 217.1763 | 266.2758 | -86.8826 | 80.1736 |  | -375.3411
11 | Nagrakata | 23.4309 |  |  | 135.6729 |  |  | 159.1038 | 107.825 | 84.7787 | 6.8374 | 16.9883 | 0.621 | 0.73093 | 109.9564 | 49.1474 | #REF! | 73.3785 | 36.5779 | 29.6664 |  | -149.8995
12 | Rajganj | -4.6747 |  |  | 181.05 |  |  | 176.3753 | 129.65 | 70.8526 | 3.5851 | 26.1328 | 19.3256 | 0.85715 | 120.7532 | 55.622 | #REF! | 158.2235 | -37.4703 | 52.4855 |  | -103.422
13 | Sadar | 76.5827 |  |  | 423.2951 |  |  | 499.8778 | 129.4625 | 256.4862 | 14.477 | 27.4415 | 6.5635 | 0.942 | 305.9102 | 193.9676 | #REF! | 198.2151 | 107.695 | 61.025 |  | -117.2727
| Total | 628.6761 | 0 | 0 | 4808.2253 |  | 0 | 5436.9014 | 2967.7112 | 2385.1997 | 156.7834 | 603.9964 | 67.0515 | 25.7494 | 3238.7804 | 2198.121 | #REF! | 4111.6353 | -872.8549 | 969.5746 |  | -2795.4167
1 | Line Deptt. | 216.61 |  |  | 46.8573 |  |  | 263.4673 |  | 55.07 | 0 | 0 | 0 | 0 | 55.07 | 208.3973 |  | 83.25
2 | District Cell | 670.3172 |  |  | 7400 | 0 |  | 8070.3172 |  | 0 | 0 | 0 | 8.2436 | 0.18 | 8.4236 |  |  | 29.3346
| Total | 886.9272 | 0 | 0 | 7400 | 0 | 0 | 8333.7844 |  | 55.07 | 0 | 0 | 8.2436 | 0.18 | 63.4936 |  |  | 71.9172
| G.T. | 1515.6033 | 0 | 0 | 7400 | 0 | 0 | 8915.6033 | 2967.7112 | 2440.2697 | 156.7834 | 603.9964 | 75.2952 | 25.9294 | 3302.274 | 5613.3293 | 5238.4338 | 4183.5525 |  | -1936.1598
DPC
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri
Note on K24: May 2012
Note on N25: May' 12
Note on O25: May' 12

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2012-13 Up to the Month of MAY 2012 | [19 empty] | Physical Performance Under NREGA During the year 2012-13 Up to the Month of MAY 2012 | [17 empty] | Physical Performance Under NREGA During the year 2012-13 Up to the Month of MAY 2012
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 377 | 218635.7081 | 360.9754 | 734 | 234538.9942 | 250.0803 | 37 | 65.045 | 16.3653 | 175 | 54.6926 | 36.1085 | 126 | 58.8289 | 115.7896 | 190 | 48.1401 | 95.3381 | 40 | 15.5 | 30.7489 | 41 | 60.1 | 2.1059 | 36 | 1323.0247 | 32.2222 | 261 | 138735.5596 | 61.1654 | 443 | 2803.571 | 432.8747 | 628 | 2803.4014 | 144.8944 | 104 | 36.1279 | 204.8992 | 388 | 213.1247 | 276.6228 | 487 | 176.763 | 590.9957 | 916 | 326.1092 | 517.383 | 0 | 0 | 0 | 48 | 5.25 | 32.4797 | 1650 | 1784.8712 | 3381 | 1416.1783
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2012-13 Up to the Month of MAY 2012
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 1013 | 0 | 11 | 3 | 307 | 2 | 0 | 10 | 0 | 0
2 | Alipurduar-II | 444 | 0 | 11 | 0 | 436 | 0 | 1 | 0 | 8 | 0
3 | Dhupguri | 68.7802 | 275.1207 | 16 | 0 | 0 | 0 | 0 | 1 | 12 | 12
4 | Falakata | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Kalchini | 58 | 0 | 11 | 0 | 0 | 0 | 34 | 24 | 0 | 0
6 | Kumargram | 2972 | 294 | 11 | 0 | 48 | 2 | 10 | 1 | 0 | 0
7 | Madarihat-Birpara | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0
8 | Mal | 0 | 0 | 12 | 0 | 0 | 8 | 0 | 0 | 0 | 0
9 | Matiali | 0 | 49 | 5 | 0 | 0 | 6 | 0 | 5 | 0 | 0
10 | Maynaguri | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 2 | 0
11 | Nagrakata | 198 | 0 | 5 | 0 | 140 | 0 | 5 | 0 | 0 | 4
12 | Rajganj | 11619 | 890 | 12 | 0 | 611 | 53 | 0 | 0 | 0 | 0 | report collected from sudip da muster roll verification and inspection
13 | Sadar | 2257 | 962 | 14 | 0 | 184 | 27 | 0 | 0 | 4 | 4
| Total | 18629.7802 | 2470.1207 | 146 | 3 | 1726 | 98 | 50 | 51 | 26 | 20
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of MAY 2012)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of MAY 2012)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
MAY 2012
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
1 | Alipurduar-I | 5902 | 0 | 9.9229 | 39269 | 320 | 117.2593 | 127.1822 | 127.1822 | 0
2 | Alipurduar-II | 7895 | 36 | 35.3359 | 26404 | 45 | 213.4856 | 248.8215 | 248.8215 | 0 | #REF! | 248.8215
3 | Dhupguri | 920 | 752 | 84.2154 | 8751 | 3637 | 152.58 | 236.7954 | 236.792 | 0.00345
4 | Falakata | 16013 | 612 | 158.0669 | 43281 | 59 | 279.9189 | 437.9858 | 437.9858 | 0
5 | Kalchini | 19265 | 345 | 73.3789 | 36469 | 3086 | 178.4636 | 251.8425 | 251.8425 | 0
6 | Kumargram | 4454 | 1607 | 44.6276 | 30546 | 5853 | 178.7045 | 223.3321 | 223.3313 | 0.0008
7 | Madarihat | 4466 | 53 | 8.5137 | 35893 | 4300 | 120.3878 | 128.9015 | 128.9015 | 0
8 | Mal | 2380 | 11 | 0 | 32582 | 1389 | 110.6106 | 110.6106 | 110.6106 | 0
9 | Matiali | 0 | 0 | 0 | 52395 | 501 | 86.4154 | 86.4154 | 86.4154 | 0
10 | Maynaguri | 7679 | 0 | 0 | 48857 | 0 | 121.2 | 121.2 | 121.1996 | 0.0004
11 | Nagrakata | 3213 | 0 | 11.0487 | 28403 | 0 | 73.73 | 84.7787 | 84.7787 | 0
12 | Rajganj | 2906 | 0 | 11.3334 | 45947 | 4733 | 59.5192 | 70.8526 | 70.8526 | 0
13 | Sadar | 2741 | 0 | 21.1973 | 40160 | 0 | 235.2889 | 256.4862 | 256.4862 | 0
| Line dep. |  |  | 24.6495 |  |  | 30.4205 | 55.07 | 55.07 | 0
Total |  | 77834 | 3416 | 482.2901 | 468957 | 23923 | 1957.9842 | 2440.2744 | 2440.2697 | 0.00465