## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
part I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of March 2014 (for the financial year 2013-14)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals |  |  | 1.85
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 | 3 | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Alipurduar-I | 40870 | 21013 | 7904 | 11945 | 40862 | 24312 | 13501 | 22662 | 12825 | 402931 | 4.2065 | 0.99614 | 2.435 | 7.6376 | 3.7705 | 0.010682 | 647 | 69 | 10 | 0 | 33.7025
2 | Alipurduar-II | 46392 | 17723 | 5158 | 23511 | 46392 | 30103 | 16352 | 28118 | 3320 | 463018 | 3.24 | 0.80506 | 3.7182 | 7.7633 | 2.8971 | 3.7983 | 197 | 198 | 31 | 37.3175 | 27.6097
3 | Dhupguri | 78323 | 39846 | 15853 | 22586 | 78285 | 67954 | 71038 | 66506 | 78459 | 2157508 | 6.6348 | 3.0006 | 8.9344 | 18.5699 | 6.0922 | 0.01805 | 273 | 418 | 121 | 32.807 | 27.9221
4 | Falakata | 56264 | 24464 | 10426 | 21203 | 56166 | 38468 | 31315 | 37010 | 20274 | 886104 | 4.8656 | 1.6405 | 6.5352 | 13.0413 | 5.941 | 0.8113 | 509 | 217 | 33 | 45.5555 | 35.2372
5 | Kalchini | 60207 | 8550 | 29137 | 22080 | 59767 | 44424 | 29301 | 44323 | 22284 | 792264 | 0.9723 | 4.0275 | 7.5494 | 12.5492 | 5.7794 | 0.36149 | 271 | 118 | 92 | 46.0537 | 28.3132
6 | Kumargram | 48891 | 19715 | 13857 | 15319 | 48891 | 33655 | 48281 | 32695 | 34947 | 1301055 | 3.2484 | 1.257 | 4.8855 | 9.3909 | 3.4359 | 0.25 | 77 | 135 | 9 | 36.5873 | 28.7227
7 | Madarihat | 40076 | 4934 | 12064 | 23078 | 40076 | 27782 | 30942 | 27346 | 11935 | 865613 | 1.5571 | 2.9555 | 6.9101 | 11.4228 | 6.01 | 1.6998 | 686 | 70 | 22 | 52.6143 | #REF!
8 | Mal | 59222 | 18574 | 21679 | 18969 | 59222 | 36918 | 23475 | 35289 | 13815 | 665767 | 1.8298 | 2.525 | 4.3302 | 8.685 | 3.6091 | 0 | 150 | 298 | 13 | 62.0962 | 21.2104
9 | Matiali | 25505 | 6567 | 12139 | 6986 | 23735 | 18177 | 7901 | 17618 | 16321 | 220739 | 0.77147 | 1.41 | 2.396 | 4.5774 | 2.4116 | 0.01004 | 57 | 8 | 2 | 52.6855 | 25.9813
10 | Maynaguri | 71202 | 46253 | 706 | 24186 | 71145 | 45580 | 13676 | 43634 | 18629 | 649328 | 5.6264 | 0.13962 | 4.0284 | 9.7944 | 3.528 | 0.15471 | 132 | 194 | 27 | 36.02 | 22.4467
11 | Nagrakata | 27087 | 4299 | 15529 | 7203 | 27031 | 19793 | 12735 | 19439 | 7714 | 345068 | 0.69509 | 1.5712 | 2.4964 | 4.7626 | 2.0234 | 0.58698 | 56 | 58 | 3 | 42.4851 | 24.5003
12 | Rajganj | 51850 | 28014 | 2207 | 21573 | 51794 | 31014 | 11747 | 29351 | 5456 | 355231 | 2.5053 | 0.18559 | 3.3421 | 6.033 | 2.717 | 1.563 | 57 | 145 | 55 | 45.0352 | 20.5546
13 | Sadar | 61804 | 33902 | 4045 | 23857 | 61804 | 40893 | 15291 | 38557 | 17369 | 418174 | 5.3457 | 0.37841 | 4.165 | 9.889 | 3.7029 | 1.1397 | 206 | 174 | 21 | 37.4444 | 25.6478
| Total: | 667693 | 273854 | 150704 | 242496 | 665170 | 459073 | 325555 | 442548 | 263348 | 9522800 | 41.4985 | 20.892 | 61.726 | 124.1165 | 51.918 | 10.4041 | 3318 | 2102 | 439 | 41.8301 | 28.0459
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2012-13 Up to the Month of March ' 2014
1250.56
Sl. No. | Name of the Block | Actual O.B. as on 01.04.13 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh) | [6 empty] | 2389.34
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (10+11+12+13+14)
[13 empty] | Recurring | Non-Recurring |  |  | 4.32 |  |  |  |  | avg. gp
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | [8 empty] | WAGE% | PER LABOUR
1 | Alipurduar-I | 14.5029 |  |  | 1147.3118 |  | 3.2093 | 1165.0239 | 1191.068 | 735.33 | 64.51 | 378.53 | 56.71 | 0.35 | 1235.43 |  | 11.2445 | 48.5761 | 783.9061 | 395.2494 | 11 | 112.3118 | 112.3118 | 59.5202 | 96.277 | Alipurduar-I | 506.4504 | 1178.37
2 | Alipurduar-II | 19.8569 |  |  | 1399.2383 |  | 4.8438 | 1423.939 | 1167.261 | 872.53 | 73.36 | 427.66 | 52.09 | 0.47 | 1426.11 |  | 12.98 | 0 | 872.53 | 556.075 | 11 | 129.6464 | 129.6464 | 61.1825 | 112.3916 | Alipurduar-II | 704.6012
3 | Dhupguri | 169.1634 |  |  | 2633.3569 |  | 4.6937 | 2807.214 | 5662.817 | 1859.72 | 133.55 | 787.07 | 88.89 | 0.45 | 2869.68 |  | 26.1189 | 293.6928 | 2153.4128 | 946.3318 | 16 | 179.355 | 260.88 | 64.8058 | 100.1472 | Dhupguri | 831.2044
4 | Falakata | 24.2016 |  |  | 1753.1191 |  | 3.9796 | 1781.3003 | 2328.192 | 1089.42 | 74.59 | 505.16 | 92.08 | 0.53 | 1761.78 |  | 16.0351 | 208.1356 | 1297.5556 | 1457.4699 | 12 | 146.815 | 160.1618 | 61.8363 | 83.5362 | Falakata | 1512.1343
5 | Kalchini | 86.4572 |  |  | 2565.6795 |  | 7.9168 | 2660.0536 | 2090.185 | 1793.85 | 179.29 | 603.06 | 63.07 | 1.07 | 2640.34 |  | 24.0315 | 627.6754 | 2421.5254 | 1030.0591 | 11 | 240.0309 | 240.0309 | 67.9401 | 142.9449 | Kalchini | 866.6745
6 | Kumargram | 25.0465 |  |  | 2377.233 |  | 6.5766 | 2408.8561 | 3340.901 | 1155.97 | 181.88 | 1051.49 | 81.75 | 0.49 | 2471.58 |  | 22.4955 | 360.7182 | 1516.6882 | 853.5048 | 11 | 224.6891 | 224.6891 | 46.7705 | 123.0948 | Kumargram | 952.4868
7 | Madarihat | 21.262 |  |  | 1664.1312 |  | 2.9103 | 1688.3034 | 2258.643 | 1250.07 | 99.97 | 260.11 | 45.89 | 0.04 | 1656.08 |  | 15.0731 | 362.2288 | 1612.2988 | 527.0331 | 10 | 165.608 | 150.5527 | #REF! | #REF! | Madarihat-Birpara | 466.6014
8 | Mal | 37.7467 |  |  | 1189.5054 |  | 2.3096 | 1229.5617 | 1786.858 | 990.16 | 61.73 | 138.46 | 58.26 | 1.95 | 1250.56 |  | 11.3822 | 256.0477 | 1246.2077 | 394.9049 | 12 | 104.2133 | 113.6873 | 79.1773 | 114.0077 | Malbazar | 402.7251
9 | Matiali | 26.9722 |  |  | 631.0559 |  | 1.2737 | 659.3017 | 597.168 | 495.87 | 39.75 | 79.36 | 46.38 | 0.24 | 661.6 |  | 6.0217 | 90.765 | 586.635 | 329.2062 | 5 | 132.32 | 60.1455 | #REF! | #REF! | Matiali | 230.7365
10 | Maynaguri | 107.6975 |  |  | 1529.5718 |  | 2.8018 | 1640.0711 | 1791.097 | 1168.31 | 75.97 | 253.48 | 77.32 | 1.56 | 1576.64 |  | 14.3501 | 163.3348 | 1331.6448 | 421.4004 | 16 | 98.54 | 143.3309 | 74.1013 | 119.2833 | Maynaguri | 677.9344
11 | Nagrakata | 20.9906 |  |  | 777.3679 |  | 1.9212 | 800.2797 | 911.406 | 543.84 | 47.1 | 176.66 | 47.73 | 0.81 | 816.14 |  | 7.4282 | 44.7303 | 588.5703 | 284.0694 | 5 | 163.228 | 74.1945 | #REF! | #REF! | Nagrakata | 243.0925
12 | Rajganj | 23.7163 |  |  | 795.8985 |  | 2.4208 | 822.0356 | 1007.893 | 667.3 | 44.13 | 81.67 | 33.53 | 1.15 | 827.78 | 51.1913 | 7.5342 | 108.1158 | 775.4158 | 217.4445 | 12 | 68.9817 | 75.2527 | 80.6132 | 110.6089 | Rajganj | 282.2
13 | Sadar | 78.7703 |  |  | 1193.4168 |  | 2.4147 | 1274.6017 | 1275.732 | 1011.3 | 91.41 | 132.75 | 51.37 | 0 | 1286.83 |  | 11.7123 | 87.0017 | 1098.3017 | 551.7063 | 14 | 91.9164 | 116.9845 | 78.5885 | 102.2647 | Sadar | 641.197
| Total | 656.384 | 0 | 0 | 19656.886 |  | 47.2718 | 20360.5419 | 25409.221 | 13633.67 | 1167.24 | 4875.46 | 795.07 | 9.11 | 20480.55 |  | 45.61 |  |  |  | 146 | 140.2777 | 1861.8682 | 66.5689
1 | Line Deptt. | 44.3 |  |  | 123.15 |  | 0 | 167.45 |  | 86.41 | 4.8 | 30.63 | 0 | 0 | 121.84 | [5 empty] | 19798.21 |  | 140.2777
2 | District Cell | 727.12 |  |  | 18700 | 2000 | 0 | 21427.12 |  | 0 | 0 | 0 | 61.1753 | 4.5763 | 65.7516 |  | 57.61
| Total | 771.42 | 0 | 0 | 18700 | 2000 | 0 | 21594.57 |  | 86.41 | 4.8 | 30.63 | 61.1753 | 4.5763 | 187.5916 |  | 53.61
| G.T. | 1427.804 | 0 | 0 | 18700 | 2000 | 47.2718 | 22175.0758 | 25409.221 | 13720.08 | 1172.04 | 4906.09 | 856.2453 | 13.6863 | 20668.1416 |  | 93.04
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2013-14 Up to the Month of March 2014 | [19 empty] | Physical Performance Under NREGA During the year 2013-14 Up to the Month of March 2014 | [17 empty] | Physical Performance Under NREGA During the year 2013-14 Up to the Month of March 2014
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 837 | 398163.5817 | 1134.2782 | 705 | 68207.114 | 435.18 | 143 | 45221.0437 | 65.2859 | 208 | 4.4004 | 48.4072 | 523 | 533.7794 | 1174.0677 | 586 | 258.8356 | 763.0221 | 717 | 294.9152 | 671.1974 | 804 | 1100.3193 | 205.5035 | 265 | 56222.4973 | 188.6878 | 328 | 5089.2805 | 164.0868 | 1618 | 6303.7935 | 1686.5329 | 1250 | 318.4124 | 648.1162 | 796 | 2670.586 | 2066.959 | 682 | 148.8385 | 1763.8167 | 2210 | 1690.6493 | 4559.2885 | 2426 | 742.1219 | 3224.9653 | 227 | 162 | 485.6383 | 276 | 1002 | 513.1846 | 7336 | 12031.9357 | 7265 | 7766.2824
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2013-14 Up to the Month of March 2014
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 644 | 0 | 0 | 8 | 628 | 16 | 0 | 9 | 3 | 0
2 | Alipurduar-II | 510 | 0 | 4 | 0 | 488 | 0 | 1 | 0 | 8 | 0
3 | Dhupguri | 4271.5527 | 17086.2107 | 1278 | 9 | 0 | 0.1 | 0 | 1 | 12 | 12
4 | Falakata | 7 | 1830 | 7 | 4 | 0 | 2.02 | 1 | 2 | 0 | 0
5 | Kalchini | 695 | 115 | 7 | 15 | 0 | 4 | 17 | 15 | 0 | 0
6 | Kumargram | 2162 | 939 | 2 | 70 | 6 | 6 | 16 | 9 | 0 | 0
7 | Madarihat-Birpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Mal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Matiali | 0 | 33 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 1
10 | Maynaguri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
11 | Nagrakata | 4643 | 22 | 0 | 10 | 394 | 90 | 0 | 5 | 0 | 1
12 | Rajganj | 13940 | 1247 | 2 | 10 | 1266 | 65 |  |  | 0 | 0
13 | Sadar | 10933 | 120 | 0 | 14 | 229 | 54 | 0 | 28 | 0 | 0
| Total | 37805.5527 | 21392.2107 | 1300 | 140 | 3011 | 242.12 | 35 | 69 | 25 | 14
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of March 2014)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 11 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of March 2014)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
March 2014
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
1 | Alipurduar-I | 5956 | 0 | 71.5956 | 42987 | 320 | 663.7296 | 735.3252 | 735.33 | -0.00475
2 | Alipurduar-II | 7895 | 36 | 38.4218 | 26404 | 45 | 834.1087 | 872.5305 | 872.53 | 0.00051
3 | Dhupguri | 9904 | 254 | 1036.53 | 1059 | 3980 | 823.19 | 1859.72 | 1859.72 | 0
4 | Falakata | 23654 | 155 | 411.5458 | 40488 | 59 | 677.8781 | 1089.4238 | 1089.42 | 0.00384
5 | Kalchini | 18947 | 297 | 546.7107 | 37542 | 2753 | 1247.141 | 1793.8517 | 1793.85 | 0.00169
6 | Kumargram | 4791 | 1607 | 201.5692 | 30546 | 3458 | 954.3963 | 1155.9654 | 1155.97 | -0.00456
7 | Madarihat | 4980 | 46 | 163.69 | 46837 | 628 | 1086.3838 | 1250.0739 | 1250.07 | 0.00387
8 | Mal | 1279 | 8 | 0 | 32627 | 1377 | 990.1648 | 990.1648 | 990.16 | 0.00484
9 | Matiali | 0 | 0 | 0 | 52395 | 501 | 495.8701 | 495.8701 | 495.87 | 7e-05
10 | Maynaguri | 6051 | 0 | 105.7 | 61904 | 0 | 1062.6077 | 1168.3077 | 1168.31 | -0.00233
11 | Nagrakata | 3247 | 0 | 108.3271 | 23143 | 0 | 435.5083 | 543.8354 | 543.84 | -0.00462
12 | Rajganj | 4331 | 0 | 41.3468 | 51097 | 0 | 625.955 | 667.3019 | 667.3 | 0.00186
13 | Sadar | 4056 | 0 | 40.954 | 59535 | 0 | 970.3469 | 1011.3009 | 1011.3 | 0.00091091
| Line dep. |  |  | 0 |  |  | 86.41 | 86.41 | 86.41 | 0
Total |  | 95091 | 2403 | 2766.4009 | 506564 | 13121 | 10953.6804 | 13720.0813 | 13720.08 | 0.0013309
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri