## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
part I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of Feb 2014 (for the financial year 2013-14)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals |  |  | 1.85
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 | 3 | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Alipurduar-I | 40552 | 20824 | 7885 | 11835 | 40544 | 23883 | 10792 | 23883 | 7611 | 225534 | 2.8828 | 0.98201 | 1.4328 | 5.2976 | 2.6282 | 0.00145 | 69 | 500 | 10 | 0 | 22.1815
2 | Alipurduar-II | 46267 | 17695 | 5146 | 23426 | 46267 | 29412 | 13027 | 29412 | 2848 | 261792 | 2.0612 | 0.57785 | 2.3617 | 5.0007 | 1.8368 | 2.3742 | 26 | 172 | 25 | 36.7314 | 17.0024
3 | Dhupguri | 78323 | 39846 | 15853 | 22586 | 78285 | 50811 | 53481 | 53794 | 78459 | 1214110 | 2.9096 | 1.4237 | 3.6464 | 7.9797 | 2.6415 | 0.01805 | 0 | 18 | 13 | 33.1033 | 14.8338
4 | Falakata | 53112 | 24585 | 10336 | 18191 | 53112 | 26879 | 24779 | 26879 | 10646 | 497226 | 3.6233 | 1.7937 | 3.6665 | 9.0835 | 4.2731 | 0.98959 | 253 | 2700 | 50 | 47.0425 | 33.794
5 | Kalchini | 60091 | 8532 | 29106 | 22013 | 59651 | 42365 | 23410 | 41185 | 15474 | 445117 | 1.3977 | 4.5277 | 3.1538 | 9.0791 | 4.3821 | 0.30958 | 2 | 384 | 1 | 48.2662 | 22.0447
6 | Kumargram | 46275 | 18421 | 13632 | 14222 | 46275 | 52060 | 38077 | 45377 | 33913 | 733506 | 2.0168 | 0.70582 | 3.0351 | 5.7577 | 2.1115 | 0.25 | 0 | 143 | 8 | 36.6725 | 12.6886
7 | Madarihat | 39991 | 4936 | 11814 | 23241 | 39991 | 27045 | 24578 | 26745 | 7865 | 486998 | 0.8461 | 1.7678 | 3.7405 | 6.3545 | 3.5351 | 0.96103 | 36 | 1 | 4 | 55.6318 | #REF!
8 | Mal | 59222 | 18574 | 21679 | 18969 | 59222 | 28320 | 18606 | 28320 | 6869 | 373119 | 1.459 | 1.9434 | 3.1892 | 6.5916 | 2.8034 | 0 | 17 | 441 | 0 | 62.0962 | 21.2104
9 | Matiali | 25505 | 6296 | 12104 | 7105 | 23548 | 12508 | 6263 | 12508 | 9002 | 123630 | 0.47006 | 1.0863 | 0.46319 | 2.0196 | 1.208 | 0.00088 | 0 | 15 | 9 | 59.813 | 16.1461
10 | Maynaguri | 70072 | 47513 | 805 | 21800 | 70118 | 61045 | 10916 | 34528 | 26760 | 362757 | 3.0795 | 0.06546 | 2.0461 | 5.191 | 1.9531 | 0.20085 | 0 | 64 | 12 | 37.6247 | 15.0343
11 | Nagrakata | 26629 | 4148 | 15432 | 6993 | 26573 | 22260 | 10043 | 22260 | 4238 | 193463 | 0.59408 | 1.5084 | 0.6898 | 2.7923 | 0.992 | 0.1596 | 23 | 81 | 6 | 35.526 | 12.5441
12 | Rajganj | 51403 | 29106 | 2466 | 19775 | 51347 | 29159 | 9409 | 29049 | 12889 | 197402 | 2.0385 | 0.1552 | 2.4949 | 4.6886 | 2.1037 | 1.5442 | 14 | 0 | 0 | 44.8678 | 16.1401
13 | Sadar | 61555 | 34054 | 4037 | 23464 | 61555 | 38942 | 12064 | 31293 | 11119 | 233816 | 3.0328 | 0.2874 | 2.5607 | 5.8809 | 2.1337 | 0.87459 | 29 | 419 | 29 | 36.2822 | 18.7931
| Total: | 658997 | 274530 | 150295 | 233620 | 656488 | 444689 | 255445 | 405233 | 227693 | 5348470 | 26.4114 | 16.8247 | 32.4806 | 75.7168 | 32.6022 | 7.684 | 469 | 4938 | 167 | 43.0581 | 18.6848
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2012-13 Up to the Month of Feb ' 2013
1033.9748
Sl. No. | Name of the Block | Actual O.B. as on 01.04.13 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh) | [6 empty] | 2148.9399
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (10+11+12+13+14)
[13 empty] | Recurring | Non-Recurring |  |  | 4.32 |  |  |  |  | avg. gp
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | [8 empty] | WAGE% | PER LABOUR
1 | Alipurduar-I | 14.5029 |  |  | 1055.4817 |  | 2.6399 | 1072.6245 | 580.447 | 601.9004 | 50.3277 | 385.1259 | 39.5753 | 7.0373 | 1083.9667 |  | 9.8659 | 42.6207 | 644.5211 | 395.2494 | 11 | 98.5424 | 98.5424 | 55.5276 | 113.6174 | Alipurduar-I | 506.4504 | 1037.3541
2 | Alipurduar-II | 19.8569 |  |  | 1324.0433 |  | 3.4753 | 1347.3755 | 661.916 | 719.7374 | 60.9301 | 416.3189 | 27.4766 | 13.8985 | 1238.3614 |  | 11.2712 | 0 | 719.7374 | 556.075 | 11 | 112.5783 | 112.5783 | 58.1201 | 143.9262 | Alipurduar-II | 704.6012
3 | Dhupguri | 169.1634 |  |  | 2476.9119 |  | 3.8278 | 2649.9031 | 3405.249 | 1438.3793 | 95.8808 | 793.1572 | 19.6299 | 18.5731 | 2365.6203 |  | 21.5311 | 212.4236 | 1650.8028 | 946.3318 | 16 | 147.8513 | 215.0564 | 60.8035 | 180.255 | Dhupguri | 831.2044
4 | Falakata | 24.2016 |  |  | 1627.3641 |  | 8.7629 | 1660.3285 | 1277.722 | 1665.6765 | 160.6027 | 632.3852 | 24.4854 | 23.6826 | 2506.8324 |  | 22.8164 | 257.1665 | 1922.8431 | 1457.4699 | 12 | 208.9027 | 227.8939 | 66.4455 | 183.3739 | Falakata | 1512.1343
5 | Kalchini | 86.4572 |  |  | 2404.3595 |  | 7.9168 | 2498.7336 | 1143.812 | 1581.5348 | 155.4497 | 570.0461 | 32.9734 | 24.9393 | 2364.9434 |  | 21.5249 | 463.455 | 2044.9898 | 1030.0591 | 11 | 214.9949 | 214.9949 | 66.8741 | 174.1949 | Kalchini | 866.6745
6 | Kumargram | 25.0465 |  |  | 2244.463 |  | 6.2314 | 2275.7409 | 1884.901 | 982.8655 | 164.1096 | 1001.9648 | 34.8478 | 55.8755 | 2239.6632 |  | 20.3847 | 465.1037 | 1447.9691 | 853.5048 | 11 | 203.6057 | 203.6057 | 43.8845 | 170.7045 | Kumargram | 952.4868
7 | Madarihat | 21.262 |  |  | 1530.7362 |  | 2.4192 | 1554.4174 | 1251.438 | 927.2578 | 77.2469 | 211.387 | 11.109 | 21.1673 | 1248.168 |  | 11.3604 | 244.5319 | 1171.7897 | 527.0331 | 10 | 124.8168 | 113.4698 | #REF! | #REF! | Madarihat-Birpara | 466.6014
8 | Mal | 37.7467 |  |  | 1090.0704 |  | 1.7338 | 1129.551 | 958.793 | 762.44 | 72.5587 | 185.895 | 3.1778 | 9.9033 | 1033.9748 |  | 9.4109 | 191.8379 | 954.2779 | 394.9049 | 12 | 86.1646 | 93.9977 | 73.7387 | 115.6677 | Malbazar | 402.7251
9 | Matiali | 26.9722 |  |  | 561.0659 |  | 0.96211 | 589.0002 | 317.691 | 307.774 | 27.9791 | 77.1735 | 3.8637 | 3.6034 | 420.3937 |  | 3.8263 | 43.4681 | 351.2422 | 329.2062 | 5 | 84.0787 | 38.2176 | #REF! | #REF! | Matiali | 230.7365
10 | Maynaguri | 107.6975 |  |  | 1412.9268 |  | 3.103 | 1523.7273 | 1153.233 | 808.3663 | 50.7954 | 186.4406 | 21.584 | 5.3346 | 1072.5209 |  | 9.7617 | 91.8666 | 900.2329 | 421.4004 | 16 | 67.0326 | 97.5019 | 75.3707 | 155.7237 | Maynaguri | 677.9344
11 | Nagrakata | 20.9906 |  |  | 716.4679 |  | 1.9431 | 739.4016 | 497.147 | 471.8933 | 39.4386 | 183.1599 | 1.7747 | 9.6652 | 705.9317 |  | 6.4252 | 24.5845 | 496.4777 | 284.0694 | 5 | 141.1863 | 64.1756 | #REF! | #REF! | Nagrakata | 243.0925
12 | Rajganj | 23.7163 |  |  | 740.7535 |  | 1.4627 | 765.9325 | 556.992 | 510.9928 | 33.6031 | 70.7229 | 1.7213 | 3.4505 | 620.4907 | 51.1913 | 5.6475 | 55.1293 | 566.1222 | 217.4445 | 12 | 51.7076 | 56.4082 | 82.353 | 108.9874 | Rajganj | 282.2
13 | Sadar | 78.7703 |  |  | 1090.6267 |  | 1.7161 | 1171.1131 | 596.969 | 840.075 | 59.5989 | 110.3933 | 31.0883 | 9.1585 | 1050.3141 |  | 9.5596 | 61.422 | 901.497 | 551.7063 | 14 | 75.0224 | 95.4831 | 79.9832 | 142.8476 | Sadar | 641.197
| Total | 656.384 | 0 | 0 | 18275.271 |  | 46.1941 | 18977.8491 | 14286.31 | 11618.8933 | 1048.5212 | 4824.1705 | 253.3071 | 206.2892 | 17951.1813 |  | 112.11 |  |  |  | 146 | 122.9533 | 1631.9256 | 64.725
1 | Line Deptt. | 44.3 |  |  | 98.15 |  | 0 | 142.45 |  | 9.96 | 2.66 | 17.72 | 0 | 0 | 30.34 | [5 empty] | 17521.9249 |  | 122.9533
2 | District Cell | 727.12 |  |  | 17700 | 1000 | 0 | 19427.12 |  | 0 | 0 | 0 | 53.61 | 4.01 | 57.62 |  | 57.61
| Total | 771.42 | 0 | 0 | 17700 | 1000 | 0 | 19569.57 |  | 9.96 | 2.66 | 17.72 | 53.61 | 4.01 | 87.96 |  | 53.61
| G.T. | 1427.804 | 0 | 0 | 17700 | 1000 | 46.1941 | 20173.9981 | 14286.31 | 11628.8533 | 1051.1812 | 4841.8905 | 306.9171 | 210.2992 | 18039.1413
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2013-14 Up to the Month of Feb 2014 | [19 empty] | Physical Performance Under NREGA During the year 2013-14 Up to the Month of Feb 2014 | [17 empty] | Physical Performance Under NREGA During the year 2013-14 Up to the Month of Feb 2014
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 1002 | 377609.3069 | 1222.6566 | 636 | 65354.1679 | 471.151 | 76 | 45222.3437 | 45.391 | 292 | 5.9004 | 83.2093 | 385 | 433.049 | 931.115 | 532 | 207.329 | 763.0013 | 649 | 297.0751 | 576.2432 | 478 | 172.4034 | 213.8709 | 241 | 20221.9822 | 206.9887 | 183 | 5254.6802 | 174.5733 | 1569 | 4210.156 | 1549.7918 | 886 | 2530.2932 | 570.9841 | 633 | 2580.3488 | 1714.6256 | 683 | 145.1709 | 1795.1745 | 1759 | 1679.7734 | 3435.6322 | 2219 | 618.3587 | 3185.3359 | 22 | 162 | 219.2786 | 165 | 1002 | 362.9024 | 6336 | 9901.7228 | 6074 | 7620.2029
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2013-14 Up to the Month of Feb 2014
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 598 | 0 | 0 | 8 | 582 | 16 | 0 | 9 | 3 | 0
2 | Alipurduar-II | 476 | 0 | 4 | 0 | 454 | 0 | 1 | 0 | 8 | 0
3 | Dhupguri | 3624.0344 | 14496.1377 | 876 | 9 | 0 | 0.1 | 0 | 1 | 12 | 12
4 | Falakata | 270 | 1793 | 1 | 11 | 0 | 440 | 3 | 2 | 0 | 2
5 | Kalchini | 695 | 115 | 7 | 15 | 0 | 4 | 16 | 15 | 0 | 0
6 | Kumargram | 2162 | 939 | 2 | 70 | 6 | 6 | 16 | 9 | 0 | 0
7 | Madarihat-Birpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Mal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Matiali | 0 | 33 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 1
10 | Maynaguri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
11 | Nagrakata | 4305 | 22 | 5 | 5 | 280 | 90 | 0 | 5 | 0 | 1
12 | Rajganj | 13940 | 1247 | 2 | 10 | 1266 | 65 |  |  | 0 | 0
13 | Sadar | 4859 | 120 | 0 | 14 | 229 | 54 | 0 | 28 | 0 | 0
| Total | 30929.0344 | 18765.1377 | 897 | 142 | 2817 | 680.1 | 36 | 69 | 25 | 16
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of Feb 2014)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 11 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of Feb 2014)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
Feb 2014
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
1 | Alipurduar-I | 5956 | 0 | 68.7629 | 42987 | 320 | 533.1376 | 601.9004 | 601.9004 | 0
2 | Alipurduar-II | 7895 | 36 | 33.4218 | 26404 | 45 | 686.3157 | 719.7374 | 719.7374 | 0
3 | Dhupguri | 9904 | 254 | 829.53 | 1059 | 3980 | 608.85 | 1438.38 | 1438.3793 | 0.00074
4 | Falakata | 15685 | 612 | 533.4568 | 41801 | 59 | 1132.2197 | 1665.6765 | 1665.6765 | 0
5 | Kalchini | 18947 | 297 | 467.0824 | 37542 | 2753 | 1114.4525 | 1581.5348 | 1581.5348 | 0
6 | Kumargram | 4791 | 1607 | 144.8354 | 30546 | 3458 | 838.0267 | 982.862 | 982.8655 | -0.00342
7 | Madarihat | 4356 | 10 | 103.1683 | 45223 | 739 | 824.0895 | 927.2578 | 927.2578 | 0
8 | Mal | 1279 | 8 | 0 | 32627 | 1377 | 762.4445 | 762.4445 | 762.44 | 0.00452
9 | Matiali | 0 | 0 | 0 | 52395 | 501 | 307.774 | 307.774 | 307.774 | 0
10 | Maynaguri | 6051 | 0 | 72.1063 | 61904 | 0 | 736.26 | 808.3663 | 808.3663 | 0
11 | Nagrakata | 3078 | 0 | 94.2965 | 23143 | 0 | 377.5967 | 471.8933 | 471.8933 | 0
12 | Rajganj | 3401 | 0 | 20.7706 | 54001 | 0 | 490.2222 | 510.9928 | 510.9928 | 0
13 | Sadar | 4056 | 0 | 40.954 | 59535 | 0 | 799.121 | 840.075 | 840.075 | 9.054e-07
| Line dep. |  |  | 0 |  |  | 9.96 | 9.96 | 9.96 | 0
Total |  | 85399 | 2824 | 2408.3949 | 509167 | 13232 | 9220.4602 | 11628.8551 | 11628.8533 | 0.0018409
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri