## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
part I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of Oct 2013 (for the financial year 2013-14)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals |  |  | 1.85
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 | 3 | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Alipurduar-I | 40434 | 20824 | 7801 | 11801 | 40426 | 3443 | 6934 | 3443 | 495 | 108181 | 0.11887 | 0.01616 | 0.08689 | 0.22192 | 0.101 | 0 | 0 | 149 | 3 | 0 | 6.4455
2 | Alipurduar-II | 45348 | 17364 | 5206 | 22778 | 45348 | 6522 | 8043 | 6522 | 713 | 123712 | 0.21801 | 0.09645 | 0.2971 | 0.61156 | 0.23285 | 0.2327 | 0 | 56 | 3 | 38.0748 | 9.3769
3 | Dhupguri | 78253 | 39732 | 15852 | 22586 | 78170 | 50811 | 33858 | 43915 | 880 | 572869 | 1.2172 | 0.08021 | 0.65141 | 1.9488 | 0.59274 | 0.00626 | 0 | 18 | 13 | 30.4155 | 4.4377
4 | Falakata | 53621 | 24296 | 9869 | 19456 | 53621 | 544 | 15775 | 644 | 328 | 223729 | 0.0038 | 0 | 0.00688 | 0.01068 | 0.00435 | 0.02 | 0 | 0 | 0 | 40.7303 | 1.6584
5 | Kalchini | 59033 | 8488 | 30139 | 19578 | 58205 | 13320 | 14637 | 13320 | 5879 | 204515 | 0.14942 | 0.83815 | 0.60773 | 1.5953 | 0.7146 | 0.0237 | 0 | 80 | 0 | 44.7941 | 11.9767
6 | Kumargram | 41941 | 15806 | 13195 | 12940 | 41941 | 29770 | 24120 | 26768 | 7909 | 328021 | 0.2254 | 0.09368 | 0.36984 | 0.68892 | 0.27065 | 0.25 | 0 | 143 | 8 | 39.2861 | 2.5737
7 | Madarihat | 39752 | 4891 | 11724 | 23137 | 39752 | 14635 | 15679 | 14635 | 0 | 221189 | 0.22395 | 0.49079 | 1.0868 | 1.8015 | 1.039 | 0.27893 | 3 | 1 | 4 | #REF! | #REF!
8 | Mal | 59222 | 18574 | 21679 | 18969 | 59222 | 1964 | 11989 | 1964 | 1163 | 174942 | 0.50608 | 0.16772 | 0.3901 | 1.0639 | 0.33388 | 0 | 0 | 0 | 0 | 62.0962 | 21.2104
9 | Matiali | 25454 | 6270 | 12097 | 7087 | 25454 | 6057 | 3947 | 6057 | 5530 | 59259 | 0.20064 | 0.49487 | 0.16519 | 0.8607 | 0.3564 | 0.00088 | 0 | 11 | 8 | 41.4082 | 14.21
10 | Maynaguri | 69587 | 47826 | 812 | 20932 | 69570 | 138.0056 | 7162 | 694 | 547 | 175323 | 0.04158 | 0.0003 | 0.01385 | 0.05573 | 0.02201 | 0.0002088 | 0 | 580 | 3 | 39.494 | 8.0303
11 | Nagrakata | 26629 | 4148 | 15432 | 6993 | 26573 | 8943 | 6361 | 4454 | 0 | 85236 | 0.035 | 0.06328 | 0.13269 | 0.23097 | 0.10223 | 0.06283 | 0 | 52 | 6 | 44.2612 | 5.1857
12 | Rajganj | 51403 | 29106 | 2466 | 19775 | 51347 | 2887 | 5744 | 2887 | 1292 | 99832 | 0.13293 | 0.026111 | 0.067149 | 0.22619 | 0.10508 | 0.12111 | 0 | 0 | 0 | 46.4561 | 7.8348
13 | Sadar | 60220 | 33908 | 3940 | 22372 | 60220 | 5156 | 7639 | 4632 | 3167 | 117162 | 0.12603 | 0.05947 | 0.09235 | 0.27785 | 0.08868 | 0.03654 | 0 | 0 | 0 | 31.9165 | 5.9985
| Total: | 650897 | 271233 | 150212 | 228404 | 649849 | 144190.0056 | 161888 | 129935 | 27903 | 2493970 | 3.1989 | 2.4272 | 3.9679 | 9.594 | 3.9634 | 1.0332 | 3 | 1090 | 48 | 41.3116 | 7.3837
1090
[15 empty] | District Programme Coordinator | [5 empty] | 0.27785
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2012-13 Up to the Month of Oct ' 2013
495.5042
Sl. No. | Name of the Block | Actual O.B. as on 01.04.13 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh) | [6 empty] | 1339.9314
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (10+11+12+13+14)
[13 empty] | Recurring | Non-Recurring |  |  | 4.32 |  |  |  |  | avg. gp
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | [8 empty] | WAGE% | PER LABOUR
1 | Alipurduar-I | 14.5029 |  |  | 681.156 |  | 1.0158 | 696.6747 | 280.068 | 399.4415 | 32.484 | 248.4463 | 24.8996 | 2.1511 | 707.4224 |  | 6.4387 | 27.8153 | 427.2568 | 395.2494 | 11 | 64.3111 | 64.3111 | 56.4644 | 1799.9347 | Alipurduar-I | 506.4504 | 680.3718
2 | Alipurduar-II | 19.8569 |  |  | 751.5908 |  | 2.1621 | 773.6099 | 324.993 | 402.9063 | 40.3707 | 239.2058 | 19.1061 | 10.1798 | 711.7687 |  | 6.4783 | 0 | 402.9063 | 556.075 | 11 | 64.7062 | 64.7062 | 56.6064 | 658.8174 | Alipurduar-II | 704.6012
3 | Dhupguri | 169.1634 |  |  | 1517.903 |  | 3.31 | 1690.3764 | 1501.413 | 794.0942 | 82.289 | 604.6887 | 10.021 | 8.7577 | 1499.8506 |  | 13.6511 | 87.8959 | 881.9901 | 946.3318 | 16 | 93.7407 | 136.3501 | 52.9449 | 407.4765 | Dhupguri | 831.2044
4 | Falakata | 24.2016 |  |  | 1064.0454 |  | 0.7272 | 1088.9742 | 616.46 | 587.2729 | 43.318 | 353.4732 | 7.2643 | 4.6026 | 995.931 |  | 9.0646 | 58.7232 | 645.9961 | 1457.4699 | 12 | 82.9942 | 90.5392 | 58.9672 | 54988.0964 | Falakata | 1512.1343
5 | Kalchini | 86.4572 |  |  | 1475.1795 |  | 4.2489 | 1565.8856 | 515.848 | 891.616 | 102.891 | 435.2387 | 18.8612 | 13.7813 | 1462.3882 |  | 13.3102 | 181.699 | 1073.315 | 1030.0591 | 11 | 132.9444 | 132.9444 | 60.9699 | 558.9018 | Kalchini | 866.6745
6 | Kumargram | 25.0465 |  |  | 1402.3264 |  | 4.9979 | 1432.3708 | 909.404 | 577.7173 | 103.1015 | 659.1126 | 21.0297 | 33.4644 | 1394.4255 |  | 12.6916 | 115.0446 | 692.7619 | 853.5048 | 11 | 126.766 | 126.766 | 41.4305 | 838.584 | Kumargram | 952.4868
7 | Madarihat | 21.262 |  |  | 869.6016 |  | 1.2315 | 892.0951 | 603.77 | 586.1514 | 50.7811 | 177.7297 | 8.715 | 14.6613 | 838.0385 |  | 7.6275 | 101.5239 | 687.6753 | 527.0331 | 10 | 83.8038 | 76.1853 | #REF! | #REF! | Madarihat-Birpara | 466.6014
8 | Mal | 37.7467 |  |  | 566.3315 |  | 0.54758 | 604.6259 | 462.603 | 348.6537 | 21.2925 | 121.1457 | 0.73094 | 3.6814 | 495.5042 |  | 4.5099 | 57.238 | 405.8917 | 394.9049 | 12 | 41.292 | 45.0458 | 70.3634 | 327.7128 | Malbazar | 402.7251
9 | Matiali | 26.9722 |  |  | 346.6859 |  | 0.36446 | 374.0225 | 153.273 | 223.6616 | 23.0213 | 68.5789 | 2.6871 | 2.007 | 319.9558 |  | 2.9121 | 22.2124 | 245.874 | 329.2062 | 5 | 63.9912 | 29.0869 | #REF! | #REF! | Matiali | 230.7365
10 | Maynaguri | 107.6975 |  |  | 714.2568 |  | 1.3564 | 823.3107 | 480.207 | 453.5038 | 34.7395 | 136.8281 | 15.1462 | 3.1418 | 643.3593 |  | 5.8556 | 26.4084 | 479.9122 | 421.4004 | 16 | 40.21 | 58.4872 | 70.49 | 8137.5159 | Maynaguri | 677.9344
11 | Nagrakata | 20.9906 |  |  | 465.5626 |  | 0.71568 | 487.2689 | 239.856 | 273.5491 | 25.8864 | 139.3297 | 1.3127 | 3.0906 | 443.1685 |  | 4.0336 | 11.7463 | 285.2953 | 284.0694 | 5 | 88.6337 | 40.288 | #REF! | #REF! | Nagrakata | 243.0925
12 | Rajganj | 23.7163 |  |  | 280.7373 |  | 0.72987 | 305.1835 | 245.149 | 184.8524 | 15.1875 | 50.5074 | 0.51789 | 1.6817 | 252.747 | 51.1913 | 2.3004 | 13.4704 | 198.3229 | 217.4445 | 12 | 21.0622 | 22.977 | 73.1373 | 817.2441 | Rajganj | 282.2
13 | Sadar | 78.7703 |  |  | 643.213 |  | 0.85497 | 722.8382 | 288.028 | 497.9213 | 40.5145 | 98.9135 | 17.0791 | 4.0367 | 658.4651 |  | 5.9931 | 24.1737 | 522.095 | 551.7063 | 14 | 47.0332 | 59.8605 | 75.6185 | 1792.0508 | Sadar | 641.197
| Total | 656.384 | 0 | 0 | 10778.5899 |  | 22.2624 | 11457.2363 | 6621.072 | 6221.3415 | 615.8769 | 3333.1983 | 147.3708 | 105.2372 | 10423.0247 |  | 59.11 |  |  |  | 146 | 71.3906 | 947.5477 | 59.6884
1 | Line Deptt. | 44.3 |  |  | 45.15 |  | 0 | 89.45 |  | 9.96 | 2.66 | 17.72 | 0 | 0 | 30.34 | [5 empty] | 10200.7567 |  | 71.3906
2 | District Cell | 727.12 |  |  | 15200 |  | 0 | 15927.12 |  | 0 | 0 | 0 | 36.42 | 2.89 | 39.31
| Total | 771.42 | 0 | 0 | 15200 | 0 | 0 | 16016.57 |  | 9.96 | 2.66 | 17.72 | 36.42 | 2.89 | 69.65
| G.T. | 1427.804 | 0 | 0 | 15200 | 0 | 22.2624 | 16650.0664 | 6621.072 | 6231.3015 | 618.5369 | 3350.9183 | 183.7908 | 108.1272 | 10492.6747
District Programme Coordinator
[13 empty] | MGNREGS, Jalpaiguri |  | 10200.7567
&
District Magistrate
Jalpaiguri

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2013-14 Up to the Month of Oct 2013 | [19 empty] | Physical Performance Under NREGA During the year 2013-14 Up to the Month of Oct 2013 | [17 empty] | Physical Performance Under NREGA During the year 2013-14 Up to the Month of Oct 2013
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 421 | 138734.5373 | 623.0509 | 333 | 85237.131 | 326.2249 | 35 | 12 | 14.1568 | 280 | 0.000349 | 43.8813 | 134 | 67.2728 | 320.5659 | 244 | 95.9553 | 322.5497 | 281 | 203.6985 | 278.9785 | 185 | 17.0152 | 34.2269 | 204 | 18477.819 | 113.7983 | 112 | 4469.8642 | 94.5536 | 854 | 354.3145 | 951.3571 | 502 | 2899.8655 | 359.4999 | 284 | 1507.0164 | 798.9672 | 537 | 691.3856 | 1207.7492 | 1037 | 1374.1786 | 2403.2918 | 1105 | 559.7945 | 2018.1928 | 15 | 162 | 162.5519 | 65 | 1002 | 127.1568 | 3265 | 5666.7184 | 3363 | 4534.035
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2013-14 Up to the Month of Oct 2013
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 330 | 0 | 0 | 4 | 330 | 0 | 0 | 9 | 0 | 0
2 | Alipurduar-II | 372 | 0 | 4 | 0 | 380 | 0 | 1 | 0 | 8 | 0
3 | Dhupguri | 2000.7412 | 8002.9649 | 435 | 9 | 0 | 0.1 | 0 | 1 | 12 | 12
4 | Falakata | 0 | 0 | 8 | 0 | 0 | 0.02 | 0 | 1 | 0 | 0
5 | Kalchini | 0 | 0 | 4 | 4 | 0 | 3 | 16 | 5 | 0 | 0
6 | Kumargram | 621 | 1081 | 1 | 3 | 6 | 6 | 10 | 1 | 0 | 0
7 | Madarihat-Birpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Mal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Matiali | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10 | Maynaguri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
11 | Nagrakata | 1054 | 22 | 7 | 3 | 165 | 68 | 5 | 0 | 0 | 1
12 | Rajganj | 13940 | 1247 | 2 | 10 | 1266 | 65 |  |  | 0 | 0
13 | Sadar | 710 | 0 | 11 | 3 | 47 | 0 | 14 | 0 | 0 | 0
| Total | 19027.7412 | 10352.9649 | 472 | 36 | 2194 | 142.12 | 46 | 17 | 22 | 14
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of Oct 2013)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 11 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of Oct 2013)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
Oct 2013
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
1 | Alipurduar-I | 5956 | 0 | 50.3592 | 42987 | 320 | 349.0823 | 399.4415 | 399.4415 | 0
2 | Alipurduar-II | 7895 | 36 | 28.5248 | 26404 | 45 | 374.3815 | 402.9063 | 402.9063 | 0
3 | Dhupguri | 798 | 654 | 449.9 | 1059 | 3980 | 344.19 | 794.09 | 794.0942 | -0.00419
4 | Falakata | 15985 | 612 | 201.2375 | 41801 | 59 | 386.0353 | 587.2729 | 587.2729 | 0
5 | Kalchini | 18440 | 296 | 258.9705 | 37747 | 2885 | 632.6455 | 891.616 | 891.616 | 0
6 | Kumargram | 4791 | 1607 | 72.7841 | 30546 | 3425 | 504.931 | 577.7151 | 577.7173 | -0.00217
7 | Madarihat | 2915 | 10 | 43.6936 | 42887 | 739 | 542.4579 | 586.1514 | 586.1514 | 0
8 | Mal | 1279 | 8 | 0 | 32627 | 1377 | 348.6537 | 348.6537 | 348.6537 | 0
9 | Matiali | 0 | 0 | 0 | 52395 | 501 | 223.6605 | 223.6605 | 223.6616 | -0.00114
10 | Maynaguri | 6051 | 0 | 40.4525 | 61904 | 0 | 413.0512 | 453.5038 | 453.5038 | 0
11 | Nagrakata | 3078 | 0 | 46.6552 | 29453 | 0 | 226.8939 | 273.5491 | 273.5491 | 0
12 | Rajganj | 3167 | 0 | 4.1276 | 53316 | 0 | 180.7248 | 184.8524 | 184.8524 | 0
13 | Sadar | 3676 | 0 | 21.9877 | 59535 | 0 | 475.9336 | 497.9213 | 497.9213 | 9.054e-07
| Line dep. |  |  | 0 |  |  | 9.96 | 9.96 | 9.96 | 0
Total |  | 74031 | 3223 | 1218.7028 | 512661 | 13331 | 5012.5912 | 6231.294 | 6231.3015 | -0.0074991
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri