## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
Part - I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of November 2014 (for the financial year 2014-15)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals |  |  | 1.85
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 | 3 | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Dhupguri | 81308 | 39729 | 16111 | 23803 | 79643 | 88915 | 37246 | 33459 | 34573 | 630154 | 1.5394 | 0.94882 | 2.4276 | 4.9159 | 1.6866 | 0 | 0 | 18 | 13 | 34.3083 | 14.6923
2 | Mal | 59222 | 18574 | 21679 | 18969 | 59222 | 18576 | 13188 | 18440 | 10044 | 192438 | 1.0051 | 1.3443 | 2.2846 | 4.634 | 1.6812 | 0 | 0 | 0 | 0 | 62.0962 | 21.2104
3 | Matiali | 25693 | 5715 | 11476 | 8437 | 25628 | 15623 | 4333 | 15623 | 3765 | 65183 | 0.40191 | 0.89329 | 0.97399 | 2.2692 | 1.1206 | 0 | 5 | 21 | 13 | 49.3824 | 14.5247
4 | Maynaguri | 70830 | 45575 | 817 | 24359 | 70751 | 24465 | 7658 | 22453 | 2208 | 192855 | 2.4433 | 0.05232 | 1.7435 | 4.2391 | 1.5852 | 0.011277 | 0 | 12 | 0 | 37.3932 | 18.8801
5 | Nagrakata | 27087 | 4299 | 15529 | 7203 | 27031 | 15159 | 7635 | 15139 | 415 | 101454 | 0.7159 | 1.1971 | 0.49553 | 2.4085 | 1.1227 | 0.15023 | 0 | 71 | 7 | 46.6153 | 15.9094
6 | Rajganj | 51850 | 28046 | 2207 | 21573 | 51826 | 12258 | 6318 | 12258 | 2156 | 109815 | 0.89723 | 0.04603 | 1.384 | 2.3272 | 1.1243 | 0.66797 | 2 | 15 | 0 | 48.3128 | 18.9854
7 | Sadar | 62033 | 33976 | 4063 | 23994 | 62033 | 15548 | 8404 | 14172 | 3301 | 128879 | 1.274 | 0.1219 | 1.0311 | 2.427 | 0.88829 | 0.11769 | 4 | 103 | 9 | 36.6003 | 17.1253
| Total: | 378023 | 175914 | 71882 | 128338 | 376134 | 190544 | 84782 | 131544 | 56462 | 1420778 | 8.2769 | 4.6037 | 10.3404 | 23.221 | 9.2089 | 0.94717 | 11 | 240 | 42 | 39.6575 | 17.6526
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2014-15 Up to the Month of November ' 2014
865.0179
Sl. No. | Name of the Block | Actual O.B. as on 01.04.14 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Authorisation of EFMS | Total Availability | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh) | [6 empty] | #REF!
|  |  | Central | State | Central | State |  |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (10+11+12+13+14)
[14 empty] | Recurring | Non-Recurring |  |  | 4.32 |  |  |  |  | avg. gp
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | [8 empty] | WAGE% | PER LABOUR
1 | Dhupguri | 29.1483 |  |  | 2199.47 |  | 8.3822 | 145.9 | 2382.9005 | 1651.554 | 1632.6884 | 120.8451 | 202.0057 | 9.8236 | 7.1646 | 1972.5275 |  | 17.9533 | #REF! | #REF! | 946.3318 | 16 | 123.283 | 179.3207 | 82.7714 | 332.1247 | Dhupguri | 831.2044
2 | Mal | 12.7201 |  |  | 866.75 |  | 0 | 84.77 | 964.2401 | 508.863 | 707.5789 | 54.007 | 76.862 | 25.09 | 1.48 | 865.0179 |  | 7.8731 | #REF! | #REF! | 394.9049 | 12 | 72.0848 | 78.638 | 81.7993 | 152.6922 | Malbazar | 402.7251
3 | Matiali | 15.5383 |  |  | 582.82 |  | 0.37129 | 54.16 | 652.8896 | 168.6 | 510.2261 | 38.6994 | 58.1349 | 4.885 | 4.6039 | 616.5492 |  | 5.6116 | #REF! | #REF! | 329.2062 | 5 | 123.3098 | 56.0499 | 82.7551 | #REF! | Matiali | 230.7365
4 | Maynaguri | 39.4891 |  |  | 902.7 |  | 1.2281 | 195.65 | 1139.0671 | 528.228 | 748.1684 | 45.8589 | 71.3709 | 17.6453 | 7.3296 | 890.3731 |  | 8.1039 | 63.8027 | 811.971 | 421.4004 | 16 | 55.6483 | 80.943 | 84.0286 | 176.4906 | Maynaguri | 677.9344
5 | Nagrakata | 6.0022 |  |  | 599.78 |  | 0.78223 | 34.14 | 640.7044 | 286.131 | 466.8782 | 31.6788 | 103.2413 | 12.8057 | 7.012 | 621.6159 |  | 5.6577 | 31.7491 | 498.6273 | 284.0694 | 5 | 124.3232 | 56.5105 | 75.1072 | #REF! | Nagrakata | 243.0925
6 | Rajganj | 13.8428 |  |  | 532.63 |  | 1.2376 | 107.18 | 654.8904 | 269.664 | 488.9575 | 33.3796 | 48.7825 | 4.6992 | 5.1017 | 580.9204 | 51.1913 | 5.2873 | 42.848 | 531.8054 | 217.4445 | 12 | 48.41 | 52.8109 | 84.1694 | 210.1028 | Rajganj | 282.2
7 | Sadar | 36.2088 |  |  | 985.21 |  | 2.3235 | 155.84 | 1179.5822 | 316.381 | 1011.0541 | 59.6169 | 32.4413 | 23.7146 | 7.2142 | 1134.041 |  | 10.3217 | 58.3973 | 1069.4514 | 551.7063 | 14 | 81.0029 | 103.0946 | 89.155 | 416.586 | Sadar | 641.197
| Total | 152.9495 | 0 | 0 | 6669.36 | 0 | 14.3249 | 777.64 | 7614.2743 | 3729.421 | 5565.5515 | 384.0856 | 592.8386 | 98.6633 | 39.906 | 6681.045 |  | 37.7187 |  |  |  | 80 | 83.5131 | 607.3677 | 83.3036
1 | Line Deptt. | 28.3699 |  |  | 127.89 |  |  |  | 156.2599 | 0 | 96.9224 | 7.0344 | 14.1144 | 0.47 | 0 | 118.5412 |  | 6542.4757 |  |  |  | 6660.5469 |  | 45.7606
2 | District Cell | 1072.1861 |  |  | 11500 | 1525 |  |  | 14097.1861 |  |  |  |  | 28.72 | 4.57 | 33.29
| Total |  |  |  | 11500 |  |  |  | 14253.4459 |  | 96.9224 | 7.0344 | 14.1144 | 29.19 | 4.57 | 151.8312
G.T. |  | 1253.5054 | 0 | 0 | 11500 | 1525 | 14.3249 | 777.64 | 15070.4703 | 3729.421 | 5662.4739 | 391.12 | 606.953 | 127.8533 | 44.476 | 6832.8762
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2014-15 Up to the Month of November 2014 | [19 empty] | Physical Performance Under NREGA During the year 2014-15 Up to the Month of November 2014 | [17 empty] | Physical Performance Under NREGA During the year 2014-15 Up to the Month of November 2014
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 83 | 262030.8425 | 388.4599 | 192 | 26652.2106 | 140.9149 | 83 | 10870.2993 | 146.1602 | 254 | 29.89 | 79.1634 | 183 | 297 | 493.761 | 311 | 55.93 | 335.5537 | 163 | 169.2787 | 188.9138 | 560 | 45.0886 | 136.2517 | 70 | 28988.6139 | 113.067 | 80 | 760.9717 | 51.3707 | 369 | 459.53 | 595.6519 | 361 | 134.13 | 329.0962 | 131 | 1428.467 | 376.5013 | 279 | 62.1565 | 366.994 | 555 | 674.2071 | 1127.6802 | 615 | 450.1858 | 1054.2438 | 16 | 409.6 | 379.101 | 147 | 648 | 357.6621 | 1653 | 3809.2964 | 2799 | 2851.2505
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2014-15 Up to the Month of November 2014
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Dhupguri | 4113.6014 | 16454.4057 | 16 | 16 | 0 | 0.1 | 0 | 1 | 12 | 12
2 | Mal | 0 | 108 | 12 | 12 | 0 | 29 | 0 | 0 | 0 | 0
3 | Matiali | 0 | 33 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 1
4 | Maynaguri | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 2 | 0
5 | Nagrakata | 2323 | 545 | 5 | 5 | 101 | 70 | 5 | 0 | 0 | 0
6 | Rajganj | 13940 | 1247 | 12 | 12 | 1266 | 65 |  |  | 0 | 0
7 | Sadar | 4084 | 659 | 14 | 14 | 341 | 52 | 0 | 28 | 0 | 0
| Total | 24460.6014 | 19046.4057 | 80 | 80 | 1708 | 221.1 | 5 | 29 | 14 | 13
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of Nomber 2014)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 103 | 85 | 7 | 7 | 8 | 7 | 7 | 7 | 7 | 6 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri
0

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of November 2014)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 67 | 67 | 7 | 7 | 6 | 15 | 0 | 7 | 0 | 6 | 5 | 5 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 1 | 578 | 718 | 17 | 17
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
November 2014
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
3 | Dhupguri | 12920 | 0 | 954.51 | 34220 | 250 | 678.18 | 1632.69 | 1632.6884 | 0.00159
8 | Mal | 1279 | 8 | 0 | 32627 | 1377 | 707.5789 | 707.5789 | 707.5789 | 0
9 | Matiali | 1500 | 0 | 10 | 52395 | 501 | 500.2261 | 510.2261 | 510.2261 | 0
10 | Maynaguri | 29813 | 0 | 375.0568 | 29360 | 0 | 373.1116 | 748.1684 | 748.1684 | 0
11 | Nagrakata | 3112 | 0 | 99.2789 | 29038 | 0 | 367.5993 | 466.8782 | 466.8782 | 0
12 | Rajganj | 4331 | 0 | 48.6492 | 51097 | 0 | 440.3082 | 488.9575 | 488.9575 | 0
13 | Sadar | 17039 | 225 | 345.18 | 53037 | 597 | 665.8741 | 1011.0541 | 1011.0541 | 0
| Line dep. |  |  | 0 | 96.9224 | 0 | 96.9224 | 96.9224 | 96.9224 | 0
Total |  | 69994 | 233 | 1832.6849 | 281774 | 2725 | 3829.7906 | 5662.4755 | 5662.4739 | 0.00159
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri