## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
Part - I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of September 2014 (for the financial year 2014-15)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals |  |  | 1.85
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 | 3 | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Dhupguri | 78323 | 38744 | 15853 | 23715 | 78312 | 88915 | 32439 | 33459 | 34573 | 513882 | 1.2469 | 0.67454 | 1.8636 | 3.7851 | 1.9859 | 0 | 0 | 18 | 13 | 52.4657 | 11.3127
2 | Mal | 59222 | 18574 | 21679 | 18969 | 59222 | 18576 | 11826 | 18440 | 10044 | 160082 | 0.56555 | 0.65215 | 1.2205 | 2.4382 | 0.94477 | 0 | 0 | 0 | 0 | 62.0962 | 21.2104
3 | Matiali | 25693 | 5715 | 11476 | 8437 | 25628 | 15623 | 3791 | 15623 | 3765 | 53037 | 0.40191 | 0.89329 | 0.97399 | 2.2692 | 1.1206 | 0 | 5 | 21 | 13 | 49.3824 | 14.5247
4 | Maynaguri | 70830 | 45575 | 817 | 24359 | 70751 | 21515 | 6306 | 19834 | 7699 | 155859 | 2.0779 | 0.04578 | 1.5358 | 3.6594 | 1.9473 | 0.0071484 | 0 | 12 | 0 | 53.2135 | 18.4503
5 | Nagrakata | 27087 | 4299 | 15529 | 7203 | 27031 | 14334 | 6129 | 14334 | 2017 | 83001 | 0.59819 | 1.1043 | 0.38054 | 2.083 | 0.99978 | 0.14368 | 0 | 71 | 7 | 47.9967 | 14.532
6 | Rajganj | 51850 | 28014 | 2207 | 21573 | 51794 | 11362 | 5342 | 11362 | 5392 | 84837 | 0.78208 | 0.04403 | 1.1974 | 2.0235 | 0.97242 | 0.62797 | 2 | 15 | 0 | 48.0554 | 17.8097
7 | Sadar | 62019 | 33976 | 4063 | 23994 | 62033 | 12729 | 7363 | 11577 | 5318 | 99663 | 0.84597 | 0.11172 | 0.68705 | 1.6447 | 0.58675 | 0.11769 | 1 | 76 | 5 | 35.6743 | 14.207
| Total: | 375024 | 174897 | 71624 | 128250 | 374771 | 183054 | 73196 | 124629 | 68808 | 1150361 | 6.5185 | 3.5258 | 7.8589 | 17.9032 | 8.5575 | 0.89649 | 8 | 213 | 38 | 47.7987 | 14.3652
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2014-15 Up to the Month of September ' 2014
861.3279
Sl. No. | Name of the Block | Actual O.B. as on 01.04.14 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Authorisation of EFMS | Total Availability | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh) | [6 empty] | #REF!
|  |  | Central | State | Central | State |  |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (10+11+12+13+14)
[14 empty] | Recurring | Non-Recurring |  |  | 4.32 |  |  |  |  | avg. gp
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | [8 empty] | WAGE% | PER LABOUR
1 | Dhupguri | 29.1483 |  |  | 2268.271 |  | 8.3822 | 147.95 | 2453.7515 | 1382.477 | 1577.6884 | 120.8451 | 202.0057 | 9.8236 | 7.1646 | 1917.5275 |  | 17.4527 | #REF! | #REF! | 946.3318 | 16 | 119.8455 | 174.3207 | 82.2772 | 416.8155 | Dhupguri | 831.2044
2 | Mal | 12.7201 |  |  | 861.8 |  | 0 | 85.31 | 959.8301 | 423.943 | 707.5789 | 54.007 | 76.862 | 21.4 | 1.48 | 861.3279 |  | 7.8395 | #REF! | #REF! | 394.9049 | 12 | 71.7773 | 78.3025 | 82.1498 | 290.2102 | Malbazar | 402.7251
3 | Matiali | 15.5383 |  |  | 580.2 |  | 0.37129 | 55.64 | 651.7496 | 140.468 | 510.2261 | 38.6994 | 58.1349 | 4.885 | 4.6039 | 616.5492 |  | 5.6116 | #REF! | #REF! | 329.2062 | 5 | 123.3098 | 56.0499 | #REF! | #REF! | Matiali | 230.7365
4 | Maynaguri | 39.4891 |  |  | 897.67 |  | 1.2281 | 196.59 | 1134.9771 | 414.138 | 731.9537 | 45.3912 | 66.2151 | 17.1277 | 7.0768 | 867.7646 |  | 7.8981 | 61.9173 | 793.871 | 421.4004 | 16 | 54.2353 | 78.8877 | 84.3493 | 200.0185 | Maynaguri | 677.9344
5 | Nagrakata | 6.0022 |  |  | 615.7166 |  | 0.70147 | 34.14 | 656.5602 | 219.813 | 457.2697 | 31.4988 | 103.2093 | 10.3411 | 6.3835 | 608.7023 |  | 5.5402 | 31.0896 | 488.3593 | 284.0694 | 5 | 121.7405 | 55.3366 | #REF! | #REF! | Nagrakata | 243.0925
6 | Rajganj | 13.8428 |  |  | 529.4 |  | 1.1476 | 109.11 | 653.5004 | 224.673 | 473.3672 | 32.0726 | 47.5615 | 4.4629 | 4.5818 | 562.0459 | 51.1913 | 5.1156 | 40.4032 | 513.7704 | 217.4445 | 12 | 46.8372 | 51.0951 | 84.2222 | 233.9302 | Rajganj | 282.2
7 | Sadar | 36.2088 |  |  | 1010.105 |  | 2.3235 | 159.38 | 1208.0172 | 263.938 | 812.5188 | 48.7584 | 31.3626 | 19.6284 | 7.6808 | 919.9491 |  | 8.3731 | 46.3885 | 858.9074 | 551.7063 | 14 | 65.7106 | 83.6317 | 88.3222 | 494.0105 | Sadar | 641.197
| Total | 152.9495 | 0 | 0 | 6763.1626 | 0 | 14.1541 | 788.12 | 7718.3862 | 3069.45 | 5270.6028 | 371.2725 | 585.351 | 87.6687 | 38.9714 | 6353.8665 |  | 37.7187 |  |  |  | 80 | 79.4233 | 577.6242 | 82.9511
1 | Line Deptt. | 28.3699 |  |  | 127.89 |  |  |  | 156.2599 | 0 | 96.9224 | 7.0344 | 14.1144 | 0.47 | 0 | 118.5412 |  | 6227.2263 |  |  |  | 6345.2975 |  | 43.5196
2 | District Cell | 1072.1861 |  |  | 11500 | 1525 |  |  | 14097.1861 |  |  |  |  | 19.62 | 4.24 | 23.86
| Total |  |  |  | 11500 |  |  |  | 14253.4459 |  | 96.9224 | 7.0344 | 14.1144 | 20.09 | 4.24 | 142.4012
G.T. |  | 1253.5054 | 0 | 0 | 11500 | 1525 | 14.1541 | 788.12 | 15080.7795 | 3069.45 | 5367.5252 | 378.3068 | 599.4655 | 107.7587 | 43.2114 | 6496.2676
6345.2975
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2014-15 Up to the Month of September 2014 | [19 empty] | Physical Performance Under NREGA During the year 2014-15 Up to the Month of September 2014 | [17 empty] | Physical Performance Under NREGA During the year 2014-15 Up to the Month of September 2014
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 83 | 262030.8425 | 388.4599 | 192 | 26652.2106 | 140.9149 | 70 | 10867.7993 | 144.8111 | 257 | 24.49 | 70.2009 | 147 | 274.5002 | 415.3034 | 313 | 58.59 | 320.0599 | 142 | 169.2787 | 166.9187 | 581 | 45.0886 | 153.8091 | 70 | 28988.6139 | 113.067 | 80 | 760.9717 | 51.3707 | 369 | 459.2403 | 563.1614 | 337 | 132.2632 | 248.9657 | 131 | 1428.467 | 376.5013 | 272 | 62.1565 | 353.8835 | 515 | 616.2404 | 1103.9452 | 603 | 441.3958 | 1030.035 | 9 | 359.6 | 379.101 | 106 | 608 | 324.8973 | 1536 | 3651.269 | 2741 | 2694.028
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2014-15 Up to the Month of September 2014
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Dhupguri | 3975.0275 | 15900.11 | 344 | 9 | 0 | 0.1 | 0 | 1 | 12 | 12
2 | Mal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Matiali | 0 | 33 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 1
4 | Maynaguri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
5 | Nagrakata | 1864 | 545 | 6 | 4 | 73 | 70 | 5 | 0 | 0 | 0
6 | Rajganj | 13940 | 1247 | 2 | 10 | 1266 | 65 |  |  | 0 | 0
7 | Sadar | 11068 | 659 | 20 | 14 | 341 | 52 | 0 | 28 | 0 | 0
| Total | 30847.0275 | 18384.11 | 372 | 37 | 1680 | 192.1 | 5 | 29 | 14 | 13
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of September 2014)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 103 | 81 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of August 2014)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 67 | 67 | 7 | 7 | 0 | 7 | 0 | 7 | 0 | 6 | 5 | 5 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 1 | 578 | 718 | 17 | 17
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
August 2014
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
3 | Dhupguri | 12920 | 0 | 909.51 | 34220 | 250 | 668.18 | 1577.69 | 1577.6884 | 0.00159
8 | Mal | 1279 | 8 | 0 | 32627 | 1377 | 707.5789 | 707.5789 | 707.5789 | 0
9 | Matiali | 0 | 0 | 0 | 52395 | 501 | 510.2261 | 510.2261 | 510.2261 | 0
10 | Maynaguri | 6051 | 0 | 65.2903 | 61904 | 0 | 666.6634 | 731.9537 | 731.9537 | 0
11 | Nagrakata | 3112 | 0 | 90.2065 | 29038 | 0 | 367.0632 | 457.2697 | 457.2697 | 0
12 | Rajganj | 4331 | 0 | 39.4548 | 51097 | 0 | 433.9124 | 473.3672 | 473.3672 | 0
13 | Sadar | 4056 | 0 | 81.5521 | 59535 | 0 | 730.9668 | 812.5188 | 812.5188 | 0
| Line dep. |  |  | 0 | 96.9224 | 0 | 96.9224 | 96.9224 | 96.9224 | 0
Total |  | 31749 | 8 | 1186.0237 | 320816 | 2128 | 4181.5031 | 5367.5268 | 5367.5252 | 0.00159
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri