## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
part I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of May 2014 (for the financial year 2014-15)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals |  |  | 1.85
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 | 3 | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Alipurduar-I | 40870 | 21013 | 7904 | 11945 | 40862 | 0 | 704 | 0 | 0 | 7530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
2 | Alipurduar-II | 46392 | 17723 | 5158 | 23511 | 46392 | 0 | 815 | 0 | 0 | 8772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
3 | Dhupguri | 78323 | 39846 | 15853 | 22586 | 78285 | 0 | 3182 | 0 | 0 | 40060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
4 | Falakata | 55934 | 24384 | 10260 | 21192 | 55836 | 0 | 1545 | 0 | 0 | 16338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
5 | Kalchini | 60440 | 8550 | 29137 | 22080 | 59767 | 0 | 1380 | 0 | 0 | 14967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
6 | Kumargram | 43114 | 16971 | 13268 | 12875 | 43114 | 0 | 2283 | 0 | 0 | 24661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
7 | Madarihat | 40076 | 4934 | 12064 | 23078 | 40076 | 158 | 1513 | 0 | 0 | 16376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #REF!
8 | Mal | 59222 | 18574 | 21679 | 18969 | 59222 | 3013 | 1159 | 3013 | 3013 | 12542 | 0.00523 | 0.00308 | 0.00057 | 0.00888 | 0 | 0 | 0 | 0 | 0 | 62.0962 | 21.2104
9 | Matiali | 25604 | 6567 | 12139 | 6986 | 25637 | 200 | 381 | 200 | 0 | 4152 | 0 | 0 | 0 | 0 | 0 | 0.00088 | 0 | 0 | 0 | #DIV/0! | 0
10 | Maynaguri | 71083 | 46016 | 690 | 24298 | 71004 | 0 | 333 | 0 | 0 | 11734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
11 | Nagrakata | 27087 | 4299 | 15529 | 7203 | 27031 | 0 | 598 | 0 | 0 | 6502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
12 | Rajganj | 51850 | 28014 | 2207 | 21573 | 51794 | 0 | 615 | 0 | 0 | 6646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
13 | Sadar | 62019 | 33976 | 4063 | 23980 | 62019 | 0 | 724 | 0 | 0 | 7810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0!
| Total: | 662014 | 270867 | 149951 | 240276 | 661039 | 3371 | 15232 | 3213 | 3013 | 178090 | 0.00523 | 0.00308 | 0.00057 | 0.00888 | 0 | 0.00088 | 0 | 0 | 0 | 0 | 0.27638
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2014-15 Up to the Month of May ' 2014
479.8159
Sl. No. | Name of the Block | Actual O.B. as on 01.04.13 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Total Availability | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh) | [6 empty] | 834.0809
|  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (10+11+12+13+14)
[13 empty] | Recurring | Non-Recurring |  |  | 4.32 |  |  |  |  | avg. gp
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | [8 empty] | WAGE% | PER LABOUR
1 | Alipurduar-I | 7.5954 |  |  | 559.71 |  | 0 | 567.3054 | 20.156 | 333.9334 | 16.216 | 61.9302 | 6.1749 | 2.2025 | 420.4572 |  | 3.8269 | 16.532 | 350.4655 | 395.2494 | 11 | 38.2234 | 38.2234 | 79.4215 | #DIV/0! | Alipurduar-I | 506.4504 | 412.0797
2 | Alipurduar-II | 17.2285 |  |  | 696.18 |  | 0.65143 | 714.0599 | 23.38 | 333.4699 | 19.4307 | 81.273 | 1.0663 | 1.9205 | 437.1605 |  | 3.9789 | 0 | 333.4699 | 556.075 | 11 | 39.7419 | 39.7419 | 76.2809 | #DIV/0! | Alipurduar-II | 704.6012
3 | Dhupguri | 16.818 |  |  | 1373.98 |  | 0 | 1390.798 | 106.878 | 680.1204 | 80.4363 | 57.5983 | 3.5151 | 1.2676 | 822.9376 |  | 7.4901 | 28.6636 | 708.784 | 946.3318 | 16 | 51.4336 | 74.8125 | 82.6454 | #DIV/0! | Dhupguri | 831.2044
4 | Falakata | 19.3759 |  |  | 922.74 |  | 1.0182 | 943.1341 | 44.353 | 544.4786 | 26.9592 | 31.8317 | 2.707 | 3.8053 | 609.7817 |  | 5.55 | 22.0829 | 566.5615 | 1457.4699 | 12 | 50.8151 | 55.4347 | 89.2907 | #DIV/0! | Falakata | 1512.1343
5 | Kalchini | 11.8702 |  |  | 868.35 |  | 0 | 880.2202 | 39.701 | 520.1112 | 34.891 | 98.3663 | 5.906 | 3.9479 | 663.2224 |  | 6.0364 | 45.2135 | 565.3246 | 1030.0591 | 11 | 60.2929 | 60.2929 | 78.4218 | #DIV/0! | Kalchini | 866.6745
6 | Kumargram | 6.7525 |  |  | 973.36 |  | 1.0054 | 981.1179 | 65.028 | 411.0842 | 94.279 | 328.7177 | 8.601 | 5.3122 | 847.9942 |  | 7.7182 | 42.836 | 453.9202 | 853.5048 | 11 | 77.0904 | 77.0904 | 48.4772 | #DIV/0! | Kumargram | 952.4868
7 | Madarihat | 30.778 |  |  | 602.45 |  | 0 | 633.228 | 43.425 | 348.1283 | 14.6626 | 32.7317 | 1.14 | 4.5932 | 401.2558 |  | 3.6521 | 22.0456 | 370.1739 | 527.0331 | 10 | 40.1256 | 36.4778 | #REF! | #REF! | Madarihat-Birpara | 466.6014
8 | Mal | 10.2451 |  |  | 609.52 |  | 0 | 619.7651 | 33.282 | 414.8579 | 13.138 | 44.66 | 6.32 | 0.84 | 479.8159 |  | 4.3671 | 33.7062 | 448.564 | 394.9049 | 12 | 39.9847 | 43.6196 | 86.4619 | 46718.2286 | Malbazar | 402.7251
9 | Matiali | 6.0934 |  |  | 438.12 |  | 0 | 444.2134 | 11.029 | 229.9889 | 19.3525 | 13.9569 | 0.64584 | 0.48716 | 264.4314 |  | 2.4068 | 8.7897 | 238.7787 | 329.2062 | 5 | 52.8863 | 24.0392 | #REF! | #REF! | Matiali | 230.7365
10 | Maynaguri | 25.43 |  |  | 660.1 |  | 0.4709 | 686.0009 | 32.111 | 394.9798 | 20.0555 | 24.3808 | 3.9621 | 0.85706 | 444.2353 |  | 4.0433 | 17.6575 | 412.6373 | 421.4004 | 16 | 27.7647 | 40.385 | 88.9123 | #DIV/0! | Maynaguri | 677.9344
11 | Nagrakata | 5.5276 |  |  | 446.02 |  | 0 | 451.5476 | 17.256 | 290.4742 | 25.6131 | 51.6652 | 0.35979 | 0.76105 | 368.8733 |  | 3.3574 | 8.0804 | 298.5546 | 284.0694 | 5 | 73.7747 | 33.5339 | #REF! | #REF! | Nagrakata | 243.0925
12 | Rajganj | 18.3455 |  |  | 446.2 |  | 0.84 | 465.3856 | 17.636 | 263.4142 | 14.0441 | 18.7581 | 3.7554 | 0.90157 | 300.8733 | 51.1913 | 2.7384 | 11.0723 | 274.4866 | 217.4445 | 12 | 25.0728 | 27.3521 | 87.5499 | #DIV/0! | Rajganj | 282.2
13 | Sadar | 35.5001 |  |  | 787.88 |  | 1.0628 | 824.4429 | 20.717 | 629.9403 | 18.2106 | 15.8385 | 6.7435 | 5.0786 | 675.8115 |  | 6.151 | 20.6512 | 650.5914 | 551.7063 | 14 | 48.2722 | 61.4374 | 93.2124 | #DIV/0! | Sadar | 641.197
| Total | 211.5601 | 0 | 0 | 9384.61 |  | 5.0488 | 9601.2189 | 474.952 | 5394.9812 | 397.2888 | 861.7084 | 50.8969 | 31.9747 | 6736.85 |  | 125.83 |  |  |  | 146 | 46.1428 | 612.4409 | 80.0817
1 | Line Deptt. | 45.61 |  |  | 90 |  |  | 135.61 |  | 9.09 |  | 0.69 |  |  | 9.78 | [5 empty] | 6663.7584 |  | 46.1428
2 | District Cell | 1054.22 |  |  | 10000 |  |  | 11054.22 |  |  |  |  | 5.64 | 1.41 | 7.05 |  | 57.61
| Total |  |  |  | 10000 |  |  | 11189.83 |  | 9.09 | 0 | 0.69 | 5.64 | 1.41 | 16.83 |  | 53.61
| G.T. | 211.5601 | 0 | 0 | 10000 | 0 | 5.0488 | 10216.6089 | 474.952 | 5404.0712 | 397.2888 | 862.3984 | 56.5369 | 33.3847 | 6753.68 |  | 80
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2014-15 Up to the Month of May 2014 | [19 empty] | Physical Performance Under NREGA During the year 2014-15 Up to the Month of May 2014 | [17 empty] | Physical Performance Under NREGA During the year 2014-15 Up to the Month of May 2014
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 102 | 278022.5421 | 333.2899 | 566 | 39695.819 | 322.6589 | 15 | 10784.7899 | 22.6033 | 103 | 5.1 | 9.6648 | 106 | 62.5892 | 268.2084 | 479 | 162.4564 | 327.1327 | 113 | 26.5003 | 227.2759 | 690 | 18.7504 | 119.0291 | 63 | 19893.7858 | 137.4515 | 343 | 92685.3171 | 132.2929 | 569 | 540.0198 | 725.3868 | 901 | 53.8181 | 392.7099 | 200 | 1518.6819 | 368.9084 | 516 | 98.0885 | 438.8601 | 548 | 335.0135 | 1089.2733 | 1688 | 478.003 | 1397.4928 | 3 | 358.4 | 34.8789 | 203 | 502 | 316.6416 | 1719 | 3207.2765 | 5489 | 3456.4829
6663.7593
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2014-15 Up to the Month of May 2014
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 372 | 0 | 0 | 0 | 372 | 0 | 0 | 0 | 4 | 0
2 | Alipurduar-II | 186 | 0 | 4 | 0 | 182 | 0 | 1 | 0 | 8 | 0
3 | Dhupguri | 1713.5812 | 6854.3249 | 266 | 9 | 0 | 0.1 | 0 | 1 | 12 | 12
4 | Falakata | 7 | 1830 | 6 | 3 | 0 | 2.02 | 1 | 1 | 0 | 0
5 | Kalchini | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Kumargram | 1390 | 379 | 2 | 2 | 6 | 6 | 16 | 9 | 0 | 0
7 | Madarihat-Birpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Mal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Matiali | 0 | 33 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 1
10 | Maynaguri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
11 | Nagrakata | 0 | 0 | 10 | 0 | 0 | 0 | 5 | 0 | 0 | 0
12 | Rajganj | 13940 | 1247 | 2 | 10 | 1266 | 65 |  |  | 0 | 0
13 | Sadar | 47 | 0 | 1 | 1 | 341 | 16 | 0 | 28 | 0 | 0
| Total | 17655.5812 | 10343.3249 | 291 | 25 | 2167 | 94.12 | 23 | 39 | 26 | 13
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of May 2014)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 11 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of May 2014)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
May 2014
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
1 | Alipurduar-I | 5956 | 0 | 13.1446 | 42987 | 320 | 320.7889 | 333.9334 | 333.9334 | 0
2 | Alipurduar-II | 7895 | 36 | 34.1268 | 26404 | 45 | 299.3431 | 333.4699 | 333.4699 | 0
3 | Dhupguri | 12520 | 102 | 469.32 | 3420 | 250 | 210.8 | 680.12 | 680.1204 | -0.00039
4 | Falakata | 19756 | 520 | 279.7016 | 38910 | 59 | 264.777 | 544.4786 | 544.4786 | 0
5 | Kalchini | 20639 | 757 | 123.8985 | 37640 | 2753 | 396.2127 | 520.1112 | 520.1112 | 0
6 | Kumargram | 4791 | 1607 | 64.8141 | 30546 | 3458 | 346.2712 | 411.0853 | 411.0842 | 0.0011
7 | Madarihat | 4980 | 46 | 22.2468 | 46837 | 628 | 325.8815 | 348.1283 | 348.1283 | 0
8 | Mal | 1279 | 8 | 0 | 32627 | 1377 | 414.8579 | 414.8579 | 414.8579 | 0
9 | Matiali | 0 | 0 | 0 | 52395 | 501 | 229.9889 | 229.9889 | 229.9889 | 0
10 | Maynaguri | 6051 | 0 | 35.2322 | 61904 | 0 | 359.7476 | 394.9798 | 394.9798 | 0
11 | Nagrakata | 3247 | 0 | 48.998 | 29453 | 0 | 241.4762 | 290.4742 | 290.4742 | 0
12 | Rajganj | 4331 | 0 | 14.6379 | 51097 | 0 | 248.7763 | 263.4142 | 263.4142 | 0
13 | Sadar | 4056 | 0 | 73.8624 | 59535 | 0 | 556.0778 | 629.9403 | 629.9403 | 0
| Line dep. |  |  | 0 |  |  | 9.09 | 9.09 | 9.09 | 0
Total |  | 95501 | 3076 | 1179.993 | 513755 | 9391 | 4224.079 | 5404.0719 | 5404.0712 | 0.00071
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri