## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
part I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of Sept 2016 (for the financial year 2016-17)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals |  |  | 1.85
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 | 3 | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Dhupguri | 97570 | 36053 | 15348 | 44859 | 96260 | 50073 |  | 47712 | 9678 |  | 4.284 | 1.9931 | 5.0695 | 11.3466 | 4.7994 |  | 32 | 410 | 86 | 42.2984 | 23.7815
2 | Jalpaiguri | 67207 | 33711 | 2863 | 29509 | 66083 | 29824 |  | 28304 | 8369 |  | 3.8148 | 0.36376 | 2.4995 | 6.678 | 2.9075 |  | 90 | 151 | 21 | 62.0962 | 21.2104
3 | Mal | 65969 | 14986 | 16947 | 32809 | 64742 | 34565 |  | 30992 | 16200 |  | 2.0032 | 2.2146 | 4.0919 | 8.3097 | 4.0529 |  | 33 | 262 | 20 | 48.7728 | 26.8124
4 | Matiali | 28121 | 3843 | 10597 | 13065 | 27505 | 16756 |  | 15682 | 7027 |  | 0.80325 | 1.7666 | 2.3412 | 4.9111 | 2.6007 |  | 69 | 1671 | 6 | 52.9559 | 31.3166
5 | Maynaguri | 74913 | 43452 | 803 | 30225 | 74480 | 38722 |  | 37333 | 16919 |  | 5.9464 | 0.1179 | 3.7426 | 9.807 | 4.4631 |  | 19 | 481 | 48 | 45.5099 | 26.2689
6 | Nagrakata | 28565 | 4376 | 13271 | 10684 | 28331 | 15910 |  | 15179 | 5838 |  | 0.73006 | 1.702 | 1.8577 | 4.2898 | 2.0197 |  | 7 | 38 | 26 | 47.0823 | 28.2613
7 | Rajganj | 58434 | 25272 | 1776 | 30520 | 57568 | 20233 |  | 18468 | 8155 |  | 2.3662 | 0.22086 | 2.9849 | 5.5719 | 2.7034 |  | 167 | 201 | 53 | 48.5186 | 30.1708
| Total: | 420779 | 161693 | 61605 | 191671 | 414969 | 206083 | 0 | 193670 | 72186 | 0 | 19.948 | 8.3788 | 22.5873 | 50.9141 | 23.5468 | 0 | 417 | 3214 | 260 | 46.2481 | 26.2891
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2016-17 Up to the Month of Sept' 2016
1615.12
Sl. No. | Name of the Block | Actual O.B. as on 01.04.16 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Authorization of efms | Total Availability | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh) | [6 empty] | #REF!
|  |  | Central | State | Central | State |  |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (10+11+12+13+14)
[14 empty] | Recurring | Non-Recurring |  |  | 4.32 |  |  |  |  | avg. gp
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | [8 empty] | WAGE% | PER LABOUR
1 | Dhupguri | -1.46 | [5 empty] | 3115.95 | 3114.48 |  | 2797.63 | 201.46 | 77.07 | 21.68 | 2.89 | 3100.73 |  | 28.2218 | #REF! | #REF! | 946.3318 | 16 | 193.7956 | 281.8845 | 90.2249 | 246.5609 | Dhupguri | 831.2044
2 | Jalpaiguri | -4.51 | [5 empty] | 1620.48 | 1615.97 |  | 1461.84 | 69.05 | 49.7 | 31.78 | 2.75 | 1615.12 |  | 14.7003 | #REF! | #REF! | 394.9049 | 12 | 134.5933 | 146.8291 | 90.5097 | 218.9029 | Malbazar | 402.7251
3 | Mal | -17.56 | [5 empty] | 2054.06 | 2036.51 |  | 1737.27 | 115.36 | 154.86 | 27.22 | 0 | 2034.71 |  | 18.5193 | #REF! | #REF! | 329.2062 | 5 | 406.942 | 184.9736 | #REF! | #REF! | Matiali | 230.7365
4 | Matiali | -3.82 | [5 empty] | 1106.14 | 1102.32 |  | 802.9 | 55.33 | 127.69 | 16.65 | 0 | 1002.57 |  | 9.1251 | 134.1409 | 937.0409 | 421.4004 | 16 | 62.6606 | 91.1427 | 80.0842 | 163.4878 | Maynaguri | 677.9344
5 | Maynaguri | 14.17 | [5 empty] | 2942.69 | 2956.86 |  | 2444.19 | 146.01 | 325.17 | 15.4 | 0 | 2930.77 |  | 26.6749 | 493.9989 | 2938.1889 | 284.0694 | 5 | 586.154 | 266.4336 | #REF! | #REF! | Nagrakata | 243.0925
6 | Nagrakata | 0.11 | [5 empty] | 1126.38 | 1126.49 |  | 828.91 | 91.11 | 165.92 | 9.3 | 2.14 | 1097.38 | 51.1913 | 9.988 | 91.1409 | 920.0509 | 217.4445 | 12 | 91.4483 | 99.7618 | 75.5354 | 193.2286 | Rajganj | 282.2
7 | Rajganj | 13.56 | [5 empty] | 1138.54 | 1152.1 |  | 1020.45 | 40.47 | 35.96 | 8.9 | 2.16 | 1107.94 |  | 10.0841 | 268.9922 | 1289.4422 | 551.7063 | 14 | 79.1386 | 100.7218 | 92.1034 | 183.1409 | Sadar | 641.197
| Total | 0.49 | 0 | 0 | 0 |  | 0 | 13104.24 | 13104.73 | 0 | 11093.19 | 718.79 | 936.37 | 130.93 | 9.94 | 12889.22 |  | 18.82 |  |  |  | 80 | 161.1153 | 1171.7473 | 86.0656
1 | Line Deptt. | 18.9 | [5 empty] | 0.78 | 19.68 |  | 0 | 0.86 | 0 |  |  | 0.86 | [5 empty] | 12749.21 |  | 88.2823
2 | District Cell | 8.45 | [5 empty] | 120.66 | 120.66 |  |  |  |  | 112.2 |  | 112.2 |  | 57.61
| Total | 27.35 |  |  | 0 |  |  | 13225.68 |  |  | 11093.19 | 719.65 | 936.37 | 243.13 | 9.94 | 13002.28 |  | 53.61
| G.T. | 27.84 | 0 | 0 | 0 | 0 | 0 | 13225.68 | 13253.52 | 0 | 11093.19 | 719.65 | 936.37 | 243.13 | 9.94 | 13002.28 |  | 100
12749.21
[13 empty] | District Programme Coordinator |  |  |  |  | 12749.21
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2016-17 Up to the Month of Sept 2016 | [19 empty] | Physical Performance Under NREGA During the year 2016-17 Up to the Month of Sept 2016 | [17 empty] | Physical Performance Under NREGA During the year 2016-17 Up to the Month of Sept 2016
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 56 | 227143.4148 | 216.15 | 219 | 21683.3737 | 1021.43 | 157 | 86.02 | 86.02 | 812 | 5.1 | 44.6 | 26 | 50.3258 | 908.43 | 560 | 201.1163 | 517.54 | 73 | 14 | 124.3827 | 656 | 13 | 48.5839 | 60 | 17662.9032 | 75.34 | 58 | 67288.3052 | 278.77 | 76 | 453.8698 | 181.11 | 248 | 116.148 | 3756.53 | 238 | 1483.2643 | 116.11 | 557 | 134.2669 | 287.29 | 17 | 427.5677 | 127.87 | 375 | 288.1596 | 3324.38 | 495 | 358.4 | 288.32 | 1901 | 502 | 1346.35 | 1198 | 2123.7327 | 5386 | 10625.4739
12749.21
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator |  | 12749.2067
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri |  | 0.003345
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2016-17 Up to the Month of Sept 2016
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Dhupguri | 1207.6756 | 4830.7025 | 267 | 9 | 0 | 0.1 | 0 | 1 | 12 | 12
2 | Jalpaiguri | 10933 | 120 | 0 | 14 | 341 | 16 | 0 | 28 | 0 | 0
3 | Mal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Matiali | 0 | 33 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 1
5 | Maynaguri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
6 | Nagrakata | 0 | 0 | 10 | 0 | 0 | 0 | 5 | 0 | 0 | 0
7 | Rajganj | 13940 | 1247 | 2 | 10 | 1266 | 65 |  |  | 0 | 0
| Total | 26080.6756 | 6230.7025 | 279 | 33 | 1607 | 86.1 | 5 | 29 | 14 | 13
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of Sept 2016)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 126 | 101 | 5 | 3 | 14 | 12 | 7 | 7 | 7 | 6 | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of Sept 2016)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 2 | 99 | 0 | 3 | 0 | 12 | 0 | 7 | 0 | 6 | 5 | 5 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 578 | 718 | 17 | 17
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
Sept 2016
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
1 | Dhupguri | 12520 | 102 | 1890.39 | 1059 | 3980 | 907.24 | 2797.63 | 2797.63 | 0
2 | Jalpaiguri | 1279 | 8 | 0 | 32627 | 1377 | 1461.8393 | 1461.8393 | 1461.84 | -0.00073
3 | Mal | 0 | 0 | 0 | 52395 | 501 | 1737.2693 | 1737.2693 | 1737.27 | -0.00075
4 | Matiali | 6051 | 0 | 404.1809 | 61904 | 0 | 398.7144 | 802.8954 | 802.9 | -0.00465
5 | Maynaguri | 3078 | 0 | 1689.8143 | 29453 | 0 | 754.3749 | 2444.1892 | 2444.19 | -0.00082
6 | Nagrakata | 4331 | 0 | 13.8256 | 51097 | 0 | 815.0894 | 828.915 | 828.91 | 0.00497
7 | Rajganj | 4056 | 0 | 44.51 | 59535 | 0 | 975.94 | 1020.45 | 1020.45 | 0
8 | Line dep. |  |  | 0 |  |  | 0 | 0 | 0 | 0
Total |  | 31315 | 110 | 4042.7307 | 288070 | 5858 | 7050.4573 | 11093.188 | 11093.19 | -0.00198
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri