## Part-I
National Rural Employment Gurantee Act (N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of October' 2008
MPR- Part-I
1 | 2 |  | 3 | [5 empty] | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  |  | 10 | 11 | 12
|  |  | a | b | c | d |  |  |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Register | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Job Card as on 15-06-08 | Difference | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) |  |  |  |  | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals
|  |  | SC | ST | Others | Total | [8 empty] | ST | Others | Total | Women | bar: 9
1 | Alipurduar-I | 34863 | 19443 | 7771 | 7649 | 34863 | 33502 | 1361 | 10056 | 2994542 | 10056 | 1063 | 204624 | 0.98981 | 0.40715 | 0.35409 | 1.751 | 1.1515 | 0 | 1106 | 17
2 | Alipurduar-II | 40680 | 19423 | 9448 | 11808 | 40679 | 40465 | 214 | 13750 | 243770 | 15282 | 2986 | 120822.04 | 0.36247 | 0.5437 | 0.30206 | 1.2082 | 0.38663 | 2 | 1898 | 279
3 | Dhupguri | 75331 | 39789 | 16324 | 19150 | 75263 | 75263 | 0 | 30179 | 83258 | 30179 | 6931 | 1200842 | 1.5526 | 0.86117 | 0.95903 | 3.3727 | 0.8296 | 0 | 669 | 35
4 | Falakata | 42989 | 20459 | 8527 | 13908 | 42894 | 42195 | 699 | 13058 | 28614 | 13058 | 204 | 170718 | 0.49624 | 0.23375 | 0.33137 | 1.0614 | 0.32557 | 1 | 825 | 7
5 | Kalchini | 49815 | 6910 | 28694 | 14120 | 49724 | 48777 | 947 | 17370 | 54163.88 | 20500 | 1513 | 758294.32 | 0.63578 | 1.8667 | 0.8549 | 3.3574 | 0.94329 | 0 | 3677 | 493
6 | Kumargram | 37583 | 14801 | 14072 | 8710 | 37583 | 13297 | 8542 | 27235 | 131113 | 26681 | 9913 | 1059973 | 2.0494 | 0.98295 | 0.84705 | 3.8794 | 1.1038 | 0 | 8769 | 1451
7 | Madarihat-Birpara | 34382 | 6958 | 14532 | 12892 | 34382 | 34186 | 196 | 12984 | 58213 | 12984 | 2014 | 548406 | 0.52777 | 1.1968 | 0.88907 | 2.6137 | 1.0096 | 0 | 321 | 70
8 | Mal | 51666 | 16582 | 18003 | 17293 | 51878 | 51300 | 578 | 21470 | 39700 | 21470 | 4931 | 172210 | 0.78481 | 1.0463 | 0.95875 | 2.7899 | 0.93504 | 0 | 855 | 79
9 | Matiali | 21740 | 5320 | 10728 | 5667 | 21715 | 21292 | 423 | 10986 | 9753 | 9995 | 1455 | 205359 | 0.3346 | 0.642 | 0.52733 | 1.5039 | 0.71565 | 0 | 655 | 54
10 | Maynaguri | 60915 | 46026 | 994 | 13830 | 60850 | 60376 | 474 | 21443 | 38051 | 21336 | 7859 | 605904 | 1.3435 | 0.03382 | 0.36952 | 1.7468 | 0.57851 | 0 | 2286 | 83
11 | Nagrakata | 23114 | 3644 | 13479 | 5991 | 23114 | 22683 | 431 | 15965 | 0 | 15965 | 1814 | 0 | 0.38405 | 1.2561 | 0.59479 | 2.2349 | 0.68844 | 0 | 843 | 125
12 | Rajganj | 44357 | 26569 | 2366 | 15422 | 44357 | 40114 | 4243 | 7729 | 3665584 | 7648 | 1469 | 236889 | 0.34768 | 0.05182 | 0.106 | 0.5055 | 0.21887 | 0 | 401 | 2
13 | Sadar | 55241 | 37620 | 4105 | 13516 | 55241 | 54816 | 425 | 11556 | 0 | 11556 | 3058 | 0 | 0.74903 | 0.14448 | 0.17356 | 1.0671 | 0.27664 | 0 | 689 | 34
| Total: | 572676 | 263544 | 149043 | 159956 | 572543 | 538266 | 18533 | 213781 | 7346761.88 | 216710 | 45210 | 5284041.36 | 10.5577 | 9.2668 | 7.2675 | 27.092 | 9.1631 | 3 | 22994 | 2729

## Part-II
Part-II
National Rural Employment Gurantee Act (N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2008-09 Up to the Month of October' 08
Jalpaiguri District | [15 empty] | (Rs. in lakh)
Sl. No. | Name of the Block | No. of Household | Actual O.B. as on 01.04.08 | Released last year but received during the current year |  | Release During the Current Year by the Govt. to Z.P. |  | Misc. Receipt | Total Availability (4+5+6+7+8) | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure
|  |  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (9+10+11+12)
[14 empty] | Recurring | Non-Recurring
| 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Alipurduar-I | 2912 | 2: 100.2988; 8: 100.2988; 10: 131.4587; 11: 5.6729; 12: 69.6007; Recurring 13: 1.0411; Non-Recurring 14: 2.5835; Non-Recurring 15: 210.3569 |  | 62.49%
2 | Alipurduar-II | 4447 | 96.0436 | [5 empty] | 96.0436 | 41.1067 | 100.1988 | 6.3463 | 72.5484 | 7.4812 | 2.6811 | 189.2558 |  | 52.94%
3 | Dhupguri | 2895 | 2: 98.1287; 8: 98.1287; 10: 268.1432; 11: 10.9836; 12: 268.5571; Recurring 13: 0.65967; Non-Recurring 14: 9.0314; Non-Recurring 15: 557.375 |  | 48.11%
4 | Falakata | 4593 | 2: 58.3644; 8: 58.3644; 10: 78.9817; 11: 3.5292; 12: 50.3713; Recurring 13: 2.2085; Non-Recurring 14: 1.1747; Non-Recurring 15: 136.2653 |  | 57.96%
5 | Kalchini | 2539 | 2: 129.3238; 8: 129.3238; 10: 275.983; 11: 18.5589; 12: 75.6887; Recurring 13: 3.2399; Non-Recurring 14: 2.2574; Non-Recurring 15: 375.728 |  | 73.45%
6 | Kumargram | 3620 | 2: 77.2946; 8: 77.2946; 10: 312.064; 11: 15.2817; 12: 174.7683; Recurring 13: 1.7438; Non-Recurring 14: 11.3539; Non-Recurring 15: 515.2117 |  | 60.57%
7 | Madarihat-Birpara | 3872 | 2: 42.5347; 8: 42.5347; 10: 206.9269; 11: 17.101; 12: 225.4803; Recurring 13: 2.0685; Non-Recurring 14: 7.4268; Non-Recurring 15: 459.0035 |  | 45.08%
8 | Mal | 3006 | 2: 124.7644; 8: 124.7644; 10: 249.3075; 11: 10.0567; 12: 90.6353; Recurring 13: 2.764; Non-Recurring 14: 6.0326; Non-Recurring 15: 358.7961 |  | 69.48%
9 | Matiali |  | 2: 70.1932; 8: 70.1932; 10: 129.0759; 11: 7.1224; 12: 69.7906; Recurring 13: 2.7206; Non-Recurring 14: 3.7629; Non-Recurring 15: 212.4725 |  | 60.75%
10 | Maynaguri |  | 2: 99.5516; 8: 99.5516; 10: 130.9766; 11: 3.4232; 12: 67.4862; Recurring 13: 3.9348; Non-Recurring 14: 2.717; Non-Recurring 15: 208.5379 |  | 62.81%
11 | Nagrakata |  | 2: 31.5438; 8: 31.5438; 10: 167.6198; 11: 9.7878; 12: 89.7796; Recurring 13: 2.2422; Non-Recurring 14: 5.7029; Non-Recurring 15: 275.1322 |  | 60.92%
12 | Rajganj | 2781 | 2: 37.5782; 8: 37.5782; 10: 40.6313; 11: 1.2592; 12: 26.4919; Recurring 13: 18.4761; Non-Recurring 14: 0.07861; Non-Recurring 15: 86.9371 |  | 46.74%
13 | Sadar | 3059 | 2: 118.9983; 8: 118.9983; 10: 82.1877; 11: 3.3968; 12: 39.7856; Recurring 13: 0.75512; Non-Recurring 14: 1.851; Non-Recurring 15: 127.9762 |  | 64.22%
| Total | 33724 | 1084.6182 | 0 | 0 | 0 | 0 | 0 | 1084.6182 |  | 2173.555 | 112.5199 | 1320.984 | 49.3356 | 56.6537 | 3713.0481 | 0
1 | Line Deptt. |  | 2: 68.313; 8: 68.313; 10: 66.21; Non-Recurring 15: 66.21
2 | District Cell |  | 2: 319.8484; 8: 319.8484; Recurring 13: 6.7823; Non-Recurring 14: 16.205; Non-Recurring 15: 22.9873 |  | 22.9873
| Total | 57194 | 388.1614 | 0 | 0 | 0 | 0 | 0 | 388.1614 |  | 66.21 | 0 | 0 | 6.7823 | 16.205 | 89.1973
| G.T. |  | 1472.7796 | 0 | 0 | 0 | 0 | 0 | 1472.7796 |  | 2239.765 | 112.5199 | 1320.984 | 56.1178 | 72.8588 | 3802.2454 |  | 2397.7625 | 1404.4829
Note on L27: N.R.E.G.S.4: Oct' 08
Note on O28: N.R.E.G.S.4: For the month of Oct, 08
Note on P28: N.R.E.G.S.4: For the month of Oct, 08

## Part-III
National Rural Employment Gurantee Act (NREGA) | [19 empty] | National Rural Employment Gurantee Act (NREGA) | [17 empty] | National Rural Employment Gurantee Act (NREGA)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2008-09 Up to the Month of October' 08 | [19 empty] | Physical Performance Under NREGA During the year 2008-09 Up to the Month of October' 08 | [17 empty] | Physical Performance Under NREGA During the year 2008-09 Up to the Month of October' 08
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the Block | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec. |  | No. | Hec. |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  |  | No.
1 | Alipurduar-I | 48 | 51382.49 | 24.7613 | 7 | 16663.36 | 4.4141 | 20 | 14.04 | 2.4941 | 29 | 23.32 | 2.4373 | 1 | 0.55 | 0.25625 | 0 | 0 | 0 | 6 | 3.25 | 4.7484 | 2 | 1.5 | 0.4 | 18 | 8100 | 8.4962 | 1 | 150 | 0.38466 | 5 | 5.05 | 3.2184 | 1 | 0 | 0.93825 | 16 | 10.419 | 22.2987 | 9 | 6.493 | 43.0831 | 60 | 64.285 | 73.0278 | 22 | 20.115 | 21.7558 | 0 | 0 | 0 | 0 | 0 | 0 | 174 |  | 139.3012 | 71 | 0 | 62.4319 | 201.733
2 | Alipurduar-II | 0 | 0 | 0 | 19 | 34096.1905 | 10.7403 | 2 | 3.1406 | 1.005 | 18 | 12.7545 | 5.1756 | 4 | 1.2712 | 0.78817 | 5 | 10.8726 | 7.0672 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2858.697 | 0.94337 | 5 | 7377.2121 | 2.4345 | 0 | 0 | 0 | 2 | 0.16406 | 0.0525 | 2 | 0.68689 | 1.4974 | 40 | 24.8755 | 54.1649 | 35 | 6.5062 | 17.2317 | 66 | 40.6607 | 76.5225 | 0 | 0 | 0 | 0 | 0 | 0 | 46 |  | 21.4657 | 155 |  | 156.1575 | 177.6232
3 | Dhupguri | 42 | 107765.7231 | 35.0239 | 4 | 10078.0615 | 3.2754 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 22.891 | 14.1924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 35.2405 | 11.277 | 1 | 0 | 0 | 14 | 22.1936 | 50.6015 | 0 | 0 | 0 | 210 | 811.1838 | 389.3682 | 63 | 109.244 | 52.4371 | 0 | 0 | 0 | 0 | 0 | 0 | 286 |  | 500.463 | 68 |  | 55.7125 | 556.1755
4 | Falakata | 11 | 26764.2593 | 7.2264 | 9 | 23759.037 | 6.4149 | 1 | 0.12 | 0.03 | 2 | 0.555 | 0.13875 | 8 | 3.9925 | 2.4754 | 3 | 1.2 | 0.90226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3378.5 | 1.0811 | 5 | 9.5755 | 2.9684 | 4 | 9.3654 | 2.9033 | 6 | 2.7833 | 6.2624 | 4 | 3.9183 | 8.8162 | 64 | 53.67 | 42.3766 | 65 | 73.21 | 51.152 | 0 | 0 | 0 | 0 | 0 | 0 | 95 |  | 61.3391 | 89 |  | 71.4085 | 132.7476
5 | Kalchini | 14 | 26472.12 | 10.0902 | 7 | 2765.81 | 1.3319 | 0 | 0 | 0 | 9 | 5.1 | 1.29 | 40 | 115.17 | 51.3313 | 8 | 12.3 | 7.1719 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 7.61 | 0 | 0 | 0 | 6 | 42.18 | 37.1501 | 1 | 0 | 0.002 | 59 | 36.623 | 66.769 | 44 | 16.71 | 40.0592 | 96 | 115 | 128.0684 | 21 | 28.525 | 27.6612 | 0 | 0 | 0 | 0 | 0 | 0 | 216 |  | 301.019 | 90 |  | 77.5162 | 378.5352
6 | Kumargram | 29 | 67351.5 | 22.7452 | 28 | 33344.05 | 26.0769 | 14 | 4.902 | 5.4645 | 26 | 8.953 | 11.5548 | 11 | 10.89 | 11.8981 | 15 | 7.804 | 17.5537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0.75613 | 43 | 75.171 | 39.3776 | 11 | 9.015 | 12.6525 | 10 | 13.9 | 34.3783 | 16 | 6 | 68.4924 | 69 | 45.36 | 66.0997 | 96 | 81.775 | 115.2149 | 0 | 0 | 0 | 0 | 0 | 0 | 176 |  | 179.9634 | 195 |  | 252.3014 | 432.2648
7 | Madarihat-Birpara | 5 | 9855.13 | 2.7667 | 8 | 27251 | 10.7827 | 2 | 1 | 0.19125 | 28 | 2 | 9.7241 | 1 | 0.8 | 2.0518 | 3 | 2 | 1.3918 | 2 | 8 | 1.9305 | 2 | 0 | 0.37305 | 6 | 12608 | 8.3583 | 12 | 12681 | 10.2839 | 5 | 14.94 | 4.8412 | 4 | 2.5 | 1.2075 | 45 | 43.3 | 83.2603 | 47 | 18.69 | 103.562 | 78 | 116.15 | 86.6633 | 84 | 52.9 | 96.1138 | 0 | 0 | 0 | 0 | 0 | 0 | 144 |  | 190.0633 | 188 |  | 233.4389 | 423.5022
8 | Mal | 19 | 10079.916 | 10.7182 | 39 | 54017.393 | 35.3723 | 8 | 7.59 | 2.0842 | 25 | 24.93 | 6.9056 | 151 | 93.15 | 54.47 | 58 | 71.703 | 37.0192 | 0 | 0 | 0 | 1 | 160 | 5.0713 | 8 | 4625 | 3.7679 | 8 | 2300 | 8.5122 | 4 | 3.9 | 1.7181 | 7 | 2.795 | 2.7804 | 9 | 9.275 | 17.1322 | 33 | 1044.4 | 23.2189 | 58 | 72.898 | 58.9249 | 51 | 50.839 | 66.1409 | 0 | 0 | 0 | 0 | 0 | 0 | 257 |  | 148.8155 | 222 |  | 185.0208 | 333.8363
9 | Matiali | 16 | 16909.3333 | 7.6092 | 13 | 15744.4444 | 7.085 | 0 | 0 | 0 | 7 | 36.972 | 8.7066 | 23 | 21.7471 | 14.0378 | 47 | 67.7926 | 41.7411 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2967.3143 | 1.0386 | 16 | 16926.9714 | 5.9244 | 6 | 15.6378 | 3.7952 | 12 | 25.8227 | 6.6052 | 8 | 11.73 | 7.0673 | 20 | 68.741 | 65.5417 | 22 | 23.0623 | 14.339 | 40 | 30.2254 | 22.4858 | 0 | 0 | 0 | 0 | 0 | 0 | 77 |  | 47.8871 | 155 |  | 158.0899 | 205.977
10 | Maynaguri | 8 | 2541 | 4.1231 | 40 | 49202.5 | 15.7921 | 4 | 2.5 | 1.7901 | 169 | 100.3 | 51.3637 | 1 | 0.2 | 0 | 1 | 0.6 | 0.43687 | 1 | 0 | 0.70226 | 9 | 6008 | 4.6516 | 4 | 15000 | 0.58311 | 5 | 5630 | 1.7683 | 0 | 0 | 0 | 7 | 3.5 | 1.5974 | 7 | 5 | 4.6943 | 11 | 15.8 | 2.3834 | 52 | 46.08 | 28.4 | 95 | 103.975 | 55.5285 | 0 | 0 | 0 | 0 | 0 | 0 | 77 |  | 40.2929 | 337 |  | 133.5218 | 173.8147
11 | Nagrakata | 11 | 33446.24 | 12.9071 | 0 | 0 | 0 | 45 | 202.17 | 35.6117 | 1 | 1.6 | 0.2265 | 56 | 131.54 | 62.6872 | 5 | 2.5 | 0.74625 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 221.16 | 7.7032 | 3 | 0 | 0 | 3 | 6750 | 3.8051 | 3 | 2300 | 1.485 | 19 | 14.775 | 39.1113 | 5 | 1.125 | 15.0001 | 58 | 69.2 | 92.4258 | 13 | 3.2 | 3.4229 | 0 | 0 | 0 | 0 | 0 | 0 | 206 |  | 254.2514 | 30 |  | 20.8808 | 275.1322
12 | Rajganj | 1 | 1133.41 | 0.39175 | 2 | 2292 | 0.019 | 11 | 51.295 | 2.1778 | 33 | 108.95 | 15.2963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6.25 | 7.7544 | 0 | 0 | 0 | 2 | 1.8 | 2.8865 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0.6 | 0.52437 | 26 | 28.45 | 25.0362 | 24 | 36.3 | 34.06 | 0 | 0 | 0 | 0 | 0 | 0 | 50 |  | 38.2467 | 62 |  | 49.8997 | 88.1464
13 | Sadar | 24 | 16353 | 9.5577 | 5 | 3854 | 1.7692 | 13 | 1588.92 | 5.2951 | 40 | 46.19 | 17.899 | 1 | 1 | 0.189 | 0 | 0 | 0 | 2 | 6.82 | 0.6345 | 0 | 0 | 0 | 3 | 9 | 1.224 | 14 | 1147 | 8.8953 | 3 | 2.5 | 1.7083 | 18 | 28.96 | 25.2068 | 5 | 4.75 | 3.8845 | 5 | 9 | 2.7033 | 32 | 1921.69 | 27.9595 | 12 | 10.497 | 12.1011 | 0 | 0 | 0 | 0 | 0 | 0 | 83 |  | 50.4525 | 94 |  | 68.5747 | 119.0272
| Total | 228 | 370054.1217 | 147.9208 | 181 | 273067.8465 | 123.0738 | 120 | 1875.6776 | 56.1437 | 387 | 371.6246 | 130.7184 | 314 | 403.202 | 214.3774 | 145 | 176.7722 | 114.0302 | 11 | 18.07 | 8.0156 | 14 | 6169.5 | 10.4959 | 69 | 48483.4213 | 47.4791 | 69 | 49590.6835 | 40.0405 | 85 | 6955.9948 | 112.7459 | 71 | 2382.1222 | 55.4308 | 200 | 175.4358 | 336.9572 | 237 | 1216.3528 | 427.5496 | 860 | 3373.5353 | 1049.921 | 652 | 641.4661 | 634.5966 | 0 | 0 | 0 | 0 | 0 | 0 | 1887 | 0 | 1973.5608 | 1756 | 0 | 1524.9545 | 3498.5152
[56 empty] | 1584 |  |  | 1224
[56 empty] | -303 |  |  | -532

## Part-IV
Part-IV
National Rural Employment Gurantee Act (N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2008-09 Up to the Month of October' 08
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 458 | 105 | 0 | 40 | 0 | 60 | 0 | 11 | 3 | 5
2 | Alipurduar-II | 200 | 5 | 197 | 8 | 205 | 0 | 1 | 4 | 0 | 0
3 | Dhupguri | 152 | 10 | 41 | 0 | 41 | 0 | 32 | 0 | 0 | 0
4 | Falakata | 103 | 2 | 41 | 0 | 41 | 4 | 0 | 12 | 0 | 0
5 | Kalchini | 14262 | 225 | 0 | 11 | 0 | 147 | 4 | 18 | 0 | 5
6 | Kumargram | 1562 | 1098 | 867 | 27 | 23 | 0.82 | 35 | 3 | 0 | 0
7 | Madarihat-Birpara | 316 | 3 | 288 | 30 | 316 | 4 | 17 | 79 | 0 | 0
8 | Mal | 2278 | 69 | 475 | 4 | 472 | 7 | 0 | 0 | 0 | 0
9 | Matiali | 45 | 145 | 3 | 4 | 0 | 0 | 61 | 59 | 0 | 0
10 | Maynaguri | 35 | 15 | 0 | 0 | 35 | 15 | 165 | 0 | 0 | 0
11 | Nagrakata | 48 | 13 | 7 | 7 |  |  | 5 | 5 | 0 | 0
12 | Rajganj | 584 | 50 | 84 | 0 | 28 | 0 | 51 | 31 | 0 | 0
13 | Sadar | 101 | 5 | 45 | 5 | 24 | 0 | 2 | 1 | 0 | 0
| Total | 20144 | 1745 | 2048 | 136 | 1185 | 237.82 | 373 | 223 | 3 | 10

## Part-V-A
MPR Part - V-A
National Rural Employment Guarantee Act (NREGA)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the month of October' 2008)
Jalpaiguri District
Sl. No | Name of the BLOCK / GP | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | Alipurduar-I | 11 | 8 | 1 | 1 | 7 | 7 | 1 | 1 | 1 | 1
2 | Alipurduar-II | 11 | 9 | 1 | 1 | 5 | 5 | 1 | 1 | 1 | 1
3 | Dhupguri | 16 | 14 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1
4 | Falakata | 12 | 9 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
5 | Kalchini | 11 | 9 | 1 | 1 | 6 | 5 | 1 | 1 | 1 | 1
6 | Kumargram | 11 | 9 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
7 | Madarihat-Birpara | 10 | 6 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1
8 | Mal | 12 | 6 | 2 | 2 | 7 | 7 | 3 | 3 | 1 | 1
9 | Matiali | 5 | 5 | 1 | 1 | 5 | 5 | 1 | 1 | 1 | 1
10 | Maynaguri | 16 | 15 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
11 | Nagrakata | 5 | 3 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1
12 | Rajganj | 12 | 6 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
13 | Sadar | 14 | 11 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1
| Total: | 146 | 110 | 11 | 11 | 44 | 42 | 15 | 15 | 13 | 13 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1

## Part-V-B
MPR Part - V-B
National Rural Employment Guarantee Act (NREGA)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the month of October' 2008)
Jalpaiguri District
Sl. No | Name of the BLOCK / GP | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1 | Alipurduar-I | 8 | 8 | 1 | 0 | 7 | 0 | 1 | 0 | 1 | 0 | [10 empty] | 0 | 0 | 0 | 0
2 | Alipurduar-II | 9 | 0 | 1 | 1 | 5 | 5 | 0 | 1 | 0 | 1 | [10 empty] | 55 | 33 | 0 | 0
3 | Dhupguri | 14 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 291 | 291 | 17 | 17
4 | Falakata | 9 | 0 | 1 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | [10 empty] | 213 | 204 | 0 | 0
5 | Kalchini | 9 | 0 | 1 | 0 | 5 | 2 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0
6 | Kumargram | 9 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 0 | [10 empty] | 0 | 0 | 0 | 0
7 | Madarihat-Birpara | 6 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
8 | Mal | 6 | 0 | 2 | 2 | 7 | 7 | 3 | 3 | 1 | 1 | [10 empty] | 202 | 202 | 573 | 0
9 | Matiali | 5 | 0 | 1 | 1 | 5 | 5 | 1 | 1 | 1 | 1 | [10 empty] | 85 | 85 | 0 | 0
10 | Maynaguri | 15 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 4
11 | Nagrakata | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 1 | 1 | [10 empty] | 89 | 0 | 512 | 0
12 | Rajganj | 6 | 0 | 1 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | [10 empty] | 222 | 222 | 3460 | 36160
13 | Sadar | 11 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Total: | 110 | 8 | 13 | 10 | 41 | 28 | 12 | 13 | 10 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157 | 1037 | 4562 | 36177 | 0