## Part-I
National Rural Employment Gurantee Act (N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of September' 2008
MPR- Part-I
1 | 2 |  | 3 | [5 empty] | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  |  | 10 | 11 | 12
|  |  | a | b | c | d |  |  |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Register | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Job Card as on 15-06-08 | Difference | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) |  |  |  |  | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals
|  |  | SC | ST | Others | Total | [8 empty] | ST | Others | Total | Women | bar: 9
1 | Alipurduar-I | 34863 | 19443 | 7771 | 7649 | 34863 | 33502 | 1361 | 9371 | 2694144 | 9371 | 1562 | 184510 | 0.96747 | 0.40349 | 0.34209 | 1.7131 | 1.1065 | 0 | 1096 | 17
2 | Alipurduar-II | 40680 | 19423 | 9448 | 11809 | 40680 | 40465 | 215 | 13044 | 243770 | 13994 | 2305 | 116818.2 | 0.35045 | 0.52568 | 0.29205 | 1.1682 | 0.35045 | 1 | 1898 | 278
3 | Dhupguri | 75331 | 39789 | 16324 | 19150 | 75263 | 75263 | 0 | 27409 | 63881 | 27409 | 5133 | 929529 | 1.3143 | 0.65928 | 0.85038 | 2.824 | 0.67012 | 0 | 542 | 34
4 | Falakata | 42989 | 20459 | 8527 | 13908 | 42894 | 42195 | 699 | 13058 | 28614 | 13058 | 758 | 170718 | 0.4917 | 0.23079 | 0.32511 | 1.0476 | 0.32431 | 1 | 820 | 7
5 | Kalchini | 49815 | 6897 | 28651 | 14077 | 49625 | 48777 | 848 | 16682 | 41556.77 | 19540 | 2975 | 581794.78 | 0.44344 | 1.7157 | 0.75928 | 2.9184 | 0.82705 | 0 | 3617 | 493
6 | Kumargram | 36305 | 14466 | 13297 | 8542 | 36305 | 13297 | 8542 | 26334 | 107907 | 25804 | 12087 | 866372 | 1.9422 | 0.94005 | 0.79072 | 3.673 | 1.0629 | 0 | 7251 | 1336
7 | Madarihat-Birpara | 34606 | 6946 | 14518 | 12842 | 34306 | 34186 | 120 | 12374 | 22491 | 12374 | 2651 | 456828 | 0.45092 | 1.0732 | 0.74544 | 2.2695 | 0.8727 | 0 | 280 | 45
8 | Mal | 51666 | 16582 | 17791 | 17293 | 51666 | 51300 | 366 | 19545 | 36900 | 26440 | 5349 | 163210 | 0.78481 | 1.0463 | 0.95875 | 2.7899 | 0.93504 | 0 | 809 | 64
9 | Matiali | 21714 | 5319 | 10728 | 5667 | 21714 | 21292 | 422 | 10360 | 6269 | 9253 | 1915 | 203150 | 0.30733 | 0.61388 | 0.50838 | 1.4296 | 0.68976 | 0 | 655 | 54
10 | Maynaguri | 60889 | 46026 | 994 | 13816 | 60836 | 60376 | 460 | 20823 | 36725 | 20716 | 5490 | 5.587 | 1.6439 | 0.02493 | 0.30073 | 1.9695 | 0.55759 | 0 | 2203 | 78
11 | Nagrakata | 23067 | 3644 | 13441 | 5982 | 23067 | 22683 | 384 | 14457 | 0 | 14457 | 2824 | 0 | 0.36506 | 1.1983 | 0.56329 | 2.1266 | 0.65719 | 0 | 725 | 124
12 | Rajganj | 44046 | 26499 | 2364 | 15383 | 44246 | 40114 | 4132 | 7280 | 34873 | 7199 | 2142 | 236889 | 0.31124 | 0.01095 | 0.10238 | 0.42457 | 0.19337 | 0 | 310 | 2
13 | Sadar | 54866 | 37363 | 4105 | 13388 | 54856 | 54816 | 40 | 21315 | 0 | 21301 | 10328 | 0 | 1.2833 | 0.27754 | 0.29237 | 1.8533 | 0.21622 | 0 | 577 | 30
| Total: | 570837 | 262856 | 147959 | 159506 | 570321 | 538266 | 17589 | 212052 | 3317130.77 | 220916 | 55519 | 3909824.567 | 10.6561 | 8.72 | 6.831 | 26.2071 | 8.4632 | 2 | 20783 | 2562

## Part-II
Part-II
National Rural Employment Gurantee Act (N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2008-09 Up to the Month of September' 08
Jalpaiguri District | [15 empty] | (Rs. in lakh)
Sl. No. | Name of the Block | No. of Household | Actual O.B. as on 01.04.08 | Released last year but received during the current year |  | Release During the Current Year by the Govt. to Z.P. |  | Misc. Receipt | Total Availability (4+5+6+7+8) | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure
|  |  |  | Central | State | Central | State |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (9+10+11+12)
[14 empty] | Recurring | Non-Recurring
| 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | Alipurduar-I | 2912 | 2: 100.2988; 8: 100.2988; 10: 128.6093; 11: 5.1598; 12: 58.4257; Recurring 13: 0.95739; Non-Recurring 14: 2.1021; Non-Recurring 15: 195.2544 |  | 65.87%
2 | Alipurduar-II | 4447 | 96.0436 | [5 empty] | 96.0436 | 41.1067 | 97.1403 | 3.8454 | 60.316 | 4.2085 | 2.2281 | 167.7384 |  | 57.91%
3 | Dhupguri | 2895 | 2: 98.1287; 8: 98.1287; 10: 225.3821; 11: 9.6526; 12: 237.8687; Recurring 13: 0.65967; Non-Recurring 14: 7.0939; Non-Recurring 15: 480.6569 |  | 46.89%
4 | Falakata | 4593 | 2: 58.3644; 8: 58.3644; 10: 78.0344; 11: 3.501; 12: 50.3713; Recurring 13: 2.0239; Non-Recurring 14: 1.1655; Non-Recurring 15: 135.0961 |  | 57.76%
5 | Kalchini | 2539 | 2: 129.3238; 8: 129.3238; 10: 249.0483; 11: 16.7721; 12: 70.8189; Recurring 13: 3.1145; Non-Recurring 14: 2.1629; Non-Recurring 15: 341.9167 |  | 72.84%
6 | Kumargram | 3620 | 2: 77.2946; 8: 77.2946; 10: 293.1137; 11: 13.7882; 12: 131.4821; Recurring 13: 1.6987; Non-Recurring 14: 10.1566; Non-Recurring 15: 450.2393 |  | 65.1%
7 | Madarihat-Birpara | 3872 | 2: 42.5347; 8: 42.5347; 10: 179.7619; 11: 13.1474; 12: 184.859; Recurring 13: 2.0678; Non-Recurring 14: 6.6754; Non-Recurring 15: 386.5115 |  | 46.51%
8 | Mal | 3006 | 2: 124.7644; 8: 124.7644; 10: 222.0531; 11: 8.8474; 12: 59.5927; Recurring 13: 1.5562; Non-Recurring 14: 4.4172; Non-Recurring 15: 296.4667 |  | 74.9%
9 | Matiali |  | 2: 70.1932; 8: 70.1932; 10: 121.4071; 11: 6.7261; 12: 64.4152; Recurring 13: 2.2527; Non-Recurring 14: 3.4353; Non-Recurring 15: 198.2364 |  | 61.24%
10 | Maynaguri |  | 2: 99.5516; 8: 99.5516; 10: 104.9569; 11: 3.0292; 12: 48.7968; Recurring 13: 3.9347; Non-Recurring 14: 2.1837; Non-Recurring 15: 162.9013 |  | 64.43%
11 | Nagrakata |  | 2: 31.5438; 8: 31.5438; 10: 159.4957; 11: 8.9307; 12: 62.355; Recurring 13: 1.891; Non-Recurring 14: 5.5015; Non-Recurring 15: 238.1739 |  | 66.97%
12 | Rajganj | 2781 | 2: 37.5782; 8: 37.5782; 10: 38.2858; 11: 1.0275; 12: 22.9193; Recurring 13: 18.4444; Non-Recurring 14: 0.07375; Non-Recurring 15: 80.7508 |  | 47.41%
13 | Sadar | 3059 | 2: 118.9983; 8: 118.9983; 10: 70.8753; 11: 3.1984; 12: 29.0567; Recurring 13: 0.70857; Non-Recurring 14: 1.3653; Non-Recurring 15: 105.2043 |  | 67.37%
| Total | 33724 | 1084.6182 | 0 | 0 | 0 | 0 | 0 | 1084.6182 |  | 1968.164 | 97.6259 | 1081.2775 | 43.5181 | 48.5613 | 3239.1467 | 0
1 | Line Deptt. |  | 2: 68.313; 8: 68.313; 10: 64.59; Non-Recurring 15: 64.59
2 | District Cell |  | 2: 319.8484; 8: 319.8484; Recurring 13: 5.6223; Non-Recurring 14: 14.9938; Non-Recurring 15: 20.6161 |  | 20.6161
| Total | 57194 | 388.1614 | 0 | 0 | 0 | 0 | 0 | 388.1614 |  | 64.59 | 0 | 0 | 5.6223 | 14.9938 | 85.2061
| G.T. |  | 1472.7796 | 0 | 0 | 0 | 0 | 0 | 1472.7796 |  | 2032.754 | 97.6259 | 1081.2775 | 49.1403 | 63.5551 | 3324.3527 |  | 2397.7625 | 926.5902
Note on L27: N.R.E.G.S.4: Sept' 08
Note on O28: N.R.E.G.S.4: For the month of Sept, 08
Note on P28: N.R.E.G.S.4: For the month of Sept, 08

## Part-III
National Rural Employment Gurantee Act (NREGA) | [19 empty] | National Rural Employment Gurantee Act (NREGA) | [17 empty] | National Rural Employment Gurantee Act (NREGA)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2008-09 Up to the Month of September' 08 | [19 empty] | Physical Performance Under NREGA During the year 2008-09 Up to the Month of September' 08 | [17 empty] | Physical Performance Under NREGA During the year 2008-09 Up to the Month of September' 08
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the Block | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec. |  | No. | Hec. |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  |  | No.
1 | Alipurduar-I | 44 | 39025.49 | 17.1862 | 11 | 31584.36 | 11.018 | 20 | 74.04 | 1.9941 | 25 | 20 | 1.1965 | 1 | 0.55 | 0.25625 | 0 | 0 | 0 | 6 | 3.25 | 4.7484 | 2 | 1.5 | 0.4 | 17 | 7960 | 7.1338 | 2 | 350 | 0.83278 | 5 | 5.05 | 3.2184 | 1 | 0 | 0.93825 | 16 | 10.419 | 22.2987 | 9 | 6.493 | 37.1915 | 54 | 53.685 | 60.0132 | 28 | 25.765 | 29.0752 | 0 | 0 | 0 | 0 | 0 | 0 | 163 |  | 116.8489 | 78 | 0 | 62.4319 | 179.2808
2 | Alipurduar-II | 0 | 0 | 0 | 19 | 34096.1905 | 10.7403 | 2 | 0.16047 | 0.05135 | 16 | 6.9488 | 3.1436 | 4 | 1.2712 | 0.78817 | 5 | 8.9164 | 5.7957 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2858.697 | 0.94337 | 5 | 7377.2121 | 2.4345 | 0 | 0 | 0 | 2 | 0.16406 | 0.0525 | 2 | 0.67313 | 1.4674 | 33 | 21.8553 | 47.5357 | 22 | 4.0929 | 10.2401 | 63 | 39.5349 | 76.2809 | 0 | 0 | 0 | 0 | 0 | 0 | 33 |  | 13.4904 | 143 |  | 145.9832 | 159.4737
3 | Dhupguri | 40 | 107765.7231 | 35.0239 | 4 | 10078.0615 | 3.2754 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 22.891 | 14.1924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 32.5911 | 10.4291 | 1 | 0 | 0 | 12 | 20.0262 | 45.6597 | 5 | 0.70208 | 1.6007 | 181 | 520.509 | 249.8443 | 66 | 246.4104 | 118.277 | 0 | 0 | 0 | 0 | 0 | 0 | 252 |  | 355.1495 | 76 |  | 123.1531 | 478.3026
4 | Falakata | 11 | 26764.2593 | 7.2264 | 9 | 23759.037 | 6.4149 | 1 | 0.12 | 0.03 | 2 | 0.555 | 0.13875 | 8 | 3.9925 | 2.4754 | 3 | 1.2 | 0.90226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3378.5 | 1.0811 | 5 | 9.5755 | 2.9684 | 4 | 7.1154 | 2.2058 | 6 | 2.7833 | 6.2624 | 4 | 3.9183 | 8.8162 | 64 | 29.67 | 42.3766 | 65 | 73.21 | 50.8741 | 0 | 0 | 0 | 0 | 0 | 0 | 95 |  | 61.3391 | 89 |  | 70.4331 | 131.7723
5 | Kalchini | 14 | 26472.12 | 10.0902 | 7 | 2765.81 | 1.3319 | 0 | 0 | 0 | 9 | 5.1 | 1.29 | 39 | 111.17 | 46.285 | 7 | 1489.7 | 6.8535 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2088 | 7.61 | 0 | 0 | 0 | 4 | 5.65 | 2.6881 | 3 | 16 | 8.7855 | 53 | 34.503 | 59.8069 | 47 | 36.516 | 33.3359 | 86 | 90.5 | 98.0593 | 31 | 48.524 | 49.5453 | 0 | 0 | 0 | 0 | 0 | 0 | 197 |  | 224.5395 | 104 |  | 101.142 | 325.6815
6 | Kumargram | 27 | 67351.5 | 20.1926 | 29 | 33342.05 | 27.8544 | 11 | 4.902 | 3.7674 | 12 | 1.353 | 2.8892 | 9 | 10.89 | 9.5116 | 14 | 6.204 | 16.8482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4.785 | 41 | 75.171 | 34.8989 | 14 | 7.145 | 17.2999 | 9 | 13.9 | 33.9763 | 17 | 5 | 54.2537 | 58 | 42.802 | 55.7971 | 100 | 76.775 | 104.6823 | 0 | 0 | 0 | 0 | 0 | 0 | 155 |  | 158.1439 | 190 |  | 228.6126 | 386.7565
7 | Madarihat-Birpara | 3 | 5640 | 1.1287 | 10 | 12718.28 | 8.0769 | 0 | 0 | 0 | 28 | 3 | 9.4497 | 0 | 0 | 0 | 4 | 2.3 | 2.8772 | 2 | 8 | 1.9305 | 2 | 0 | 0.37305 | 6 | 12608 | 8.3583 | 12 | 6240 | 5.6288 | 5 | 14.94 | 4.8412 | 4 | 2.5 | 1.2075 | 35 | 36.5 | 65.9941 | 46 | 30.98 | 88.0097 | 65 | 92.95 | 65.7816 | 97 | 136.95 | 87.6241 | 0 | 0 | 0 | 0 | 0 | 0 | 116 |  | 148.0344 | 203 |  | 203.2469 | 351.2813
8 | Mal | 18 | 4079.916 | 9.1727 | 24 | 60017.393 | 28.9411 | 8 | 7.59 | 2.0842 | 17 | 6.96 | 2.5092 | 81 | 90.95 | 46.6276 | 39 | 48.983 | 28.1585 | 0 | 0 | 0 | 1 | 160 | 1.4548 | 8 | 4625 | 3.7679 | 8 | 2300 | 8.5122 | 4 | 3.9 | 1.7181 | 7 | 2.795 | 2.6762 | 9 | 9.275 | 16.1595 | 33 | 1041.87 | 18.1907 | 54 | 68.898 | 50.0613 | 51 | 50.639 | 72.8403 | 0 | 0 | 0 | 0 | 0 | 0 | 182 |  | 129.5913 | 180 |  | 163.283 | 292.8742
9 | Matiali | 16 | 16909.3333 | 7.6092 | 13 | 15744.4444 | 7.085 | 0 | 0 | 0 | 7 | 33.0464 | 7.7625 | 19 | 18.2052 | 11.7515 | 44 | 64.2172 | 39.9601 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2967.3143 | 1.0386 | 17 | 16884.8286 | 5.9097 | 6 | 15.6378 | 3.7952 | 12 | 21.0072 | 5.5338 | 2 | 1.2737 | 0.7674 | 26 | 65.6208 | 64.5789 | 21 | 21.9375 | 13.6396 | 39 | 31.1675 | 23.0744 | 0 | 0 | 0 | 0 | 0 | 0 | 66 |  | 38.6015 | 158 |  | 153.9043 | 192.5058
10 | Maynaguri | 7 | 2541 | 3.3584 | 37 | 49202.5 | 15.7921 | 4 | 2.5 | 1.7901 | 152 | 89.5 | 18.1121 | 1 | 0.2 | 0 | 1 | 0.6 | 0.43687 | 1 | 0 | 0.70226 | 9 | 6008 | 4.6516 | 4 | 15000 | 0.58311 | 5 | 5630 | 1.7683 | 0 | 0 | 0 | 7 | 3.5 | 1.5581 | 7 | 5 | 4.6943 | 11 | 15.8 | 2.3834 | 47 | 43.08 | 24.1344 | 95 | 103.975 | 55.5285 | 0 | 0 | 0 | 0 | 0 | 0 | 71 |  | 35.2625 | 317 |  | 100.231 | 135.4935
11 | Nagrakata | 10 | 31200 | 12.7286 | 0 | 0 | 0 | 27 | 174.95 | 24.35 | 1 | 0.8 | 0.19125 | 54 | 122.8 | 60.8547 | 6 | 1.75 | 1.3658 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 221.16 | 7.7032 | 3 | 0 | 0 | 3 | 6750 | 2.8278 | 3 | 2300 | 1.1489 | 17 | 13.33 | 20.6176 | 4 | 1 | 18.312 | 57 | 66 | 82.4187 | 10 | 3.5 | 5.6553 | 0 | 0 | 0 | 0 | 0 | 0 | 182 |  | 211.5007 | 27 |  | 26.6732 | 238.1739
12 | Rajganj | 1 | 1133.41 | 0.39175 | 2 | 2292 | 0.019 | 8 | 31.8 | 0.61664 | 41 | 10719.51 | 9.691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6.25 | 7.7544 | 0 | 0 | 0 | 1 | 1.2 | 1.6104 | 1 | 2 | 0 | 0 | 0 | 0 | 3 | 0.6 | 0.52437 | 26 | 28.45 | 25.0362 | 24 | 36.3 | 34.06 | 0 | 0 | 0 | 0 | 0 | 0 | 46 |  | 35.4094 | 71 |  | 44.2944 | 79.7038
13 | Sadar | 24 | 16353 | 9.5577 | 5 | 3854 | 1.7692 | 11 | 1583.92 | 3.0558 | 42 | 48.19 | 13.616 | 1 | 1 | 0.189 | 0 | 0 | 0 | 2 | 6.82 | 0.6345 | 0 | 0 | 0 | 3 | 9 | 1.224 | 14 | 1147 | 8.8525 | 3 | 2.5 | 1.7083 | 16 | 21.25 | 21.0282 | 5 | 4.75 | 3.8845 | 4 | 7 | 1.5548 | 31 | 1921.69 | 25.9529 | 10 | 9.76 | 6.681 | 0 | 0 | 0 | 0 | 0 | 0 | 80 |  | 46.2066 | 91 |  | 53.5017 | 99.7083
| Total | 215 | 345235.7517 | 133.6662 | 170 | 279454.1265 | 122.3181 | 92 | 1879.9825 | 37.7396 | 352 | 10934.9632 | 69.9897 | 234 | 383.92 | 192.9315 | 123 | 1623.8707 | 103.1981 | 11 | 18.07 | 8.0156 | 14 | 6169.5 | 6.8794 | 68 | 48343.4213 | 46.1166 | 72 | 43307.5407 | 39.8048 | 79 | 6916.2153 | 70.7039 | 75 | 2383.4767 | 62.4346 | 173 | 152.4333 | 281.5888 | 242 | 1237.3555 | 376.2876 | 766 | 2984.2644 | 803.3556 | 679 | 882.5108 | 714.1985 | 0 | 0 | 0 | 0 | 0 | 0 | 1638 | 0 | 1574.1178 | 1727 | 0 | 1476.8905 | 3051.0083
[56 empty] | 1584 |  |  | 1224
[56 empty] | -54 |  |  | -503

## Part-IV
Part-IV
National Rural Employment Gurantee Act (N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2008-09 Up to the Month of September' 08
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Alipurduar-I | 458 | 105 | 0 | 40 | 0 | 60 | 0 | 11 | 3 | 5
2 | Alipurduar-II | 166 | 5 | 163 | 8 | 171 | 0 | 1 | 4 | 0 | 0
3 | Dhupguri | 152 | 10 | 41 | 0 | 41 | 0 | 32 | 0 | 0 | 0
4 | Falakata | 95 | 2 | 36 | 0 | 36 | 4 | 0 | 12 | 0 | 0
5 | Kalchini | 14262 | 225 | 0 | 11 | 0 | 147 | 4 | 18 | 0 | 5
6 | Kumargram | 1512 | 1016 | 842 | 27 | 23 | 34 | 35 | 3 | 0 | 0
7 | Madarihat-Birpara | 316 | 3 | 288 | 30 | 316 | 4 | 17 | 79 | 0 | 0
8 | Mal | 2278 | 69 | 358 | 4 | 355 | 7 | 0 | 0 | 0 | 0
9 | Matiali | 49 | 165 | 3 | 4 | 0 | 0 | 77 | 68 | 0 | 0
10 | Maynaguri | 35 | 15 | 0 | 0 | 35 | 15 | 165 | 0 | 0 | 0
11 | Nagrakata | 50 | 10 | 7 | 7 | 0 | 0 | 5 | 5 | 0 | 0
12 | Rajganj | 459 | 0 | 44 | 0 | 38 | 0 | 102 | 0 | 0 | 0
13 | Sadar | 101 | 5 | 45 | 5 | 24 | 0 | 2 | 1 | 0 | 0
| Total | 19933 | 1630 | 1827 | 136 | 1039 | 271 | 440 | 201 | 3 | 10

## Part-V-A
MPR Part - V-A
National Rural Employment Guarantee Act (NREGA)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the month of September' 2008)
Jalpaiguri District
Sl. No | Name of the BLOCK / GP | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | Alipurduar-I | 11 | 8 | 1 | 1 | 7 | 7 | 1 | 1 | 1 | 1
2 | Alipurduar-II | 11 | 8 | 1 | 1 | 5 | 5 | 1 | 1 | 1 | 1
3 | Dhupguri | 16 | 14 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1
4 | Falakata | 12 | 9 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
5 | Kalchini | 11 | 9 | 1 | 1 | 6 | 5 | 1 | 1 | 1 | 1
6 | Kumargram | 11 | 9 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
7 | Madarihat-Birpara | 10 | 6 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1
8 | Mal | 12 | 6 | 2 | 2 | 7 | 7 | 3 | 3 | 1 | 1
9 | Matiali | 5 | 5 | 1 | 1 | 5 | 5 | 1 | 1 | 1 | 1
10 | Maynaguri | 16 | 15 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
11 | Nagrakata | 5 | 3 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1
12 | Rajganj | 12 | 6 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
13 | Sadar | 14 | 11 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 1
| Total: | 146 | 109 | 11 | 11 | 44 | 42 | 15 | 15 | 13 | 13 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1

## Part-V-B
MPR Part - V-B
National Rural Employment Guarantee Act (NREGA)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the month of September' 2008)
Jalpaiguri District
Sl. No | Name of the BLOCK / GP | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1 | Alipurduar-I | 8 | 8 | 1 | 0 | 7 | 0 | 1 | 0 | 1 | 0 | [10 empty] | 0 | 0 | 0 | 0
2 | Alipurduar-II | 8 | 0 | 1 | 1 | 5 | 5 | 0 | 1 | 0 | 1 | [10 empty] | 55 | 33 | 0 | 0
3 | Dhupguri | 14 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 291 | 291 | 17 | 17
4 | Falakata | 9 | 0 | 1 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | [10 empty] | 213 | 204 | 0 | 0
5 | Kalchini | 9 | 0 | 1 | 0 | 5 | 2 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0
6 | Kumargram | 9 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 0 | [10 empty] | 0 | 0 | 0 | 0
7 | Madarihat-Birpara | 6 | 0 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1
8 | Mal | 6 | 0 | 2 | 2 | 7 | 7 | 3 | 3 | 1 | 1 | [10 empty] | 202 | 202 | 573 | 0
9 | Matiali | 5 | 0 | 1 | 1 | 5 | 5 | 1 | 1 | 1 | 1 | [10 empty] | 85 | 85 | 0 | 0
10 | Maynaguri | 15 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 4
11 | Nagrakata | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 1 | 1 | [10 empty] | 89 | 0 | 512 | 0
12 | Rajganj | 6 | 0 | 1 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | [10 empty] | 222 | 222 | 3460 | 36160
13 | Sadar | 11 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Total: | 109 | 8 | 13 | 10 | 41 | 28 | 12 | 13 | 10 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1157 | 1037 | 4562 | 36177 | 0