## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
part I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of Dec' 2016 (for the financial year 2016-17)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals |  |  | 1.85
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 | 3 | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Dhupguri | 97570 | 35966 | 15341 | 44788 | 96095 | 53373 |  | 49994 | 2565 |  | 5.0317 | 2.2721 | 5.8811 | 13.1849 | 5.6133 |  | 212 | 445 | 89 | 42.5736 | 26.373
2 | Jalpaiguri | 67207 | 33709 | 2864 | 29436 | 66009 | 31511 |  | 29097 | 2319 |  | 4.3795 | 0.39021 | 2.9868 | 7.7565 | 3.4585 |  | 112 | 161 | 23 | 62.0962 | 21.2104
3 | Mal | 65969 | 14925 | 16946 | 32706 | 64577 | 36983 |  | 33841 | 5829 |  | 2.6325 | 2.7651 | 5.3026 | 10.7002 | 5.2625 |  | 263 | 284 | 21 | 49.1808 | 31.6191
4 | Matiali | 28121 | 3841 | 10583 | 13043 | 27467 | 16900 |  | 15804 | 615 |  | 0.85579 | 1.8272 | 2.4197 | 5.1026 | 2.7097 |  | 127 | 1638 | 6 | 53.104 | 32.287
5 | Maynaguri | 74913 | 43412 | 800 | 30116 | 74328 | 40993 |  | 38142 | 3216 |  | 6.7628 | 0.13165 | 4.0037 | 10.8981 | 5.0162 |  | 69 | 902 | 55 | 46.0276 | 28.5726
6 | Nagrakata | 28565 | 4373 | 13260 | 10665 | 28298 | 17017 |  | 15622 | 2535 |  | 0.91115 | 1.9724 | 2.136 | 5.0195 | 2.3385 |  | 26 | 503 | 26 | 46.5874 | 32.1312
7 | Rajganj | 58434 | 25223 | 1775 | 30418 | 57416 | 20939 |  | 19402 | 1672 |  | 2.7388 | 0.23983 | 3.5873 | 6.5659 | 3.1717 |  | 276 | 209 | 53 | 48.3058 | 33.8412
| Total: | 420779 | 161449 | 61569 | 191172 | 414190 | 217716 | 0 | 201902 | 18751 | 0 | 23.3122 | 9.5985 | 26.3171 | 59.2278 | 27.5703 | 0 | 1085 | 4142 | 273 | 46.5496 | 29.3349
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2016-17 Up to the Month of Dec' 2016
2099.74
Sl. No. | Name of the Block | Actual O.B. as on 01.04.16 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Authorization of efms | Total Availability | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh) | [6 empty] | #REF!
|  |  | Central | State | Central | State |  |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (10+11+12+13+14)
[14 empty] | Recurring | Non-Recurring |  |  | 4.32 |  |  |  |  | avg. gp
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | [8 empty] | WAGE% | PER LABOUR
1 | Dhupguri | -1.46 | [5 empty] | 4091.77 | 2516.54 |  | 3420.36 | 201.46 | 430.17 | 21.68 | 2.89 | 4076.56 |  | 37.1035 | #REF! | #REF! | 946.3318 | 16 | 254.785 | 370.5964 | 83.9031 | 259.4147 | Dhupguri | 831.2044
2 | Jalpaiguri | -4.51 | [5 empty] | 2105.32 | 1284.26 |  | 1866.11 | 69.05 | 130.05 | 31.78 | 2.75 | 2099.74 |  | 19.1111 | #REF! | #REF! | 394.9049 | 12 | 174.9783 | 190.8855 | 88.8734 | 240.5854 | Malbazar | 402.7251
3 | Mal | -17.56 | [5 empty] | 2804.61 | 1437.71 |  | 2431.63 | 115.36 | 211.04 | 27.22 | 0 | 2785.25 |  | 25.3504 | #REF! | #REF! | 329.2062 | 5 | 557.05 | 253.2045 | #REF! | #REF! | Matiali | 230.7365
4 | Matiali | -3.82 | [5 empty] | 1791.16 | 774.5 |  | 1356.86 | 55.33 | 248.3 | 16.65 | 0 | 1677.14 |  | 15.2648 | 291.727 | 1648.587 | 421.4004 | 16 | 104.8213 | 152.4673 | 80.9032 | 265.9139 | Maynaguri | 677.9344
5 | Maynaguri | 14.17 | [5 empty] | 3392.68 | 2093.76 |  | 2832.13 | 146.01 | 387.23 | 15.4 | 0 | 3380.77 |  | 30.7706 | 780.0484 | 3612.1784 | 284.0694 | 5 | 676.154 | 307.3427 | #REF! | #REF! | Nagrakata | 243.0925
6 | Nagrakata | 0.11 | [5 empty] | 1771.75 | 780 |  | 1355.26 | 91.11 | 284.5 | 9.3 | 2.14 | 1742.31 | 51.1913 | 15.8579 | 242.0675 | 1597.3275 | 217.4445 | 12 | 145.1925 | 158.3918 | 77.7852 | 269.9974 | Rajganj | 282.2
7 | Rajganj | 13.56 | [5 empty] | 1477.22 | 753.26 |  | 1355.3 | 40.47 | 39.59 | 8.9 | 2.16 | 1446.42 |  | 13.1648 | 405.0903 | 1760.3903 | 551.7063 | 14 | 103.3157 | 131.4927 | 93.7003 | 206.4162 | Sadar | 641.197
| Total | 0.49 | 0 | 0 | 0 |  | 0 | 17434.51 | 9640.03 | 0 | 14617.65 | 718.79 | 1730.88 | 130.93 | 9.94 | 17208.19 |  | 18.82 |  |  |  | 80 | 215.1024 | 1564.3809 | 84.9459
1 | Line Deptt. | 18.9 | [5 empty] | 0.78 | 19.68 |  | 0 | 0.86 | 0 |  |  | 0.86 | [5 empty] | 17068.18 |  | 117.8643
2 | District Cell | 8.45 | [5 empty] | 205.15 | 213.6 |  |  |  |  | 205.15 |  | 205.15 |  | 57.61
| Total | 27.35 |  |  | 0 |  |  | 17640.44 |  |  | 14617.65 | 719.65 | 1730.88 | 336.08 | 9.94 | 17414.2 |  | 53.61
| G.T. | 27.84 | 0 | 0 | 0 | 0 | 0 | 17640.44 | 17668.28 | 0 | 14617.65 | 719.65 | 1730.88 | 336.08 | 9.94 | 17414.2 |  | 100
17068.18
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2016-17 Up to the Month of Dec' 2016 | [19 empty] | Physical Performance Under NREGA During the year 2016-17 Up to the Month of Dec' 2016 | [17 empty] | Physical Performance Under NREGA During the year 2016-17 Up to the Month of Dec' 2016
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 56 | 227143.4148 | 216.15 | 219 | 21683.3737 | 1021.43 | 157 | 86.02 | 86.02 | 812 | 5.1 | 44.6 | 26 | 50.3258 | 2088.93 | 560 | 201.1163 | 1517.54 | 73 | 14 | 124.3827 | 656 | 13 | 48.5839 | 60 | 17662.9032 | 75.34 | 58 | 67288.3052 | 278.77 | 76 | 453.8698 | 2227.89 | 248 | 116.148 | 3848.22 | 238 | 1483.2643 | 116.11 | 557 | 134.2669 | 287.29 | 17 | 427.5677 | 127.87 | 375 | 288.1596 | 4324.38 | 495 | 358.4 | 288.32 | 1901 | 502 | 346.35 | 1198 | 5351.0127 | 5386 | 11717.1639
17068.1767
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri
[17 empty] | & | [17 empty] | & | [22 empty] | &
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2016-17 Up to the Month of Dec' 2016
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Dhupguri | 1207.6756 | 4830.7025 | 267 | 9 | 0 | 0.1 | 0 | 1 | 12 | 12
2 | Jalpaiguri | 10933 | 120 | 0 | 14 | 341 | 16 | 0 | 28 | 0 | 0
3 | Mal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Matiali | 0 | 33 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 1
5 | Maynaguri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
6 | Nagrakata | 0 | 0 | 10 | 0 | 0 | 0 | 5 | 0 | 0 | 0
7 | Rajganj | 13940 | 1247 | 2 | 10 | 1266 | 65 |  |  | 0 | 0
| Total | 26080.6756 | 6230.7025 | 279 | 33 | 1607 | 86.1 | 5 | 29 | 14 | 13
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of Dec' 2016)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 146 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 11 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of Dec' 2016)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 141 | 141 | 13 | 13 | 59 | 59 | 13 | 13 | 13 | 13 | 5 | 5 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2406 | 2406 | 3085 | 3085
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
Dec 2016
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
1 | Dhupguri | 12520 | 102 | 1742.87 | 1059 | 3980 | 1677.49 | 3420.36 | 3420.36 | 0
2 | Jalpaiguri | 1279 | 8 | 1866.11 | 32627 | 1377 | 0 | 1866.11 | 1866.11 | 0
3 | Mal | 0 | 0 | 0 | 52395 | 501 | 2431.6292 | 2431.6292 | 2431.63 | -0.00075
4 | Matiali | 6051 | 0 | 404.1809 | 61904 | 0 | 952.6744 | 1356.8554 | 1356.86 | -0.00465
5 | Maynaguri | 3078 | 0 | 1689.8142 | 29453 | 0 | 1142.3149 | 2832.1292 | 2832.13 | -0.00082
6 | Nagrakata | 4331 | 0 | 13.8256 | 51097 | 0 | 1341.4394 | 1355.265 | 1355.26 | 0.00497
7 | Rajganj | 4056 | 0 | 44.51 | 59535 | 0 | 1310.79 | 1355.3 | 1355.3 | 0
8 | Line dep. |  |  | 0 |  |  | 0 | 0 | 0 | 0
Total |  | 31315 | 110 | 5761.3207 | 288070 | 5858 | 8856.328 | 14617.6488 | 14617.65 | -0.00125
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri