## Part-I
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
part I
MONTHLY PROGRESS REPORT
Employment Generation Report for the month of June 2016 (for the financial year 2016-17)
1 | 2 |  | 3 |  |  |  | 4 | 5 | 6 | 7 | 8 | 9 | [5 empty] | 10 | 11 | 12
|  |  | a | b | c | d |  | 5 | 6 | 7 | 8 | a | b | c | d | e
Sl. No. | Block | Application Registered | Cumulative No of HH issued jobcards (Till the reporting month) |  |  |  | Cumulative No of HH demanded employment (Till the reporting month) | Cumulative Labour Budget estimation of employment provided (Till the reporting month) | Cumulative No of HH provided employment (Till the reporting month) | No. of HH working under NREGA during the reporting month | Cumulative Labour Budget estimation of persondays (Till the reporting month) | Cumulative Persondays generated (in Lakhs) (till the reporting month) | [5 empty] | Cumulative No of HH completed 100 days (Till the reporting month | No. of HH which are beneficiary of land reform/ IAY | No. of Disabled beneficiary individuals |  |  | 1.85
|  |  | SC | ST | Others | Total | [6 empty] | ST | Others | Total | Women | Minorities out of Col. 9C |  |  |  | WOMEN % | avg. days | bar: 9
1 | 2 | 3 | 3a | 3b | 3c | 3d | 4 | 5 | 6 | 7 | 8 | 9a | 9b | 9c | 9d | 9e | 9f | 10 | 11 | 12
1 | Dhupguri | 97570 | 35831 | 15220 | 44500 | 95551 | 28784 |  | 14564 | 14559 |  | 0.79745 | 0.38613 | 1.0136 | 2.1972 | 0.93574 |  | 0 | 178 | 14 | 42.5886 | 15.0862
2 | Jalpaiguri | 67207 | 33675 | 2858 | 29324 | 65857 | 18036 |  | 13037 | 11700 |  | 1.1363 | 0.07117 | 0.83361 | 2.0411 | 0.88523 |  | 0 | 67 | 6 | 62.0962 | 21.2104
3 | Mal | 65969 | 14872 | 16893 | 32463 | 64228 | 16717 |  | 9795 | 9155 |  | 0.21591 | 0.50847 | 0.73218 | 1.4566 | 0.63339 |  | 0 | 39 | 3 | 43.4853 | 14.8704
4 | Matiali | 28121 | 3829 | 10440 | 12999 | 27268 | 11259 |  | 5783 | 5536 |  | 0.22567 | 0.32209 | 0.55713 | 1.1049 | 0.59748 |  | 0 | 429 | 3 | 54.076 | 19.1058
5 | Maynaguri | 74913 | 42660 | 796 | 30726 | 74182 | 21757 |  | 10749 | 10261 |  | 0.97637 | 0.00941 | 0.72845 | 1.7142 | 0.68805 |  | 0 | 59 | 6 | 40.1376 | 15.9478
6 | Nagrakata | 28565 | 4362 | 13227 | 10613 | 28202 | 9722 |  | 6505 | 6454 |  | 0.17631 | 0.36854 | 0.44668 | 0.99153 | 0.45651 |  | 0 | 10 | 5 | 46.041 | 15.2426
7 | Rajganj | 58434 | 25161 | 1768 | 30092 | 57021 | 11687 |  | 7920 | 7116 |  | 0.63083 | 0.05662 | 0.75077 | 1.4382 | 0.71184 |  | 0 | 89 | 30 | 49.4945 | 18.1593
| Total: | 420779 | 160390 | 61202 | 190717 | 412309 | 117962 | 0 | 68353 | 64781 | 0 | 4.1589 | 1.7224 | 5.0624 | 10.9437 | 4.9082 | 0 | 0 | 871 | 67 | 44.8499 | 16.0106
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-II
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Financial Performance Under NREGA During the year 2016-17 Up to the Month of June' 2016
1263.48
Sl. No. | Name of the Block | Actual O.B. as on 01.04.16 | Released last year but received during the current year |  | Release During the Current year |  | Misc. Receipt | Authorization of efms | Total Availability | Cumulative Labour Budget estimation of Total Expenditure (Till the reporting month) | Cummulative Expenditure (Rs. in lakh) | [6 empty] | #REF!
|  |  | Central | State | Central | State |  |  |  |  | On unskilled wage | On semi-skilled and skilled wage | On material | Admistrative Expenses |  | Total (10+11+12+13+14)
[14 empty] | Recurring | Non-Recurring |  |  | 4.32 |  |  |  |  | avg. gp
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | [8 empty] | WAGE% | PER LABOUR
1 | Dhupguri | -1.46 | [5 empty] | 2379.49 | 2516.54 |  | 2142.38 | 181.11 | 41.06 | 0 | 0 | 2364.55 |  | 21.5213 | #REF! | #REF! | 946.3318 | 16 | 147.7844 | 214.9591 | 90.6041 | 975.0678 | Dhupguri | 831.2044
2 | Jalpaiguri | -4.51 | [5 empty] | 1267.78 | 1284.26 |  | 1143.5 | 61.85 | 41.32 | 14.7 | 2.11 | 1263.48 |  | 11.4998 | #REF! | #REF! | 394.9049 | 12 | 105.29 | 114.8618 | 90.504 | 560.2344 | Malbazar | 402.7251
3 | Mal | -17.56 | [5 empty] | 1420.67 | 1437.71 |  | 1138.61 | 96.57 | 145.14 | 20.44 | 0 | 1400.76 |  | 12.7492 | #REF! | #REF! | 329.2062 | 5 | 280.152 | 127.3418 | #REF! | #REF! | Matiali | 230.7365
4 | Matiali | -3.82 | [5 empty] | 740.32 | 774.5 |  | 479.48 | 45.16 | 116.6 | 3.1 | 0 | 644.34 |  | 5.8646 | 67.4412 | 546.9212 | 421.4004 | 16 | 40.2713 | 58.5764 | 74.4141 | 433.9618 | Maynaguri | 677.9344
5 | Maynaguri | 14.17 | [5 empty] | 1803.94 | 2093.76 |  | 1643.43 | 116.57 | 18.89 | 15.4 | 0 | 1794.29 |  | 16.331 | 208.2083 | 1851.6383 | 284.0694 | 5 | 358.858 | 163.1173 | #REF! | #REF! | Nagrakata | 243.0925
6 | Nagrakata | 0.11 | [5 empty] | 746.49 | 780 |  | 548.88 | 78.61 | 85.56 | 4.97 | 0 | 718.02 | 51.1913 | 6.5352 | 38.326 | 587.206 | 217.4445 | 12 | 59.835 | 65.2745 | 76.4436 | 553.5687 | Rajganj | 282.2
7 | Rajganj | 13.56 | [5 empty] | 672.29 | 753.26 |  | 572.07 | 34.43 | 28.36 | 4.83 | 2.16 | 641.85 |  | 5.8419 | 95.4043 | 667.4743 | 551.7063 | 14 | 45.8464 | 58.35 | 89.1283 | 397.7625 | Sadar | 641.197
| Total | 0.49 | 0 | 0 | 0 |  | 0 | 9030.98 | 9640.03 | 0 | 7668.35 | 614.3 | 476.93 | 63.44 | 4.27 | 8827.29 |  | 18.82 |  |  |  | 80 | 110.3411 | 802.4809 | 86.8709
1 | Line Deptt. | 18.9 | [5 empty] | 0.78 | 19.68 |  | 0 | 0.86 | 0 |  |  | 0.86 | [5 empty] | 8760.44 |  | 60.4609
2 | District Cell | 8.45 | [5 empty] | 52.05 | 60.5 |  |  |  |  | 52.05 |  | 52.05 |  | 57.61
| Total | 27.35 |  |  | 0 |  |  | 9083.81 |  |  | 7668.35 | 615.16 | 476.93 | 115.49 | 4.27 | 8880.2 |  | 53.61
| G.T. | 27.84 | 0 | 0 | 0 | 0 | 0 | 9083.81 | 9111.65 | 0 | 7668.35 | 615.16 | 476.93 | 115.49 | 4.27 | 8880.2 |  | 100
8760.44
[13 empty] | District Programme Coordinator |  |  |  |  | 8760.44
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-III.
[16 empty] | MPR Part-III | [18 empty] | MPR Part-III | [22 empty] | MPR Part-III
Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [19 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.) | [17 empty] | Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT | [19 empty] | MONTHLY PROGRESS REPORT | [17 empty] | MONTHLY PROGRESS REPORT
Physical Performance Under NREGA During the year 2016-17 Up to the Month of June 2016 | [19 empty] | Physical Performance Under NREGA During the year 2016-17 Up to the Month of June 2016 | [17 empty] | Physical Performance Under NREGA During the year 2016-17 Up to the Month of June 2016
Jalpaiguri District
|  | 1 | [5 empty] | 2 | [5 empty] | 3 | [5 empty] | 4 | [5 empty] | 5 | [5 empty] | 6 | [5 empty] | 7 | [5 empty] | 8 | [5 empty] | 9 | [5 empty] | 10
Sl. No. | Name of the District | Water Conservation and water harvesting | [5 empty] | Draught Proofing | [5 empty] | Micro Irrigation Works | [5 empty] | Provision of irrigation facility to land owned by…. | [5 empty] | Renovation of traditional water bodies | [5 empty] | Land Development | [5 empty] | Flood Control & Protection | [5 empty] | Rural Connectivity | [5 empty] | Any other activity (approved by MRD) | [5 empty] | Total (Unit in nos. & Exp. be reported in this row)
|  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  |  | Ongoing Works |  |  | Completed works |  | Ongoing Works
|  | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit |  | Expenditure (lac) | Unit | Expenditure (lac) | Unit | Expenditure (lac)
|  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Hec |  | No. | Hec |  | No. | Cu. Mt. |  | No. | Cu. Mt. |  | No. | Hec. |  | No. | Hec. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. | Kms. |  | No. |  |  | No. |  |  | No. |  | No.
| JALPAIGURI | 56 | 227143.4148 | 216.15 | 219 | 21683.3737 | 1021.43 | 157 | 86.02 | 86.02 | 812 | 5.1 | 44.6 | 26 | 50.3258 | 908.43 | 560 | 201.1163 | 517.54 | 73 | 14 | 124.3827 | 656 | 13 | 48.5839 | 60 | 17662.9032 | 75.34 | 58 | 67288.3052 | 278.77 | 76 | 453.8698 | 181.11 | 248 | 116.148 | 1348.22 | 238 | 1483.2643 | 116.11 | 557 | 134.2669 | 287.29 | 17 | 427.5677 | 127.87 | 375 | 288.1596 | 3324.38 | 495 | 358.4 | 288.32 | 1901 | 502 | -234.11 | 1198 | 2123.7327 | 5386 | 6636.7039
[17 empty] | District Programme Coordinator | [17 empty] | District Programme Coordinator | [22 empty] | District Programme Coordinator |  | 8760.4367
[17 empty] | MGNREGS, Jalpaiguri | [17 empty] | MGNREGS, Jalpaiguri | [22 empty] | MGNREGS, Jalpaiguri |  | 8760.44
[17 empty] | & | [17 empty] | & | [22 empty] | & |  | -0.003345
[17 empty] | District Magistrate | [17 empty] | District Magistrate | [22 empty] | District Magistrate
[17 empty] | Jalpaiguri | [17 empty] | Jalpaiguri | [22 empty] | Jalpaiguri

## Part-IV
Part-IV
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
MONTHLY PROGRESS REPORT
Transparency Report Under NREGA During the year 2016-17 Up to the Month of June 2016
Sl. No. | Name of the Block | No. of Muster Rolls verified |  | No. of Social Audits completed |  | No. of inspections conducted (2%, 10%, 100% at the State, District and Block levels |  | No. of Gram Sabhas held |  | No of Complaints disposed by PO, DPCs
|  | Due | Completed | Due | Completed | Due | Completed | Due | Completed | Due | Disposed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Dhupguri | 1207.6756 | 4830.7025 | 267 | 9 | 0 | 0.1 | 0 | 1 | 12 | 12
2 | Jalpaiguri | 10933 | 120 | 0 | 14 | 341 | 16 | 0 | 28 | 0 | 0
3 | Mal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Matiali | 0 | 33 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 1
5 | Maynaguri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
6 | Nagrakata | 0 | 0 | 10 | 0 | 0 | 0 | 5 | 0 | 0 | 0
7 | Rajganj | 13940 | 1247 | 2 | 10 | 1266 | 65 |  |  | 0 | 0
| Total | 26080.6756 | 6230.7025 | 279 | 33 | 1607 | 86.1 | 5 | 29 | 14 | 13
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-A
MPR Part - V-A
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-A (Capacity Building - Personnel Report for the Month of June 2016)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Achievement | Target | Target
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
| Jalpaiguri | 126 | 101 | 5 | 3 | 14 | 12 | 7 | 7 | 7 | 6 | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## Part-V-B
MPR Part - V-B
The Mahatma Gandhi National Rural Employment Gurantee Act (M.G.N.R.E.G.A.)
FORMAT FOR MONTHLY PROGRESS REPORT - V-B (Capacity Building - Training Report for the Month of June 2016)
Jalpaiguri District
Sl. No | Name of the District | Gram Panchayat Level |  | Block Level | [7 empty] | District Level | [9 empty] | PRI Functionaries |  | Vigilance & Monitoring Committee Report
|  | Gram Rozgar Sahayak |  | Accountant |  | Engineers / Technical Assistants |  | Programme Officer |  | Computer Assistant |  | Works Manager & Technical Assistants |  | IT Manager & Computer Assistants |  | Accounts Manager |  | Training Coordinator |  | Coordinator for Social Audit and Grievance Redressal
|  | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained | Nos to be Trained | Nos Trained
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
| Jalpaiguri | 2 | 99 | 0 | 3 | 0 | 12 | 0 | 7 | 0 | 6 | 5 | 5 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 578 | 718 | 17 | 17
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri

## bank & po report
Bank, Postoffice Account Report
June 2016
Sl. No. | Name of the Gram Panchayat | No. of Bank Account opened |  | Amount of Wages disbursed through Bank Accounts (in Rs.) | No. of Post Office Account opened |  | Amount of Wages disbursed through Post Office Accounts (in Rs.)
|  | Individual | Joint |  | Individual | Joint |  |  |  | 0
1 | 2 | 5 | 6 | 7 | 8 | 9 | 10 |  | PARI-II
1 | Dhupguri | 12520 | 102 | 1235.14 | 1059 | 3980 | 907.24 | 2142.38 | 2142.38 | 0
2 | Jalpaiguri | 1279 | 8 | 0 | 32627 | 1377 | 1143.4993 | 1143.4993 | 1143.5 | -0.00073
3 | Mal | 0 | 0 | 0 | 52395 | 501 | 1138.6092 | 1138.6092 | 1138.61 | -0.00075
4 | Matiali | 6051 | 0 | 404.1809 | 61904 | 0 | 75.2944 | 479.4753 | 479.48 | -0.00465
5 | Maynaguri | 3078 | 0 | 1570.8843 | 29453 | 0 | 72.5449 | 1643.4292 | 1643.43 | -0.00082
6 | Nagrakata | 4331 | 0 | 13.8256 | 51097 | 0 | 535.0594 | 548.885 | 548.88 | 0.00497
7 | Rajganj | 4056 | 0 | 44.51 | 59535 | 0 | 527.56 | 572.07 | 572.07 | 0
8 | Line dep. |  |  | 0 |  |  | 0 | 0 | 0 | 0
Total |  | 31315 | 110 | 3268.5507 | 288070 | 5858 | 4399.7973 | 7668.348 | 7668.35 | -0.00198
District Programme Coordinator
MGNREGS, Jalpaiguri
&
District Magistrate
Jalpaiguri